|  |  | System Planning |
| --- | --- | --- |
|  |  | Monthly Status Report February 2014 |
|  | Report Highlights |  |
|  | ERCOT is currently tracking 219 active generation interconnection requests totaling over 55,300 MW. This includes over 26,700 MW of wind generation. |  |
|  | ERCOT is currently reviewing proposed transmission improvements with a total cost of $917.7 Million Transmission Projects endorsed in 2014 total $349.8 Million All projects (in engineering, routing, licensing and construction) total approximately $4.4 Billion. Transmission Projects energized in 2014 total about $123.3 Million. |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Approved for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	5

1.5	Projects Undergoing Full Interconnection Studies with Confidentiality Waived	6

1.6	Generation Projects Undergoing Full Interconnection Studies	6

1.7	Wind Generation Capacity Installed by Year	9

2.	Regional Planning Group Project Reviews	10

3.	Asynchronous Tie Interconnection	10

4.	Planning Model Activities	11

5.	Other Notable Activities	11

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

14INR0059 – Forney Plant Upgrade – 34 MW in Kaufman County

14INR0072 – Briscoe Wind Farm – 300 MW located in Briscoe County

16INR0010 – FGE Texas 1 – 799 MW located in Mitchell County

15INR0032 – Antelope Station CT1 – 197 MW located in Hale County

15INR0033 – Antelope Station CT2 – 197 MW located in Hale County

16INR0003 – Freeport LNG Pretreatment Facility – 11 MW located in Brazoria County

## New Generation Approved for Commercial Operations

No projects have been approved for commercial operations during February 2014.

The total installed wind capacity is now reported as 11,065 MW by the resource owners through the registration process. Capacity by North, South and West is 833 MW, 2,775 MW, and 7,456 MW respectively.  Eight-hundred fifty MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |
| --- |
| Currently tracking 219 generation interconnection or change requests |
| As of February 28, 2014 | Total |
| Security Screening Study | 17 |
| SSS Completed | 28 |
| Full Interconnect Study | 101 |
| FIS Completed | 11 |
| Suspended Studies | 0 |
| Capacity of Suspended Study Projects | 0 |
| Cancelled Projects | 8 |
| Interconnect Agreement Completed | 62 |
| Capacity under Interconnection Agreements | 18,372 |
| Capacity for Grid, MW | 55,321 |
| Wind Capacity, MW | 26,728 |
| Capacity of Cancelled Projects | 2,010 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 1,893 | - | 5,882 |
| Gas-CombinedCycle |  |  | 8,215 | - | 18,620 |
| Total Gas | 3,544 | 11,437 | 9,521 | - | 24,502 |
| Nuclear | - | - | - | - | - |
| Coal | - | 30 | 240 | - | 270 |
| Wind | 5,538 | 12,777 | 8,413 | - | 26,728 |
| Solar | 1,335 | 1,414 | 198 | - | 2,947 |
| Biomass | - | - | - | - | - |
| Storage | - | 874 | - | - | 874 |
| Petroleum Coke | - | - | - | - | - |
| Grand Total | 10,417 | 26,532 | 18,372 | - | 55,321 |

Cumulative Installed MW Capacity of Interconnection Requests by Zone

## Projects with Interconnection Agreements

| Generation Interconnection Agreements as of February 28, 2014 |  |
| --- | --- |
| INR | Site Name | County | COD | Fuel | MW For Grid | Change from Last Report | Sufficient Financial Security Received by TSP |
| 11INR0013 | Goldthwaite Wind Energy | Mills | Apr-14 | WIND | 149 |  | No |
| 13INR0048 | Spinning Spur Wind Two | Oldham | Jun-14 | WIND | 161 |  | Yes |
| 11INR0094 | White Camp Solar | Kent | Jun-14 | SOLAR | 100 | Date Change | No |
| 14INR0015 | Deer Park Energy Center | Harris | Jul-14 | GAS | 190 |  | Yes |
| 14INR0030a_2 | Panhandle Wind | Carson | Jul-14 | WIND | 218 | Date Change | Yes |
| 14INR0012a | Miami Wind 1 Project | Gray | Jul-14 | WIND | 289 |  | Yes |
| 13INR0021 | Ferguson Replacement Project | Llano | Jul-14 | GAS | 570 |  | Yes |
| 10INR0020a | Panda Temple Power | Bell | Aug-14 | GAS | 717 |  | Yes |
| 13INR0040 | Rentech Project | Harris | Aug-14 | GAS | 15 |  | Yes |
| 10INR0021 | Panda Sherman Power | Grayson | Aug-14 | GAS | 720 |  | Yes |
| 14INR0059 | Forney Power Plant Upgrade | Kaufman | Aug-14 | GAS | 34 | New | No |
| 11INR0050 | Moore Wind 1 | Crosby | Aug-14 | WIND | 149 |  | No |
| 14INR0024 | OCI Alamo 4 | Kinney | Aug-14 | SOLAR | 38 | Date Change | Yes |
| 13INR0059a | Hereford Wind | Castro | Sep-14 | WIND | 200 |  | Yes |
| 12INR0034a | Stephens Ranch Wind Energy Phase 1 | Borden | Oct-14 | WIND | 201 | New | Yes |
| 13INR0010a | Mariah Wind | Parmer | Oct-14 | WIND | 232 |  | No |
| 12INR0059 | Barilla Solar | Pecos | Nov-14 | SOLAR | 30 |  | Yes |
| 14INR0032a | Route66 Wind | Randall | Dec-14 | WIND | 150 |  | Yes |
| 14INR0023 | Longhorn Energy Center | Briscoe | Dec-14 | WIND | 361 |  | Yes |
| 13INR0005 | Conway Windfarm | Carson | Dec-14 | WIND | 600 |  | Yes |
| 13INR0052 | Los Vientos III | Starr | Dec-14 | WIND | 200 |  | Yes |
| 06INR0022c | Baffin (Penascal Wind Farm 3) | Kenedy | Dec-14 | WIND | 202 |  | Yes |
| 14INR0053 | Spinning Spur Wind Three | Oldham | Dec-14 | WIND | 194 |  | Yes |
| 14INR0049_2 | Keechi Wind 138 kV Joplin | Jack | Dec-14 | WIND | 102 |  | Yes |
| 13INR0057 | Windthorst 2 | Archer | Dec-14 | WIND | 65 |  | No |
| 11INR0079a | South Clay Windfarm | Clay | Dec-14 | WIND | 200 |  | No |
| 09INR0051 | Mesquite Creek | Borden | Jan-15 | WIND | 249 |  | Yes |
| 12INR0070 | Green Pastures | Knox | Feb-15 | WIND | 300 |  | Yes |
| 12INR0068 | Sendero Wind Energy Project | Jim Hogg | Feb-15 | WIND | 78 |  | Yes |
| 12INR0034b | Stephens Ranch Wind Energy Phase b | Borden | Apr-15 | WIND | 177 | New | No |
| 13INR0059b | Jumbo Road Wind | Castro | Apr-15 | WIND | 300 |  | Yes |
| 14INR0038 | PHR Peakers | Galveston | Apr-15 | GAS | 390 |  | No |
| 13INR0020a | CPV Rattlesnake Den Ph 1 | Glasscock | May-15 | WIND | 201 |  | Yes |
| 13INR0050 | Logans Gap Wind I | Comanche | May-15 | WIND | 200 |  | No |
| 14INR0039 | Goldsmith Peaking Facility | Ector | Jun-15 | GAS | 408 |  | No |
| 11INR0057 | Cameron County Wind | Cameron | Jun-15 | WIND | 165 |  | Yes |
| 14INR0025a | South Plains Wind I | Floyd | Jul-15 | WIND | 200 | Date Change | No |
| 08INR0018 | Gunsight Mountain | Howard | Aug-15 | WIND | 120 |  | No |
| 10INR0020b | Panda Temple Power | Bell | Aug-15 | GAS | 717 |  | No |
| 14INR0012b | Miami Wind 1 Project | Gray | Aug-15 | WIND | 111 |  | No |
| 11INR0062 | Patriot (Petronilla) Wind | Nueces | Aug-15 | WIND | 178 |  | Yes |
| 13INR0049 | Friendswood Energy Generation | Harris | Sep-15 | GAS | 316 |  | No |
| 11INR0054 | Midway Farms Wind | San Patricio | Oct-15 | WIND | 161 |  | Yes |
| 14INR0030b | Panhandle Wind 2 (Phase 2) | Carson | Nov-15 | WIND | 182 | Date/MW change | Yes |
| 14INR0025b | South Plains II | Floyd | Dec-15 | WIND | 300 |  | No |
| 14INR0072 | Briscoe Wind Farm | Briscoe | Dec-15 | WIND | 300 | New | Yes |
| 13INR0010b | Mariah Wind | Parmer | Dec-15 | WIND | 200 |  | No |
| 13INR0031 | Mustang Solar Project | Travis | Dec-15 | SOLAR | 30 |  | No |
| 13INR0020b | CPV Rattlesnake Den Ph 2 | Glasscock | May-16 | WIND | 150 |  | No |
| 16INR0010 | FGE Texas 1 | Mitchell | Jun-16 | GAS | 799 | New | No |
| 13INR0028 | Antelope Station | Hale | Jun-16 | GAS | 359 |  | No |
| 15INR0033 | Antelope Station CT2 | Hale | Jul-16 | GAS | 197 | New | No |
| 15INR0032 | Antelope Station CT1 | Hale | Jul-16 | GAS | 197 | New | No |
| 06INR0006 | Cobisa-Greenville | Hunt | Dec-16 | GAS | 1792 |  | No |
| 13INR0010c | Mariah Wind | Parmer | Dec-16 | WIND | 168 |  | No |
| 12INR0029 | Comanche Run Wind | Swisher | Dec-16 | WIND | 500 |  | No |
| 12INR0018 | Pampa Wind Project | Gray | Mar-17 | WIND | 500 |  | No |
| 10INR0022 | Pondera King Power Project | Harris | Jun-17 | GAS | 1629 | Date Change | No |
| 16INR0003 | Freeport LNG PreTreatment Facility | Brazoria | Jun-17 | GAS | 11 | New | No |
| 13INR0023 | Texas Clean Energy Project | Ector | Jun-18 | COAL | 240 |  | No |

## Projects Undergoing Full Interconnection Studies with Confidentiality Waived

| INR | Site Name | County | COD | Fuel | MW for Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- |

## Generation Projects Undergoing Full Interconnection Studies

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 14INR0076 | Galveston | GAS | 5 | Jun-14 |
| 14INR0069 | Milam | COAL | 30 | Aug-14 |
| 13INR0055 | Zapata | WIND | 250 | Sep-14 |
| 14INR0013 | Cameron | WIND | 103 | Oct-14 |
| 13INR0036 | Hidalgo | WIND | 200 | Oct-14 |
| 13INR0056 | Scurry | WIND | 366 | Nov-14 |
| 14INR0066 | Lamar | GAS | 130 | Nov-14 |
| 14INR0009 | Kent | WIND | 248 | Dec-14 |
| 14INR0028 | Live Oak | WIND | 300 | Dec-14 |
| 10INR0085 | Ector | SOLAR | 57 | Dec-14 |
| 14INR0043 | Sterling | SOLAR | 40 | Dec-14 |
| 15INR0074 | Deaf Smith/Randall/Castro | WIND | 156 | Dec-14 |
| 14INR0056 | Mills | WIND | 101 | Dec-14 |
| 14INR0057b | Erath | WIND | 48 | Dec-14 |
| 13INR0010d | Parmer | WIND | 200 | Dec-14 |
| 14INR0048_2 | Wilbarger | WIND | 250 | Dec-14 |
| 12INR0045 | Kleberg | WIND | 135 | Dec-14 |
| 12INR0055 | Baylor | WIND | 40 | Dec-14 |
| 14INR0048_1 | Wilbarger | WIND | 114 | Dec-14 |
| 14INR0057a | Erath | WIND | 48 | Dec-14 |
| 14INR0049_1 | Jack | WIND | 102 | Dec-14 |
| 14INR0045a | Webb | WIND | 502 | Dec-14 |
| 14INR0014 | Val Verde | SOLAR | 100 | Jan-15 |
| 14INR0047 | Floyd and Crosby | WIND | 301 | Feb-15 |
| 14INR0050 | Uvalde | SOLAR | 40 | Mar-15 |
| 15INR0036 | Uvalde | SOLAR | 105 | Mar-15 |
| 15INR0069 | Pecos | SOLAR | 110 | Mar-15 |
| 14INR0020 | Floyd & Motley | WIND | 150 | Mar-15 |
| 15INR0070_2 | Pecos | SOLAR | 110 | Mar-15 |
| 15INR0070_1 | Pecos | SOLAR | 110 | Mar-15 |
| 10INR0009 | Castro | WIND | 300 | Mar-15 |
| 15INR0054 | Reeves | GAS | 123 | May-15 |
| 15INR0055 | Austin | GAS | 142 | May-15 |
| 15INR0053 | Winkler | GAS | 123 | May-15 |
| 15INR0021 | Starr | WIND | 200 | May-15 |
| 14INR0041a | Willacy | Wind | 115 | Jun-15 |
| 15INR0027 | Hidalgo | Gas | 79 | Jun-15 |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 15INR0028 | Freestone | Gas | 160 | Jun-15 |
| 13INR0026 | Oldham | Wind | 201 | Jun-15 |
| 14INR0040 | Hidalgo | Gas | 225 | Jun-15 |
| 15INR0023 | Wharton | Gas | 700 | Jun-15 |
| 11INR0082a | Val Verde | Wind | 50 | Jul-15 |
| 13INR0054 | Bee | Gas | 25 | Jul-15 |
| 13INR0025 | Randall | Wind | 150 | Sep-15 |
| 14INR0026 | Presidio | Solar | 30 | Sep-15 |
| 14INR0062 | Gray | Wind | 200 | Sep-15 |
| 15INR0068 | Sterling | Solar | 20 | Oct-15 |
| 14INR0030a_1 | Carson | Wind | 322 | Nov-15 |
| 12INR0060 | Schleicher | Wind | 58 | Dec-15 |
| 15INR0042 | Hood | Gas | 460 | Dec-15 |
| 15INR0034 | San Patricio | Wind | 201 | Dec-15 |
| 14INR0044 | Reeves | Solar | 100 | Dec-15 |
| 15INR0035 | Kenedy | Wind | 200 | Dec-15 |
| 08INR0019a | Gray | Wind | 250 | Dec-15 |
| 11INR0065 | Nueces | Wind | 350 | Dec-15 |
| 14INR0041b | Willacy | Wind | 115 | Dec-15 |
| 11INR0082b | Val Verde | Wind | 150 | Dec-15 |
| 15INR0051 | Castro | Wind | 200 | Dec-15 |
| 14INR0060 | Haskell | Wind | 400 | Dec-15 |
| 15INR0073 | Armstrong/Carson | Wind | 170 | Dec-15 |
| 15INR0037 | Starr | Wind | 200 | Dec-15 |
| 15INR0059 | Pecos / Crane | Solar | 102 | Dec-15 |
| 13INR0045 | Castro | Wind | 288 | Dec-15 |
| 13INR0032 | Andrews | Solar | 30 | Dec-15 |
| 13INR0038 | Swisher | Wind | 300 | Dec-15 |
| 14INR0018 | Nolan | Solar | 20 | Dec-15 |
| 12INR0002a | Briscoe | Wind | 200 | Dec-15 |
| 15INR0044 | Webb and Duval | Solar | 200 | Dec-15 |
| 11INR0093 | San Patricio | Wind | 41 | Dec-15 |
| 15INR0049 | Zapata / Webb | Wind | 250 | Dec-15 |
| 14INR0033 | Armstrong | Wind | 500 | Dec-15 |
| 13INR0010e | Parmer | Wind | 200.00 | Dec-15 |
| 14INR0045b | Webb | Wind | 251.00 | Dec-15 |
| 16INR0036 | Nolan | Gas | 280.00 | Apr-16 |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 16INR0009 | Calhoun | Gas | 510.00 | Apr-16 |
| 16INR0008 | Grimes | Gas | 687.00 | May-16 |
| 17INR0004 | Hale | Gas | 202.00 | Jun-16 |
| 14INR0027 | Guadalupe | Gas | 471.00 | Jun-16 |
| 16INR0006 | Angelina | Gas | 785.00 | Jun-16 |
| 16INR0005 | Cameron | Gas | 871.00 | Jun-16 |
| 15INR0057 | Wharton | Gas | 142.00 | Jun-16 |
| 16INR0007 | Hidalgo | Gas | 95.00 | Jun-16 |
| 16INR0004 | Cameron | Gas | 730.00 | Jun-16 |
| 16INR0013 | Nacogdoches | Gas | 215.00 | Jul-16 |
| 08INR0019b | Gray | Wind | 250.00 | Jul-16 |
| 14INR0011 | Swisher | Storage | 270.00 | Jul-16 |
| 16INR0037 | Floyd | Wind | 400.00 | Oct-16 |
| 16INR0024 | Hidalgo | Wind | 200.00 | Oct-16 |
| 08INR0019c | Gray | Wind | 250.00 | Dec-16 |
| 16INR0017 | Culberson | Solar | 70.00 | Dec-16 |
| 16INR0018 | Upton | Solar | 40.00 | Dec-16 |
| 13INR0006 | Gray | Wind | 750.00 | Dec-16 |
| 16INR0019 | Coke/Sterling | Solar | 100.00 | Dec-16 |
| 12INR0002b | Briscoe | Wind | 200.00 | Dec-16 |
| 16INR0030 | Young & Jack | Wind | 201.00 | Dec-16 |
| 16INR0029 | Hill & Limestone | Wind | 100.00 | Dec-16 |
| 16INR0028 | Jack | Wind | 100.00 | Dec-16 |
| 16INR0027 | Grayson & Fannin | Wind | 100.00 | Dec-16 |
| 16INR0026 | Erath, Somervell, Bosque | Wind | 100.00 | Dec-16 |
| 16INR0025 | Sterling | Solar | 30.00 | Dec-16 |
| 16INR0031 | Zapata & Starr | Wind | 100.00 | Dec-16 |
| 16INR0011a | Cameron | Wind | 18.00 | Dec-16 |
| 13INR0010f | Parmer | Wind | 200.00 | Dec-16 |
| 15INR0013 | Anderson | Storage | 324.00 | May-17 |
| 17INR0003 | Jackson | Gas | 965.00 | Jun-17 |
| 17INR0002 | Henderson | Gas | 489.00 | Jun-17 |
| 17INR0005 | Starr | Wind | 200.00 | Jun-17 |
| 17INR0009 | Hood | Gas | 1042.00 | Jul-17 |
| 17INR0007 | Wharton | Gas | 1141.00 | Jul-17 |
| 16INR0011b | Cameron | Wind | 132.00 | Dec-17 |
| 11INR0040 | Freestone | Gas | 640.00 | Mar-18 |
| 15INR0014 | Matagorda | Storage | 280.00 | May-18 |

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- CenterPoint Energy submitted the Houston Region Import Capacity project. This is a Tier 1 project that is estimated to cost between $297 to $532 million. ERCOT has issued the independent review report on Feb. 20th.  ERCOT will present the project to TAC on March 27, 2014 and at the Board of Directors in April 2014 for their endorsement.

- Garland Power & Light (GP&L) and Cross Texas Transmission (CTT) have jointly submitted a Houston Import project. This is a Tier 1 project that is estimated to cost between $195 to $317 million. ERCOT has issued the independent review report on Feb. 20th.  ERCOT will present the project to TAC on March 27, 2014 and at the Board of Directors in April 2014 for their endorsement.

- Lone Star Transmission has submitted a Houston Import project. This is a Tier 1 project that is estimated to cost between $417 to $675 million. ERCOT has issued the independent review report on Feb. 20th.  ERCOT will present the project to TAC on March 27, 2014 and at the Board of Directors in April 2014 for their endorsement.

- Oncor has submitted the West Texas Area project. This is a Tier 2 project that is estimated to cost $45 million. This project is currently under ERCOT independent review.

- CenterPoint has submitted the Katy Area project. This is a Tier 2 project that is estimated to cost $20.4 million. This project is currently under ERCOT independent review.

- LCRA TSC has submitted the Leander – Round Rock 138 kV project. This is a Tier 1 project that is estimated to cost $50.9 million. This project is currently under ERCOT independent review.

- Sharyland has submitted the Brady Area project. This is a Tier 2 project that is estimated to cost $18 million. This project has received several RPG comments and it is under study mode.

- Sharyland has submitted the West Texas projects for Stanton Area. This is a Tier 3 project that is estimated to cost $40.4 million. This project has received several RPG comments and it is under study mode.

- AEPSC has submitted the Brady Area Improvements project. This is a Tier 2 project that is estimated to cost $26.5 million. This project has received several RPG comments and it is under study mode.

- TNMP has submitted the Wink-Pecos Line 69E Rebuild project. This is a Tier 3 project that is estimated to cost $15 million. This project has been submitted for RPG comments.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Mar 4, 2014	Posted 14DSA and 14DSB updated cases

  - Mar 7, 2014	Post MODTPIT

  - Mar 14, 2014	Post Updated Contingency Definitions

  - Apr 1, 2014	Start 15DSA case build process

# Other Notable Activities

- The System Protection Working Group 2014 Current Year (CY) base creation process has started.  The process will include 4 passes and conclude March 21, 2014.

- ERCOT has posted the final report on the results of the Long-term study and the improvements to the long-term study process as a result of the grant received from the Department of Energy.

- ERCOT has completed and posted the 2013 Constraints and Needs Report.

- ERCOT has entered into an agreement with Powertech Labs to perform a small signal stability study.