## Change Log
Date | Script | Change
2005-02-07 | all | Modified for Flight 0405
2005-02-07 |  | STK26 and STK28 notes to use N1*BT
2005-02-07 |  | new script SCR38 (Muni/coop version of SCR35)
2005-02-07 |  | Correction to STK10
2005-02-07 |  | Change SCR35 to be on cycle switch
2005-02-18 | SCR35 | Modified to be a MVI test
2005-02-18 | SCR38 | Modified to be a MVI test
2005-05-05 | SCR32 | Noted in Transaction Details that the DTM~211 segment is optional
2005-05-05 | SCR33 | Changed Day 14 Transaction to "Reconcile" and Transaction Details to "Reconciliation of Payment to 820"
2005-05-05 | SCR34 | Noted in Transaction Details that the DTM~211 segment is optional
2005-05-05 | Timeline Base | Changes to STK02, STK05, SCR35 & SCR38 to bring in line with scripts.
2005-05-05 | various | Changed references from GISB to NAESB
2005-05-05 | various | Spelling corrections
2005-05-27 | CON50 | Removed the date in the step for sending 814_20s and added a reference to the deadline in the published flight calendar.
2005-05-27 | CON52 | Added step for CR to establish banking relationship.
2005-06-05 | STK01 STK02 STK05 STK06 STK10 STK23 STK26 STK28 SCR31 | Changed scripts to move Day 24 and Day 25 transactions (Thanksgiving Holiday)
2005-06-30 | SCR47 | Changed the verbiage around the use of the DTM~215 segment. Also changed day when the MVO is seen to occur vs what the effective date is.
2005-06-30 | SCR49 (2) | Added Script as an alternative version of SCR49
2005-06-30 | SCR50 | Change in success criteria - clean up
2005-06-30 | SCR51 | Added Script
2005-07-08 | SCR46 | Deleted
2005-07-08 | SCR47 | Storyline cleanup - changed MVO to current date +1. Made changes in body of script to reflect the change.
2005-07-08 | SCR49 | Original version with MVI deleted.
2005-07-08 | SCR49 (2) | Now shown as SCR49 - Corrected CR of Record from none to CR1
2005-07-08 | SCR50 | Deleted
2005-07-08 | SCR51 | Changed code in the 824 from CRI to A13. Added some verbiage regarding MCT recommendations and protocols.
2005-07-19 | SCR32 | Changes to reflect premium disconnect location required. Removed some of the references to dates in the notes column.
2005-07-19 | SCR34 | Added 650_02 to establish one-to-one relationship between 650_01s and 650_02s per the CC.
2005-07-19 | various | Spelling, grammar, consistency
2005-07-29 | SCR32 | Changed SCR32 to be tested by All CRs; added change control and requirement
2005-07-29 | SCR37 | STK37 renamed to MOU33
2005-07-29 | SCR38 | STK38 renamed to MOU38
2005-07-29 | SCR40 | Changed SCR40 to TDSP40
2005-07-29 | SCR41 | Changed SCR41 to TDSP41
2005-07-29 | SCR42 | Changed SCR42 to TDSP42
2005-07-29 | SCR43 | Changed SCR43 to TDSP43
2005-07-29 | SCR44 | Changed SCR44 to TDSP44
2005-07-29 | SCR50 | New Script to have Disconnect and reconnect completed unexecutable
2005-07-29 | SCR51 | Deleted again after requested to be rewritten - It will never be rewritten again :)
2005-07-29 | STK02 | STK02 renamed to TDSP02
2005-07-29 | STK05 | STK05 renamed to TDSP05
2005-07-29 | STK08 | STK08 renamed to TDSP08
2005-07-29 | STK20 | STK20 renamed to TDSP20
2005-07-29 | STK26 | STK26 renamed to MOU26
2005-07-29 | STK28 | STK28 renamed to MOU28
2005-08-11 | SCR32 | Changes to reflect the use of the REF~LW~O segment and to add ROL to the YNQ09 option.
2005-08-12 | SCR49 | Added 820_02 and began script 4 days earlier.
2005-08-24 | SCR50 | Added notations to indicate that some TDSPs may reject the reconnect request.
2005-09-07 | SCR32 | Added clarification to Day 1 step 650_01 that MTR is to be sent in the YNQ09 segment.
2005-09-14 | SCR47 | Removed Change Control 2005-686 from the Operating Rule cell
2005-09-14 | SCR49 | Removed Change Control 2004-645 from the Operating Rule cell
2005-09-14 | Script List | Removed Change Control 2005-686 for SCR47 and Change Control 2004-645 for SCR49 from the "MCT Rules/Recommendations or change controls" column in the Script list
2005-09-19 | CON51 | Typo corrected in notes section of 814_PD transaction to read that the CR will process the transaction through its translator and not the TDSP.
2005-09-27 | MOU01 | Changes to the transaction details cell for the 814_PD to remove references to the N1~BT, REF~BLT and REF~1W segments. These segments do not appear in the 814_PD.
2005-09-27 | MOU03 | Remove references to the REF~1W from the transaction details referencing the 814_08 transaction.
2005-10-03 | SCR32 | Corrected Transaction Detail for Day 5 650_02 to read REF~8X~RC001
2005-10-04 | SCR47 | Added requirement to the transaction details and the Note in the script storyline that the REF~1P~B44 segment be in the 814_24.
2005-11-16 | SCR31 | Remove this script from FL0106.
2005-11-16 | SCR32 | Remove script steps related to the reject for premium disconnect location required and the RWD response. Begin script on Day 1.
2005-11-16 | SCR45 | Remove this script from FL0106.
2005-11-16 | SCR49 | Remove this script from FL0106, use billing determinants in another script.
2005-11-16 | SCR50 | Remove this script from FL0106.
2005-11-16 | STK29 | Add STK29 to the script list for CRs changing service providers.
2005-11-30 | STK10 | Add language to the Storyline to indicate that the TDSP will assure that the SAC10 and SAC11 are populated on the final bill for Customer B. Change ESI type from Residential to Commercial. Add language to the transaction note for the final bill for Customer B indicating that the SAC10 and SAC11 will be populated.
2005-12-01 | SCR47 | Remove the 814_20 ESI retire transaction. Changed MVO RMRD from Day 11 to Day 12.
2005-12-01 | Script List | Various Changes
2006-01-31 | MOU26 | Deleted the reference to the REF*1W in the 814_25
2006-01-31 | MOU01 | Deleted the reference to the REF*1W in the 814_25
2006-01-31 | SCR32 | Reference to REF*PH (priority code) removed from 650_02
2006-01-31 | STK06 | Pretest Setup - changed ESI ID "should" to "must"
2006-01-31 | SCR32 | Changed suggested DTM*211 date in the 650_01 DNP Transaction Details to Day 3
2006-01-31 | SCR32 | Changed suggested DTM*211 date in the 650_01 RNP Transaction Details to Day 8
2006-01-31 | SCR34 | Added "BGN02" to the Transaction Details for the 650_02s as clarification.
2006-03-14 | Script List | Various Changes - Title changes from All IOU… to New IOU… and All MOU... to All New MOU… Added track for IOU bank change
2006-03-14 | Timeline Base | Clean-up to various scripts to correct scripts currently used and day's activity
2006-03-16 | various | Spelling corrections
2006-06-06 | STK07 | Day 20 - additional explanation of the TDSP handling of the 814_08 B40 transaction. Transaction is not to be processed until after the 814_08 COV transaction is received and processed.
2006-06-06 | STK07 | Script Storyline - additional explanation of the TDSP handling of the 814_08 B40 transaction. Transaction is not to be processed until after the 814_08 COV transaction is received and processed.
2006-06-06 | Script List | Added TDSP changing Service Provider to a Service Provider not previously qualified for TDSP
2006-06-16 | various | Removed Parenthetical references to previous scripts from script IDs - primarily used on the TDSP scripts. Parenthesis were making it difficult to load the scripts into the ERCOT website.
2006-06-26 | CON52 | Added language for possible request of banking information on letterhead, wet signature, etc.
2006-08-22 | MOU28 | Changed Day 26 814_06 Transaction Details to read DTM~151 instead of DTM~150
2006-08-22 | STK23 | Added a checkpoint at Day 24 to assure that both 814_12s have been processed.
2006-08-24 | TDSP02 | Synched dates with test website.
2006-08-24 | TDSP05 | Synched dates with test website. Made corrections recommended by ERCOT with regard to the Day 31 814_06 and the 814_07 as well.
2006-08-24 | TDSP08 | Synched dates with test website.
2006-08-24 | TDSP20 | Synched dates with test website.
2006-08-24 | TDSP40 | Synched dates with test website.
2006-08-24 | TDSP41 | Synched dates with test website.
2006-08-24 | TDSP42 | Synched dates with test website.
2006-08-24 | TDSP43 | Synched dates with test website.
2006-08-24 | TDSP44 | Synched dates with test website.
2006-09-13 | CON57 | Added to Workbook
2006-09-13 | CON58 | Added to Workbook
2006-09-13 | various | Reordered scripts so that the workbook order would be the same as the order presented/listed on-line.
2006-09-13 | Script List | Added CON57 and CON58 to the Connectivity Testing Script track on the Script List page.
2006-10-10 | TDSP40 | Added 814_21 (ERCOT to TDSP) to transaction stream.
2006-10-10 | TDSP42 | Added 814_21 (ERCOT to TDSP) to transaction stream.
2007-02-08 | SCR48 | SCR48 deleted. Replaced by TS04
2007-02-08 | Timeline Base | Timeline Base tab deleted. This information no longer used by Market.
2007-02-08 | Script List | Script List tab name changed to Test Track Information
2007-02-08 | Test Track Information | Disclaimer added to top of page.
2007-02-08 | Test Track Information | Added new scripts to All Track.
2007-02-08 | Test Track Information | Added API Track for MarkeTrak system.
2007-02-08 | TS01 | Added script.
2007-02-08 | TS02 | Added script.
2007-02-08 | TS03 | Added script.
2007-02-08 | TS04 | Added script.
2007-02-08 | TS05 | Added script.
2007-02-08 | TS06 | Added script.
2007-02-08 | TS07 | Added script.
2007-02-08 | TS08 | Added script.
2007-02-08 | TS09 | Added script.
2007-02-08 | TS10 | Added script.
2007-02-08 | MTAPI01 | Added script - Update TDSP.
2007-02-08 | MTAPI04 | Added script - Update CR.
2007-02-08 | MTAPI02 | Added script - Submit TDSP.
2007-02-08 | MTAPI05 | Added script - Submit CR.
2007-02-08 | MTAPI06 | Added script - Query CR.
2007-02-08 | MTAPI03 | Added script - Query TDSP.
2007-02-08 | various | Spelling/grammar
2007-02-28 | TS03 | Moved the Disconnect from the TDSP down 10 days. Redesigned the TS03 script into a service order Option 1 version TS03A and Option 2 & 3 version TS03B
2007-02-28 | STK13 | Removed STK13, Drops to AREP will no longer be accepted by ERCOT per PUCT rule
2007-03-06 | Various | Standardization changes (spacing, print set-up, CR designations, etc)
2007-03-06 | Test Track Information | Made changes to reflect TS03 change to TS03A and TS03B
2007-03-29 | TS06 | Made correction to the Transaction Details - Day 1. Changed "NM1~MQN3~~~~~~93~None" to "NM1~MQ~3~~~~~~93~None". "N" was replaced with "~".
2007-03-29 | TS05 | Added additional explanation to the Notes field for the Day 4 ERCOT NAESB validation.
2007-03-30 | TS02 | Corrected information in the Transaction Detail and Notes for the Day 25 and Day 26 867_03.
2007-04-09 | TS09 | Changes to the transaction details for the Day 8 and Day 9 814_04/05 - ASI~U to ASI~WQ
2007-04-16 | TS06 | Moved the first day of script from Day 01 to Day 16. Changed the transaction details for day 16 From NM109 NM1~MQ~3~~~~~~93~None to NM109 NM1~MQ~3~~~~~~93~All
2007-04-17 | SCR33 | Transaction Details for Day 1 Rebill. BIG08 notation changed from 00 to 05
2007-05-02 | TS05 | Integrated rewritten TS05 Script into the workbook.
2007-05-03 | TS08 | Change Mass Transition Switch Request to Day 18
2007-05-03 | TS08 | Move Mass Transition Switch 814_04 to Day 17 to allow a one day turnaround for the 814_03/04
2007-05-04 | TS05 | Changed script to begin on Day 19
2007-06-11 | TS01 | Changed script name to POLR01. This will be part of a new POLR track that is used when new POLRs are assigned.
2007-06-11 | TS02 | Deleted
2007-06-11 | TS03A | Changed script name to DOA01.
2007-06-11 | TS03B | Changed script name to DOA02.
2007-06-11 | TS04 | Changed script name to SCR49. Added the Estimation Counter from TS02 script.
2007-06-11 | TS05 | Changed script name to SCR50. Deleted day 22 and added delimited flat file to story line.
2007-06-11 | TS05 | Added a script to test transfer of flat file to POLR - POLR02. This will be part of a new POLR track that is used when new POLRs are assigned.
2007-06-11 | TS06 | Deleted
2007-06-11 | TS07 | Deleted
2007-06-11 | TS08 | Changed script name to POLR 03. Removed BGN07=TS from 814_08/814_09. Add timing to 814_04.
2007-06-11 | TS09 | Deleted
2007-06-11 | TS10 | Combined with SCR32
2007-06-11 | SCR32 | Added Non-Friday disconnect functionality
2007-06-18 | various | Clean-up to various scripts - format convention, life-cycle numbering, spelling, etc.
2007-06-18 | POLR02 | Copied remainder of Success Criteria from TS05
2007-06-18 | SCR32 | Added note to Story Line to indicate that CRs that always send a "Y" in the Friday authorization YNQ can send the Y for this script.
2007-06-21 | POLR01 | Corrected Script Name to POLR01
2007-06-21 | POLR01 | Corrected Number of CRs from 2 to 1
2007-06-21 | SCR32 | Added additional verbiage around the Friday Disconnect authorization segment in both the script Storyline and the Transaction Details for Day 4.
2008-09-16 | CON52 | Updated the Story Line to indicate that some TDSPs may require that they receive both the EFT and/or W-9 forms before Day01 of Flight testing.
2008-12-16 | various | Added REF~BLT~LDC to initiating transactions for MOU scripts
2008-12-23 | SCR47 | Added Day 10 step for CR to send email to ERCOT if date was received in 650_04
2009-09-08 | SCR50 | Updated script to include email in CBCI file submitted by CR and error response file from ERCOT to CR will include ESI ID
2009-09-29 | various | Updated SW evaluation from 5 day window to 2 day window
2009-09-29 | various | Removed Powerpoint references in stacking scripts
2010-08-04 | STK06 | Removed SIM transactions and changed reject from TDSP to A13 due to Expedited SW rules. Updated name, storyline, and success criteria
2010-08-04 | CON52 | Added that banking info. must be sent during connectivity setup
2011-06-17 | various | Edits made to existing scripts to remove steps no longer necessary for TX SET V4.0. Removed POLR01 as functionality is covered in POLR03.
2011-11-10 | various | Added TX SET V4.0 scripts - ACQ01, SCR33A, SCR51, SCR53, SCR54, SCR56, SCR58, SCR61, SCR64, SCR65, STK30, STK31, and STK33
2012-07-18 | various | Modified SCR33 to include a stand alone tampering charge in the Day 4 810_02; Modified SCR33A to be tested for a bank change or a change to an established service provider that includes a bank change; Created SCR33B to be tested for a change to an established service provider; Changed total of invoices to $50.00 NOTE: CON52 must be complete before beginning SCR33 and SCR33A

## CON50
|  | Script ID | CON50 |  | Power Point
|  | Script Name | ERCOT and TDSP Test Bed Load
|  | Script Storyline | TDSP sends Test Bed Load to ERCOT. ERCOT successfully receives and sets up.
|  | Success Criteria | Test Bed set up successfully
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Operating Rule |  |  | TRACK | TDSP
Simulated Entity
Duns Number
Number of CR's
|  |  | ERCOT | TDSP
PreTest Setup
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 01 | Pre-Day 1 | ERCOT | TDSP | email | CR List | ERCOT sends TDSP the list of CRs testing in their territory.
| Day 2 | Pre-Day 1 | ERCOT | TDSP | email | Relationship Matrix | ERCOT sends TDSP the final testing Relationship Matrix.
| Day 3 | Pre-Day 1 | ERCOT | CR | email | Relationship Matrix | ERCOT emails list of TDSP test partners to the CR.
| Day 4 | Pre-Day 1 | TDSP | CR | email | ESI ID Spreadsheet | TDSP emails ESI ID spreadsheet to primary and secondary contacts.
| Day 5 | Pre-Day 1 | TDSP | ERCOT | email | ESI ID List | TDSP emails ESI ID spreadsheet to ERCOT flight testing team.
|  | Pre-Day 1 | TDSP | ERCOT | 814_20 | Create ESI ID | TDSP transmits 814_20 Create ESI ID transactions to ERCOT BY THE DATE SPECIFIED IN THE PUBLISHED FLIGHT CALENDAR. No 814_21 or 997 transactions are returned.
Day 6
|  | Pre-Day 1 | ERCOT | TDSP | email | Notification of success | ERCOT notifies TDSP that Test Bed has been successfully set up.
Day 7

## CON51
|  | Script ID | CON51 |  | Power Point
|  | Script Name | TDSP and CR NAESB Connectivity Test
|  | Script Storyline | Test NAESB connectivity, exchange of 814_PC and 814_PD file. The 814 transactions will be created by each Trading Partners translator system and run through the translator to verify EDI enveloping between partners. TDSPs will schedule actual start dates with each CR. NOTE: If connectivity information changes after this script is completed, this script will need to be re-executed with all Trading Partners.
|  | Success Criteria | TDSP and CR successfully send and receive encrypted files.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Operating Rule |  |  | TRACK | New CR/Bank Change/Change of Service Provider
Simulated Entity
Duns Number
Number of CR's
|  |  | ERCOT | TDSP
PreTest Setup
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 01 | Pre-Day 1 | TDSP | CR | website | TW | TDSP completes Testing Worksheet on the Retail Testing Website.
| Day 2 | Pre-Day 1 | CR | TDSP | website | TW | CR completes Testing Worksheet on the Retail Testing Website.
| Day 3 | Pre-Day 1 | CR | TDSP | email | Encryption Keys | CR emails encryption keys to TDSP and schedules connectivity testing
| Day 4 | Pre-Day 1 | TDSP | CR | email | Encryption Keys | TDSP emails encryption keys to CR and schedules connectivity testing
| Day 5 | Pre-Day 1 | CR | TDSP | 814_PC | Encrypted File | CR sends an encrypted file containing the TX SET 814_PC X12 formatted file. CR emails TDSP results of successful posting from their NAESB log. TDSP will process file through translator and verify envelope set-up. No 997 FA is required.
|  | Pre-Day 1 | TDSP | CR | email | TDSP verification | TDSP verifies that the 814_PC was received via NAESB.
Day 6
|  | Pre-Day 1 | TDSP | CR | 814_PD | Encrypted File | TDSP sends an encrypted file containing the TX SET 814_PC X12 formatted file. TDSP emails CR results of successful posting from their NAESB log. CR will process file through translator and verify envelope set-up. No 997 FA is required.
Day 7
| Day 8 | Pre-Day 1 | CR | TDSP | email | CR verification | CR verifies that the 814_PD was received via NAESB.

## CON52
|  | Script ID | CON52 |  | Power Point
|  | Script Name | Penny Test
|  | Script Storyline | TDSP and CR exchange banking information using EFT template; CR instructs their bank to send $.01 to the TDSP's bank. TDSP confirms receipt. This script is not performed for CRs/TDSPs where money is being received in production. TDSPs require that they receive both the EFT template and/or W-9 forms before Day 01 of flight test. TDSPs will send an e-mail to each testing MP informing them of this requirement on Day 0 of each testi flight.
|  | Success Criteria | CR sends and TDSP receives $.01 through their banking institutions.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Operating Rule |  |  | TRACK | New CR/Bank Change
Simulated Entity
Duns Number
Number of CR's
|  |  | TDSP | CR
PreTest Setup
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
|  | Pre-Day 1 | CR | CR Bank | Establish | CR establishes banking relationship. | The CR MUST establish a banking relationship before the beginning of the Penny Test testing period.
| Day 01 | Pre-Day 1 | CR | TDSP | email/fax | TDSP and CR primary testing contacts to exchange banking information using the EFT template. Any specific requirements by either party for the transmission of this information such as "wet" signatures, letterhead, etc., shall be communicated at this time. | Payment Type (ACH or Wire). If ACH, type of ACH (CTX, CCD) Company Name, Bank Name, ABA Number, Account Number, Tax ID, Nr Refund Type (Check, ACH). Contact/Address info for refund.
| Day 2 | Pre-Day 1 | CR | CR Bank |  | CR sends instructions their bank to transfer $0.01 to TDSP by ACH or Wire transfer.
| Day 3 | Pre-Day 1 | CR | TDSP |  | CR's Bank initiates transfer via NACHA of $0.01 to TDSP bank. | A penny will be sent.
| Day 4 | Pre-Day 1 | TDSP | CR | email | TDSP notifies CR by email that $0.01 has been successfully received. | Email sent to primary testing contact.

## CON54
|  | Script ID | CON54 |  | Power Point
|  | Script Name | NAESB connectivity with ERCOT and TDSP
|  | Script Storyline | Test NAESB connectivity; successful exchange of standard X12-encrypted handshake files. Note: the 814_20 sent by the TDSP is sent with an incorrect value in the ASI segment of the transaction in order to force it to automatically create an outbound 814_21 in ERCOT's system.
|  | Success Criteria | TDSP and ERCOT successfully send and receive encrypted files.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Operating Rule |  |  | TRACK | TDSP
Simulated Entity
Duns Number
Number of CR's
|  |  | ERCOT | TDSP
PreTest Setup
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 01 | Pre-Day 1 | TDSP | ERCOT | website | TW | TDSP completes Testing Worksheet on the Retail Testing Website.
| Day 2 | Pre-Day 1 | ERCOT | TDSP | website | TW | ERCOT completes Testing Worksheet on the Retail Testing Website.
| Day 3 | Pre-Day 1 | ERCOT | TDSP | email | Encryption Keys | ERCOT emails public keys, username and password, and schedules test date to TDSP
| Day 4 | Pre-Day 1 | TDSP | ERCOT | email | Encryption Keys | TDSP emails public keys, username and password to ERCOT
| Day 5 | Pre-Day 1 | TDSP | ERCOT | 814_20 | Encrypted file | TDSP sends an encrypted X12 formatted 814_20 file containing an ESI ID of "CONNECTIVITYTESTESIID" and an "ASI*I*021". TDSP emails ERCOT results of successful posting from their NAESB EDM log.
|  | Pre-Day 1 | ERCOT | TDSP | email | ERCOT verification | ERCOT verifies that the EDI file was received and successfully decrypted via email.
Day 6
|  | Pre-Day 1 | ERCOT | TDSP | 814_21 | Encrypted file | ERCOT sends an encrypted X12 formatted 814_21 containing an ESI ID of "CONNECTIVITYTESTESIID" ERCOT emails TDSP successful NAESB response message
Day 7
| Day 8 | Pre-Day 1 | TDSP | ERCOT | email | TDSP verification | TDSP verifies that the EDI transaction was received and decrypted successfully.
|  | Pre-Day 1 | ERCOT | TDSP | email | ERCOT verification | ERCOT sends confirmation e-mail of successful completion of connectivity test.

## CON56
|  | Script ID | CON56 |  | Power Point
|  | Script Name | NAESB connectivity with ERCOT and CR
|  | Script Storyline | Test NAESB connectivity; successful exchange of standard X12-encrypted handshake files. Note: the 814_01 sent by the CR is sent with an incorrect value in the REF*SU segment of the transaction in order to force it to automatically create an outbound 814_02 in ERCOT's system.
|  | Success Criteria | CR and ERCOT successfully send and receive encrypted files.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Operating Rule |  |  | TRACK | New CR/Change of Service Provider
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | CR
PreTest Setup
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 01 | Pre-Day 1 | CR1 | ERCOT | website | TW | CR completes Testing Worksheet on the Retail Testing Website.
| Day 2 | Pre-Day 1 | ERCOT | CR1 | website | TW | ERCOT completes Testing Worksheet on the Retail Testing Website.
| Day 3 | Pre-Day 1 | ERCOT | CR1 | email | Encryption Keys | ERCOT emails public keys, username and password, and schedules test date to CR
| Day 4 | Pre-Day 1 | CR1 | ERCOT | email | Encryption Keys | CR emails public keys, username and password to ERCOT
| Day 5 | Pre-Day 1 | CR1 | ERCOT | 814_01 | encrypted file | CR sends an encrypted X12 formatted 814_01 file containing an ESI ID of "CONNECTIVITYTESTESIID" and a "REF*SU*I". CR emails ERCOT results of successful posting from their NAESB log.
|  | Pre-Day 1 | ERCOT | CR1 | email | ERCOT verification | ERCOT verifies that the EDI file was received and successfully decrypted via email.
Day 6
|  | Pre-Day 1 | ERCOT | CR1 | 814_02 | Encrypted file | ERCOT sends an encrypted X12 formatted 814_02 containing an ESI ID of "CONNECTIVITYTESTESIID". ERCOT emails CR successful NAESB response message
Day 7
| Day 8 | Pre-Day 1 | CR1 | ERCOT | email | CR verification | CR verifies that the EDI transaction was received and decrypted successfully.
|  | Pre-Day 1 | ERCOT | CR1 | email | ERCOT verification | ERCOT sends confirmation e-mail of successful completion of connectivity test.

## DOA01
|  | Script ID | DOA01 |  | Power Point
|  | Script Name | Denial of Access - Option 1 CR
|  | Script Storyline | TDSP sends an 867_03 that indicates it is unable to read the meter because it is locked inside the premise. The TDSP then sends a 650_04 to suspend delivery of service. The CR then creates a reconnect request with text instructions to the TDSP on how to resolve the DOA issue. The TDSP resolves DOA and reconnects the premise.
|  | Success Criteria | CR's can accept the 650_04 TDSP disconnect for DOA
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule | 2006-691, 2006_702 |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | Choose an ESI ID with on-cycle bills on Day 3. | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01
Day 02
|  | Day 03 |  |  |  |  | Day 3 cycle Date | 1 | Read
Day 04
Day 05
| Day 1 | Day 06 | TDSP | ERCOT | 867_03 | REF~5I must be included REF02 = D6 ESN = 3 | Usage sent, Estimate Sequence Number = 3. Meter is inaccessible. | 1 |  |  | CR1
| Day 2 | Day 07 | ERCOT | CR1 | 867_03 | REF~5I must be included REF02 = D6 ESN = 3 | Usage sent, Estimate Sequence Number = 3. Meter is inaccessible. | 1 |  |  | CR1
| Day 3 | Day 08
Day 09
| Day 17 | Day 10 | TDSP | CR1 | 650_04 | BGN08 = S2 REF~5H = GA001 | TDSP suspends service due to lack of access to meter. | 1 |  |  | CR1
|  | Day 11 | CR1 | TDSP | 650_01 | REF~8X~RC004 | Requires text instructions in the MTX segment | 1 |  |  | CR1
|  | Day 12 | TDSP | CR1 | 650_02 | REF~8X~RC004 | TDSP reconnects service | 1 |  |  | CR1

## DOA02
|  | Script ID | DOA02 |  | Power Point
|  | Script Name | Denial of Access - Option 2 & 3 CRs
|  | Script Storyline | TDSP sends an 867_03 that indicates it is unable to read the meter because it is locked inside the premise. The TDSP then sends a 650_04 to suspend delivery of service. The customer contacts the TDSP and resolves the access issue. The TDSP sends 650_04 indicating that service has been reconnected.
|  | Success Criteria | CR's can accept the 650_04 TDSP disconnect for DOA
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule | 2006-691, 2006_702 |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | Choose an ESI ID with on-cycle bills on Day 3. | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01
Day 02
|  | Day 03 |  |  |  |  | Day 3 cycle Date | 1 | Read
Day 04
Day 05
| Day 1 | Day 06 | TDSP | ERCOT | 867_03 | REF~5I must be included REF02 = D6 ESN = 3 | Usage sent, Estimate Sequence Number = 3. Meter is inaccessible. | 1 |  |  | CR1
| Day 2 | Day 07 | ERCOT | CR1 | 867_03 | REF~5I must be included REF02 = D6 ESN = 3 | Usage sent, Estimate Sequence Number = 3. Meter is inaccessible. | 1 |  |  | CR1
| Day 3 | Day 08
Day 09
| Day 17 | Day 10 | TDSP | CR1 | 650_04 | BGN08 = S2 REF~5H = GA001 | TDSP suspends service due to lack of access to meter. | 1 |  |  | CR1
Day 11
Day 12
|  | Day 13 | TDSP | CR1 | 650_04 | REF~5H~RC004 | TDSP reconnects service | 1 |  |  | CR1
Day 20

## SCR30
|  | Script ID | SCR30 |  | Power Point
|  | Script Name | Ad Hoc request for Historical Usage and change in Special Needs Indicator
|  | Script Storyline | Current CR updates the premise information by sending the TDSP an 814_PC with a change to the Special Needs Indicator and the addition of a customer name. The Current CR also requests historical usage on the premise via the ad hoc request (814_26). The TDSP responds with an 814_PD, 814_27, and 867_02.
|  | Success Criteria | CR sends 814_PC with premise updates. CR sends 814_26 request for historical usage. The TDSP updates the premise and responds appropriately with the historical usage.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Small Commercial | Single Non IDR | None | CR1 | No
|  | Operating Rule |  |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | Setup CR1 as Rep of Record | Setup CR1 as Rep of Record | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01
| Day 2 | Day 02
| Day 3 | Day 03
| Day 4 | Day 04
|  | Day 05 | CR1 | TDSP | 814_PC | REF~SU~Y N1~FJ | CR updates premise information with Special Needs Indicator and customer name. | 1 |  |  | CR1
Day10
|  | Day 06 | TDSP | CR1 | 814_PD | ASI~WQ~001 | Response to CR1 indicating the premise has been updated. | 1 |  |  | CR1
Day 11
|  | Day 07 | CR1 | ERCOT | 814_26 | BGN08 = 26 | Request for historical usage | 2 |  |  | CR1
Day 12
|  | Day 08 | ERCOT | TDSP | 814_26 | BGN08 = 26 | Request for historical usage | 2 |  |  | CR1
|  | Day 09 | TDSP | ERCOT | 814_27 | ASI~WQ~029 | Response to request | 2 |  |  | CR1
|  |  | TDSP | ERCOT | 867_02 | BPT01 = 52 | Historical usage information. | 2 |  |  | CR1
Day 14
|  | Day 10 | ERCOT | CR1 | 814_27 | ASI~WQ~029 | Response to request | 2 |  |  | CR1
|  |  | ERCOT | CR1 | 867_02 | BPT01 = 52 | Historical usage information. | 2 |  |  | CR1
Day 15

## SCR33
|  | Script ID | SCR33 |  | Power Point
|  | Script Name | Invoice and bank payment with remittance advice via bank or NAESB
|  | Script Storyline | Testing CR sends a Move-In for Day 03. After successful MVI, TDSP sends Tampering Invoice on Day 6. Testing CR then sends a Move-Out for Day 09. After the MVO, TDSP sends three invoices. The amount of the original (00) final invoice can be any amount since it will be nullified by the cancel (01) invoice. The total amount of the rebill (05) and tampering (A5) invoices should not exceed $50.00. CR initiates live payment through bank. Remittance advice may travel with payment via bank or separately (point-to-point) via NAESB. TDSP refunds the dollar amount to CR within 30 days of end of test. Two ESI IDs are used: ESI 1: Original invoice, cancel and rebill (Original is sent in one envelope and cancel rebill in another) ESI 2: Original invoice with stand alone tampering charge. NOTE: Nueces does not execute this script
|  | Success Criteria | CR initiates MVI. After MVI/MVO, TDSP sends invoices to CR. CR responds with correct bank payment and remittance advice. TDSP reconciles and refunds the payment.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | None | No
|  | Operating Rule |  |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | Exchange banking information | Exchange banking information CON52 (Penny Test) must be complete
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
|  |  | ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
[7 empty] | Day 1 of 2 day window for Day 3 MVI | 1 |  | E
|  | Day 02 | TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
|  |  | ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
[7 empty] | Day 2 of 2 day window for Day 3 MVI | 1 |  | E
|  | Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
|  | Day 04 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1 |  |  | CR1
|  |  | ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 | 1 |  |  | CR1
Day 05
|  | Day 06 | TDSP | CR1 | 810_02 | BIG07 = A5 BIG08 = 00 | TDSP sends stand alone tampering charge. | 1 |  |  | CR1
|  | Day 07 | CR1 | ERCOT | 814_24 | RMRD = Day 09 (DTM~376) LIN~1~SH~EL~SH~CE~SH~MVO | CR1 submits MVO with RMRD = Day 09 (Customer B) | 2
|  |  | ERCOT | TDSP | 814_24 | RMRD = Day 09 (DTM~376) LIN~1~SH~EL~SH~CE~SH~MVO | ERCOT forwards CR1 MVO to TDSP with RMRD - Day 09 | 2 |  |  | CR1
[7 empty] | Day 1 of 2 day window for Day 09 MVO | 2 |  | E
|  | Day 08 | TDSP | ERCOT | 814_25 | SMRD = Day 09 (DTM~376) ASI~WQ~002 | TDSP responds to CR1 MVO with SMRD = Day 09 | 2 |  |  | CR1
|  |  | ERCOT | CR1 | 814_25 | SMRD = Day 09 (DTM~376) ASI~WQ~002 | ERCOT forwards TDSP response to CR1 SMRD = Day 09 | 2
[7 empty] | Day 2 of 2 day window for Day 09 MVO | 2 |  | E
|  | Day 09 |  |  |  |  | Day 09 MVO Effectuates | 2 | MVO
|  | Day 10 | TDSP | ERCOT | 867_03 | BPT07 = F | TDSP sends final meter read to ERCOT for Customer B | 2 |  |  | CR1
|  |  | TDSP | CR1 | 810_02 | BIG07 = FB | Final Bill for Customer B SAC10 and SAC11 to be populated | 2 |  |  | CR1
|  |  | ERCOT | CR1 | 867_03 | BPT07 = F | ERCOT forwards Final Meter Read for Customer B | 2 |  |  | CR1
Day 11
|  | Day 12 | TDSP | ERCOT | 867_03 | BPT01 = 01 | TDSP sends Cancel of Consumption for Customer A | 2 |  |  | CR1
|  |  | TDSP | CR1 | 810_02 | BIG08 = 01 | Cancellation of Final Bill for Customer A | 2 |  |  | CR1
|  |  | ERCOT | CR1 | 867_03 | BPT01 = 01 | Cancel of Consumption for Customer A | 2 |  |  | CR1
| Day 2 |  | TDSP | ERCOT | 867_03 | BPT01 = 05 | TDSP sends Replacement Consumption for Customer A | 2 |  |  | CR1
|  |  | TDSP | CR1 | 810_02 | BIG08 = 05 | Replacement Bill issued for cancelled Final Bill for Customer A. | 2 |  |  | CR1
| Day 4 |  | ERCOT | CR1 | 867_03 | BPT01 = 05 | Replacement Consumption for Customer A | 2 |  |  | CR1
Day 13
| Day 7 | Day 14 | CR1 | TDSP | ACH Payment | ACH or Wire | CR sends payment instruction to the bank for ACH or Wire Transfer. | 1
|  |  | CR1 | TDSP | 820_02 | Remit all 4 invoices | Remittance advice is sent by CR to Bank for TDSP or via NAESB to TDSP. All four invoices must be referenced on the 820_02. | 1
|  | Day 15 | TDSP | CR1 | Reconcile | Reconciliation of Payment to 820 | TDSP reconciles remittance advice to invoices and trace number to Bank payment. | 1
| Day 15 | Day 16
| Day 20 | Day 17 | TDSP | CR1 | Refund | ACH or Check | TDSP refunds payment to CR1 | 1

## SCR33A
|  | Script ID | SCR33A |  | Power Point
|  | Script Name | Bank Change
|  | Script Storyline | TDSP sends invoice totaling $50.00 or less to the CR. CR initiates live payment through bank. Remittance advice may travel with payment via bank or separately (point-to-point) via NAESB. TDSP refunds the dollar amount to CR within 30 days of end of test. NOTE: Script will be tested for a bank change or a change to an established service provider that also includes a bank change Nueces does not execute this script
|  | Success Criteria | CR initiates MVI request. After MVI is complete, TDSP sends tampering invoice to CR. CR responds with correct bank payment and remittance advice. TDSP reconciles and refunds the payment.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule |  |  | TRACK | Bank Change
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | Exchange banking information | Exchange banking information CON52 (Penny Test) must be complete
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
|  |  | ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
[7 empty] | Day 1 of 2 day window for Day 3 MVI | 1 |  | E
|  | Day 02 | TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
|  |  | ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
[7 empty] | Day 2 of 2 day window for Day 3 MVI | 1 |  | E
|  | Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
|  | Day 04 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1 |  |  | CR1
|  |  | ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 | 1 |  |  | CR1
Day 05
|  | Day 06 | TDSP | CR1 | 810_02 | BIG07 = A5 BIG08 = 00 | TDSP sends stand alone tampering charge. | 1 |  |  | CR1
Day 07
| Day 7 | Day 08 | CR1 | TDSP | ACH Payment | ACH or Wire | CR sends payment instruction to the bank for ACH or Wire Transfer. | 1
|  |  | CR1 | TDSP | 820_02 | Remit invoice | Remittance advice is sent by CR to Bank for TDSP or via NAESB to TDSP. Invoice must be referenced on the 820_02. | 1
|  | Day 09 | TDSP | CR1 | Reconcile | Reconciliation of Payment to 820 | TDSP reconciles remittance advice to invoice and trace number to bank payment. | 1
| Day 20 | Day 10 | TDSP | CR1 | Refund | ACH or Check | TDSP refunds payment to CR1 | 1

## SCR33B
|  | Script ID | SCR33B |  | Power Point
|  | Script Name | Change To Established Service Provider
|  | Script Storyline | TDSP sends invoice totaling $50.00 or less to the CR. Remittance advice travels (point-to-point) via NAESB. NOTE: Script will be tested for a change to an established service provider that does not include a bank change. Nueces does not execute this script
|  | Success Criteria | CR initiates script with MVI request. After MVI, TDSP sends tampering invoice to CR. CR responds with remittance advice. TDSP reconciles.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule |  |  | TRACK | Change of Service Provider
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
|  |  | ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
[7 empty] | Day 1 of 2 day window for Day 3 MVI | 1 |  | E
|  | Day 02 | TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
|  |  | ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
[7 empty] | Day 2 of 2 day window for Day 3 MVI | 1 |  | E
|  | Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
|  | Day 04 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1 |  |  | CR1
|  |  | ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 | 1 |  |  | CR1
Day 05
|  | Day 06 | TDSP | CR1 | 810_02 | BIG07 = A5 BIG08 = 00 | TDSP sends stand alone tampering charge. | 1 |  |  | CR1
Day 07
|  | Day 08 | CR1 | TDSP | 820_02 | Remit invoice | Remittance advice is sent by CR to Bank for TDSP or via NAESB to TDSP. Invoice must be referenced on the 820_02. | 1

## SCR35
|  | Script ID | SCR35 |  | Power Point
|  | Script Name | Move-In on unmetered ESI ID, Usage, Final Bill, Duplicate Invoice, 824 Reject
|  | Script Storyline | CR1 sends MVI for Day 3 - Customer A. CR1 sends a Day 11 move-in request, for Customer B, to the TDSP. The TDSP responds per protocol. The move-ins effectuate on schedule. The Final Bill and Usage are sent to CR1. A duplicate final invoice is sent and the CR rejects with an 824.
|  | Success Criteria | CR sends two MVI requests on an unmetered premise. TDSP responds to request, move-ins effectuate and the TDSP sends the final bill to the original CR. The TDSP then sends a duplicate final bill which the CR rejects.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Small Commercial | Unmetered | None | None | No
|  | Operating Rule |  |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1 | SIM CR2
|  | Pretest Setup | None | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 01 | Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| Day 2 |  | ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
[7 empty] | Day 1 of 2 day window for Day 3 MVI | 1 |  | E
| Day 3 | Day 02 | TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| Day 4 |  | ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
[7 empty] | Day 2 of 2 day window for Day 3 MVI | 1 |  | E
|  | Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
|  | Day 04 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1 |  |  | CR1
| Day 7 |  | ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 | 1 |  |  | CR1
Day 05
Day 06
| Day 8 | Day 07 | CR1 | ERCOT | 814_16 | RMRD = Day 11 (DTM~375) | MVI requested for Day 11 for Customer B | 2 |  |  | CR1
|  |  | ERCOT | TDSP | 814_03 | RMRD = Day 11 (DTM~375) | MVI requested for Day 11 for Customer B | 2 |  |  | CR1
|  | Day 08 | TDSP | ERCOT | 814_04 | SMRD = Day 11 | MVI scheduled for Day 11 | 2 |  |  | CR1
|  |  | ERCOT | CR1 | 814_05 | SMRD = Day 11 | MVI scheduled for Day 11 | 2 |  |  | CR1
|  | Day 09 |  |  |  |  | Day 1 of 2 day window for Day 11 MVI | 2 |  | E
|  | Day 10 | ERCOT | CR1 | 814_06 | FMVO DTM~151 = Day 11 | FMVO of Customer A due to Day 11 MVI | 2 |  |  | CR1
[7 empty] | Day 2 of 2 day window for Day 11 MVI | 2 |  | E
|  | Day 11 |  |  |  |  | Move-In Effectuates | 2 | MVI |  | CR1
| Day 9 | Day 12 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer B | 2 |  |  | CR1
|  |  | ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 for Customer B | 2 |  |  | CR1
Day10
|  | Day 13 | TDSP | ERCOT | 867_03 | BPT01 = 00 BPT07 = F | Final Usage for Customer A | 2 |  |  | CR1
|  |  | TDSP | CR1 | 810_02 | BIG07 = FB | Final Bill for Customer A | 2 |  |  | CR1
|  |  | ERCOT | CR1 | 867_03 | BPT01 = 00 BPT07 = F | Final Usage for Customer A | 2 |  |  | CR1
|  | Day 14 | TDSP | CR1 | 810_02 | BIG07 = FB | TDSP sends Duplicate Final Bill for Customer A | 2 |  |  | CR1
| Day 013 |  | CR1 | TDSP | 824 | TED~848~ABN | CR rejects 810_02 duplicate invoice. | 2 |  |  | CR1

## SCR49
|  | Script ID | SCR49 |  | Power Point
|  | Script Name | TDSP Sends Replacement Invoice
|  | Script Storyline | CR1 submits a Move-In for Customer A for Day 3. The Move-In effectuates as scheduled. The Cycle Bill is generated no later than Day 9 with the Estimate Counter. The original cycle bill and 867_03 are sent by the TDSP. The TDSP then cancels and replaces the original bill.
|  | Success Criteria | TDSP is able to generate a 867_03 and 810 with appropriate "05" code, and the CR is able to successfully process them.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single | None | None | No
|  | Operating Rule | 2006-691 |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP
|  | Pretest Setup |  | ESI should cycle on Day 8
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 01 | Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| Day 2 |  | ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
[7 empty] | Day 1 of 2 day window for Day 3 MVI | 1 |  | E
| Day 3 | Day 02 | TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| Day 4 |  | ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
[7 empty] | Day 2 of 2 day window for Day 3 MVI | 1 |  | E
|  | Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
|  | Day 04 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1 |  |  | CR1
Day 8
|  |  | ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 | 1 |  |  | CR1
Day 05
Day 06
Day 07
|  | Day 08 |  |  |  |  | Cycle Read
|  | Day 09 | TDSP | ERCOT | 867_03 | REF~5I~O1~~JH^Y^ESN^0^QO^1 | The REF~5I segment will be present to indicate the reason that the read was estimated this month (01 = TDSP Reason). Additional information regarding the leaving of door hangers (Y) and the number of times estimated will also be communicated in the segment. | 1 |  |  | CR1
|  |  | TDSP | CR1 | 810_02 | BIG08 = 00 | Cycle Bill for Customer A | 1 |  |  | CR1
Day 22
|  |  | ERCOT | CR1 | 867_03 | REF~5I~O1~~JH^Y^ESN^0^QO^1 | The REF~5I segment will be present to indicate the reason that the read was estimated this month (01 = TDSP Reason). Additional information regarding the leaving of door hangers (Y) and the number of times estimated will also be communicated in the segment. | 1 |  |  | CR1
Day 10
Day 11
|  | Day 12 | TDSP | ERCOT | 867_03 | BPT01 = 01 | TDSP sends Cancel of Consumption for Customer A | 1 |  |  | CR1
|  |  | TDSP | CR1 | 810_02 | BIG08 = 01 | Cancellation of Cycle Bill for Customer A | 1 |  |  | CR1
|  |  | TDSP | ERCOT | 867_03 | BPT01 = 05 | TDSP sends Replacement Consumption for Customer A | 1 |  |  | CR1
|  |  | TDSP | CR1 | 810_02 | BIG08 = 05 | Replacement Bill issued for cancelled Cycle Bill for Customer A. | 1 |  |  | CR1
|  |  | ERCOT | CR1 | 867_03 | BPT01 = 01 | Cancel of Consumption for Customer A | 1 |  |  | CR1
|  |  | ERCOT | CR1 | 867_03 | BPT01 = 05 | Replacement Consumption for Customer A | 1 |  |  | CR1

## SCR50
| Script ID | SCR50 |  | Power Point
| Script Name | Customer Billing Contact File Transmittal
| Script Storyline | Each CR will send ERCOT a simulated Customer Billing Contact File via NAESB in a delimited flat file format.
| Success Criteria | CR1 will provide one file to ERCOT with five (5) examples of Customer Billing Contact information via NAESB. CR1 will send a second file that contains an error. Customer Billing Contact information should be simulated.
| Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Residential | Single | None | None | No
| Operating Rule | POLR Rule |  | TRACK | New CR
Simulated Entity
Duns Number
| Number of CR's | 1
|  | ERCOT | TDSP | CR1 | SIM CR2
| Pretest Setup | None | None | None | None
Checkpoint Date | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01
Day 02
Day 03
| Day 04 | CR1 | ERCOT | CSV | Customer Billing Contact Information | Simulated Customer Billing Contact Information file is sent via NAESB - five (5) contacts to be input in one file. One ESI should include an email address. Note: File layout found in appendix F6 of Retail Market Guide. | 1 |  |  | CR1
| Day 05 | ERCOT | CR1 | CSV Response | Response file | ERCOT confirms receipt of information and validates file format. Note: File layout found in appendix F6 of Retail Market Guide. | 1 |  |  | CR1
|  | ERCOT | CR1 | NAESB Response | Response indicates successful send of file
| Day 06 | CR1 | ERCOT | CSV | Customer Billing Contact Information | Simulated Customer Billing Contact Information file is sent via NAESB - five (5) contacts to be input in one file. One row should not contain the CR DUNS number. Note: File layout found in appendix F6 of Retail Market Guide. | 1 |  |  | CR1
| Day 07 | ERCOT | CR1 | CSV Response | Response file | ERCOT confirms receipt of information and validates file format. Response file from ERCOT should contain the ESI ID for the row that contained an error. Note: File layout found in appendix F6 of Retail Market Guide. | 1 |  |  | CR1
|  | ERCOT | CR1 | NAESB Response | Response indicates successful send of file

## SCR54
|  | Script ID | SCR54 |  | Power Point
|  | Script Name | Switch Rejected Due To Switch Hold In Place
|  | Script Storyline | Switch Hold for Payment Plan placed on ESI ID. CR1 submits a Switch and TDSP rejects for SHF due to the Switch Hold.
|  | Success Criteria | TDSP rejects Switch with an 814_04R for SHF. Switch is cancelled at ERCOT and CR1 successfully processes 814_05R SHF transaction.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Small Non Residential | NA | None | SIM CR2 | No
|  | Operating Rule | CC2010-736 |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | SIM CR2 set up as ROR; Manually Add Tampering Switch Hold | SIM CR2 set up as ROR; Manually Add Tampering Switch Hold | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01
| Day 2 | Day 02
| Day 3 | Day 03
| Day 4 | Day 04
| Day 5 | Day 05
|  | Day 06 | CR1 | ERCOT | 814_01 | No DTM~MRR segment | Standard switch request for Customer B | 1 |  |  | CR1
|  |  | ERCOT | TDSP | 814_03 | LIN~1~SH~EL~SH~CE | Standard switch request | 1 |  |  | CR1
|  | Day 07 | TDSP | ERCOT | 814_04 | ASI~U~101 REF~7G~SHF | Switch rejected by TDSP due to Switch hold | 1 |  |  | CR1
|  |  | ERCOT | CR1 | 814_05 | ASI~U~021 REF~7G~SHF | ERCOT sends reject to CR1 | 1 |  |  | CR1

## SCR58
|  | Script ID | SCR58
|  | Script Name | TDSP Rejects Service Order Request For Weather Moratorium And Move Out For Force Majeure
|  | Script Storyline | CR requests a disconnect that is rejected by the TDSP for weather moratorium. CR sumbits a Move Out that is rejected by the TDSP for force majeure.
|  | Success Criteria | TDSP rejects transactions using the WTM and FME codes.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule | CC2010-751 |  | TRACK | New TDSP or new TDSP /system
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | CR1 set up as ROR | CR1 set up as ROR | CR1 set up as ROR
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
|  | Day 01 | CR1 | TDSP | 650_01 | BGN07 = 72 REF~8X~DC001 DTM~211 = Day 5 | CR sends request for a diconnect | 1 |  |  | CR1
|  | Day 02 | TDSP | CR1 | 650_02 | BGN07 = 72 REF~7G~WTM REF~8X~DC001 | TDSP rejects disconnect request | 1 |  |  | CR1
|  | Day 03 | CR1 | ERCOT | 814_24 | DTM~376 = Day 7 | MVO request for Day 7 | 2 |  |  | CR1
|  | Day 04 | ERCOT | TDSP | 814_24 | DTM~376 = Day 7 | ERCOT sends MVO for Day 7 | 2 |  |  | CR1
| Day 1 | Day 05 | TDSP | ERCOT | 814_25 | REF~7G~FME | TDSP rejects MVO for force majeure | 2 |  |  | CR1
| Day 12 | Day 06 | ERCOT | CR1 | 814_25 | REF~7G~FME | ERCOT sends reject for force majeure | 2 |  |  | CR1
Day 12

## STK23
|  | Script ID | STK23
|  | Script Name | MVI with 2 date changes for the Move In; MVI completes unexecutable
|  | Script Storyline | CR1 sends a MVI for Day 35; CR1 then sends a date change for Day 25. A second date change for Day 8 is sent by CR1. The date change with the highest iteration counter should win. TDSP can't work the MVI and will send an 814_28 unexecutable. NOTE: If the 814_12's get out of order at any point in the flow of transactions; an 814_13 with a reject code of ICL (Iteration Counter Lower) will be received. If the 814_13 response is received by ERCOT before the 814_04, ERCOT will update the date on the 814_05 (E21).
|  | Success Criteria | The MVI is scheduled for Day 8 - the date on the 814_12 with the highest iteration counter. Premise is de-energized from Day 1 to Day 8 Day 8 MVI is completed unexecutable Premise remains de-energized
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | de-energized | No
|  | Operating Rule | E20, E21 E22, T5, R8 |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 6 | Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 35 | MVI requested for Day 35 for Customer A | 1 |  |  | CR1
| Day 7 |  | ERCOT | TDSP | 814_03 | RMRD = Day 35 | ERCOT forwards CR1's MVI request for Day 35 | 1 |  |  | CR1
Day 7
| Day 8 | Day 02 | TDSP | ERCOT | 814_04 | SMRD = Day 35 | TDSP schedules MVI request for Day 35 | 1
|  |  | ERCOT | CR1 | 814_05 | SMRD = Day 35 | ERCOT forwards TDSP's scheduled MVI response. | 1
| Day 8 | Day 03 | CR1 | ERCOT | 814_12 | Date Change to Day 25 DTM~RTO - Iteration Counter | 1st Iteration Counter (DTM~), E22 | 1
|  |  | ERCOT | TDSP | 814_12 | Date Change Day 25 | 1st Iteration Counter (DTM~), E22 | 1 |  |  | CR1
|  | Day 04 | TDSP | ERCOT | 814_13 | Changes SMRD = Day 25 DTM~RTO | 1st Iteration Counter for CR1 (DTM~), E22 | 1 |  |  | CR1
|  |  | ERCOT | CR1 | 814_13 | Changes SMRD = Day 25 DTM~RTO | 1st Iteration Counter | 1
| Day 9 |  | CR1 | ERCOT | 814_12 | Date Change to Day 08 DTM~RTO -Iteration Counter | 2nd Iteration counter (DTM~), E22 | 1
|  |  | ERCOT | TDSP | 814_12 | Date Change to Day 08 DTM~RTO -Iteration Counter | 2nd Iteration counter for CR1 (DTM~), E22 | 1 |  |  | CR1
Day 9
| Day10 | Day 05 | TDSP | ERCOT | 814_13 | Changes SMRD = Day 08 DTM~RTO | 2nd Iteration Counter | 1 |  |  | CR1
|  |  | ERCOT | CR1 | 814_13 | Changes SMRD = Day 08 DTM~RTO | 2nd Iteration Counter | 1
Day 10
| Day 11 | Day 06
| Day 11 | [5 empty] | Day 1 of 2 day window for Day 08 MVI | 1 |  | E
| Day 12 | Day 07
[7 empty] | Day 2 of 2 day window for Day 08 MVI | 1 |  | E
|  | Day 08 |  |  |  |  | Day 08 MVI Does Not Effectuate due to TDSP Unexecutable | 1 | MVI
| Day 14 | Day 09 | TDSP | ERCOT | 814_28 | ASI~9~021; REF~G7~Q002 or T003; BGN07=09; BGN06 must equal BGN02 from 814_16; LIN07=MVI | TDSP completes MVI unexecutable | 1 |  |  | CR1
|  |  | ERCOT | CR1 | 814_28 | ASI~9~021; REF~G7~Q002 or T003; BGN07=09; BGN06 must equal BGN02 from 814_16; LIN07=MVI | TDSP completes MVI unexecutable | 1
Day 15

## STK01
|  | Script ID | STK01
|  | Script Name | Multiple (2) MVIs from same CR
|  | Script Storyline | CR1 will initiate multiple MVIs on Day 1 for different RMRD - Day 10 and Day 15. Both MVIs will be scheduled and effectuate. The Final reads and final bills are sent for both MVIs.
|  | Success Criteria | 2 MVIs sent from Same CR - both MVIs are scheduled and effectuate. CR1 (Customer A) has power from Day 10 to Day 15 CR1 (Customer B) has power from Day 15 to End of Script
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | de-energized | No
|  | Operating Rule | E12 |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 10 (DTM~375) | MVI requested for Day 10 for Customer A | 1 |  |  | CR1
| Day 1 |  | CR1 | ERCOT | 814_16 | RMRD = Day 15 (DTM~375) | MVI requested for Day 15 for Customer B | 2 |  |  | CR1
| Day 2 | Day 02 | ERCOT | TDSP | 814_03 | RMRD = Day 10 | MVI requested for Day 10 | 1 |  |  | CR1
| Day 2 |  | ERCOT | TDSP | 814_03 | RMRD = Day 15 | MVI requested for Day 15 | 2 |  |  | CR1
| Day 3 | Day 03 | TDSP | ERCOT | 814_04 | SMRD = Day 10 | MVI scheduled for Day 10 | 1 |  |  | CR1
| Day 3 |  | TDSP | ERCOT | 814_04 | SMRD = Day 15 | MVI scheduled for Day 15 | 2 |  |  | CR1
Day 3
| Day 4 | Day 04 | ERCOT | CR1 | 814_05 | SMRD = Day 10 | MVI scheduled for Day 10 | 1 |  |  | CR1
| Day 4 |  | ERCOT | CR1 | 814_05 | SMRD = Day 15 | MVI scheduled for Day 15 | 2 |  |  | CR1
Day 4
X | Day 5 | Day 05 |  |  |  |  | Validate that ERCOT and TDSP have MVIs scheduled for Day 10 and Day 15
| Day 6 | Day 06
| Day 7 | Day 07
| Day 8 | Day 08
| Day 8 | [5 empty] | Day 1 of 2 day window for Day 10 MVI | 1 |  | E
| Day 9 | Day 09
| Day 9 | [5 empty] | Day 2 of 2 day window for Day 10 MVI | 1 |  | E
|  | Day 10 |  |  |  |  | Day 10 MVI Effectuates | 1 | MVI |  | CR1
Day 11
| Day 11 | Day 12
| Day 13 | Day 13 | ERCOT | CR1 | 814_06 | FMVO DTM~151 = Day 15 | FMVO of Customer A due to Day 15 MVI | 2
Day 13
| Day 13 | [5 empty] | Day 1 of 2 day window for Day 15 MVI | 2 |  | E
|  |  | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1
Day 14
|  | Day 14 | ERCOT | CR1 | 867_04 | BPT01 = SU | Initial Read for Customer A | 1
| Day 14 | [5 empty] | Day 2 of 2 day window for Day 15 MVI | 2 |  | E
|  | Day 15 |  |  |  |  | Day 15 MVI Effectuates | 2 | MVI |  | CR1
| Day 16 | Day 16
Day 17
|  | Day 18 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer B | 2
|  |  | TDSP | ERCOT | 867_03 | BPT07 = F | Final Usage for Customer A | 2
|  |  | TDSP | CR1 | 810_02 | BIG07 = FB | Final Invoice for Customer A | 2
|  | Day 19 | ERCOT | CR1 | 867_03 | BPT07 = F | Final Usage for Customer A | 2
|  |  | ERCOT | CR1 | 867_04 | BPT01 = SU | Initial Read for Customer B | 2
Day 17

## STK07
|  | Script ID | STK07
|  | Script Name | CR Receive FMVO notice
|  | Script Storyline | SIM CR2 initiates a MVI for Day 12, and MVI gets scheduled. SIM CR2 requests a cancel on MVI, MVI is placed in Cancel Pending. TDSP holds the 814_08 B40 and does not process until the 814_08 COV has been processed. SIM CR3 initiates a MVI for Day 13. CR1 (ROR) sends a MVO for Day 18. Both get scheduled. Force MVO sent to CR1 at beginning of evaluation period for Day 12 MVI. Cancel response not received and evaluation period for Day 13 MVI starts. Cancel Pending MVI is forced cancelled by ERCOT and cancel is sent to CR1, SIM CR2, and TDSP. Force MVO sent to CR1 because of Day 13. Two days prior to CR1's MVO request, ERCOT evaluates and determines they are not scheduled to be the ROR and cancels the MVO.
|  | Success Criteria | Day 12 MVI is in cancel state; ERCOT force cancels Day 12 MVI. Day 13 MVI effectuates and Force MVO sent to CR1 because not ROR. CR1 has power from start of script to Day 13. CR3 has power from Day 13 to end of script. NOTE: The 810 Final may be sent for the MVI on Day 13. The 867 Final and 810 Final may be sent for the MVO on Day 18. There are no checklist items for these transactions.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule | E6, E15, E26, R7 |  | TRACK | New CR
|  | Simulated Entity | CR2 | CR3
|  | Duns Number | 111111112 | 111111113
|  | Number of CR's | 3
|  |  | ERCOT | TDSP | CR1 | SIM CR2 | SIM CR3
|  | Pretest Setup | None | None | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01
Day 02
Day 03
|  | Day 04 | CR1 | ERCOT | 814_24 | RMRD = Day 18 | MVO requested for Day 18 for Current Customer (Customer C) | 3
|  | Day 05 | SIM CR2 | ERCOT | 814_16 SIM | RMRD = Day 12 | MVI requested for Day 12 for Customer A | 1
|  |  | ERCOT | TDSP | 814_24 | RMRD = Day 18 | MVO requested for Day 18 for Current Customer (Customer C) | 3 |  |  | CR1
| Day 1 | Day 06 | ERCOT | TDSP | 814_03 | RMRD = Day 12 | MVI requested for Day 12 for Customer A | 1 |  |  | SIM CR2
|  |  | SIM CR3 | ERCOT | 814_16 SIM | RMRD = Day 13 | MVI requested for Day 13 for Customer B | 2
|  |  | TDSP | ERCOT | 814_25 | RMRD = Day 18 | MVO scheduled for Day 18 | 3 |  |  | CR1
| Day 2 | Day 07 | TDSP | ERCOT | 814_04 | SMRD = Day 12 | MVI scheduled for Day 12 | 1 |  |  | SIM CR2
| Day 3 |  | ERCOT | TDSP | 814_03 | RMRD = Day 13 | MVI requested for Day 13 for Customer B | 2 |  |  | SIM CR3
|  |  | ERCOT | CR1 | 814_25 | RMRD = Day 18 | MVO scheduled for Day 18 | 3
| Day 3 | Day 08 | ERCOT | SIM CR2 | 814_05 SIM | SMRD = Day 12 | MVI scheduled for Day 12 | 1
| Day 3 |  | TDSP | ERCOT | 814_04 | SMRD = Day 13 | MVI scheduled for Day 13 | 2 |  |  | SIM CR3
| Day 4 | Day 09 | ERCOT | SIM CR3 | 814_05 SIM | SMRD = Day 13 | MVI scheduled for Day 13 | 2
|  |  | SIM CR2 | ERCOT | 814_08 SIM | REF~1P~B40 | SIM CR2 request to cancel MVI - Customer A | 1
X | [6 empty] | Validate that ERCOT and TDSP have MVI scheduled for Day 12 and Day 13 and a MVO scheduled for Day 18
|  | Day 10 | ERCOT | TDSP | 814_08 | REF~1P~B40 | ERCOT forwards cancel request to TDSP; TDSP Holds the 814_08 and does not process until after the 814_08 COV is received and processed. | 1 |  |  | SIM CR2
| Day 6 |  | ERCOT | CR1 | 814_06 | FMVO DTM~151 = Day 12 | Force MVO sent because of SIM CR2 MVI (Day 12) | 1
Day 6
[7 empty] | Day 1 of 2 day window for Day 12 MVI | 1 |  | E
|  | Day 11 | ERCOT | CR1 | 814_08 | REF~1P~COV | ERCOT force cancels the FMVO sent to CR1 because of MVI (Day 13) b/c of cancel pending status | 1
|  |  | ERCOT | SIM CR2 | 814_08 SIM | REF~1P~COV | ERCOT force cancels SIM CR2 MVI (Day 12) E15 because of MVI (Day 13) b/c of cancel pending status | 1
| Day 7 |  | ERCOT | TDSP | 814_08 | REF~1P~COV | ERCOT force cancels SIM CR2 MVI (Day 12) E15 because of MVI (Day 13) b/c of cancel pending status | 1 |  |  | SIM CR2
| Day 7 |  | ERCOT | CR1 | 814_06 | FMVO DTM~151 = Day 13 | Force MVO sent because of SIM CR3 MVI (Day 13) | 2
| Day 7 | [5 empty] | Day 1 of 2 day window for Day 13 MVI | 2 |  | E
[7 empty] | Day 2 of 2 day window for Day 13 MVI | 1 |  | E
|  | Day 12 |  |  |  |  | Day 12 MVI Does Not Effectuate | 1 | MVI
|  |  | TDSP | ERCOT | 814_09 | REF~1P~COV | Accept Response | 1 |  |  | SIM CR2
|  |  | TDSP | ERCOT | 814_09 | REF~1P~B40 | Response to CR's cancel sent on Day 12; ERCOT will not forward because the business process is closed due to Demand Cancels sent on Day 22 | 1 |  |  | SIM CR2
Day 8
| Day 9 | [5 empty] | Day 2 of 2 day window for Day 13 MVI | 2 |  | E
| Day 11 | Day 13 |  |  |  |  | Day 13 MVI Effectuates | 2 | MVI
| Day 12 | Day 14
| Day 13 | Day 15
|  | Day 16 | ERCOT | CR1 | 814_08 | REF~1P~ANL | CR1 is no longer scheduled to be the ROR - ERCOT cancels the MVO (E6) | 3
|  |  | ERCOT | TDSP | 814_08 | REF~1P~ANL | Cancel goes to TDSP (E6) | 3 |  |  | CR1
|  |  | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Meter Read for SIM CR3 - Customer B | 2 |  |  | SIM CR3
|  |  | TDSP | ERCOT | 867_03 | BPT07 = F | Final Read for Customer C | 2 |  |  | CR1
| Day 14 | [5 empty] | Day 1 of 2 day window for Day 18 MVO | 3 |  | E
|  | Day 17 | TDSP | ERCOT | 814_09 | REF~1P~ANL | Cancel goes to TDSP (E6) | 3 |  |  | CR1
|  |  | ERCOT | SIM CR3 | 867_04 SIM | BPT01 = SU | Initial Meter Read for SIM CR3 - Customer B | 2
|  |  | ERCOT | CR1 | 867_03 | BPT07 = F | Final Read for Customer C | 2
Day 15
| Day 16 | [5 empty] | Day 2 of 2 day window for Day 18 MVO | 3 |  | E
| Day 12 | Day 18 |  |  |  |  | Day 18 MVO Does Not Effectuate | 3 | MVO

## STK10
|  | Script ID | STK10
|  | Script Name | Switch Earlier Than Move-in and Move-out, Move-In Received First. Same CR
|  | Script Storyline | CR1 initiates a MVI for Day 11, a Self Selected switch for Day 07, and a MVO for Day 14. All three orders get stacked and scheduled at TDSP and ERCOT. TDSP will manipulate the final bill for Customer B to assure that both the SAC10 and SAC11 are populated in the 810_02.
|  | Success Criteria | Switch effectuates, MVI effectuates, MVO effectuates SIM CR2 (Customer A) has power from start of script to Day 07 CR1 (Customer A) has power from Day 07 to Day 11 CR1 (Customer B) has power from Day 11 to Day 14 Day 14 premised de-energized NOTE: The 867 Final may be sent for the Switch on Day 20. There are no checklist items for these transactions.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Commercial | Single Non IDR | None | SIM CR2 | No
|  | Operating Rule | E11 |  | TRACK | New TDSP or new TDSP /system
|  | Simulated Entity | CR2
|  | Duns Number | 111111112
|  | Number of CR's | 2
|  |  | ERCOT | TDSP | CR1 | SIM CR2
|  | Pretest Setup | None | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 5 | Day 01 | CR1 | ERCOT | 814_16 | LIN~1~SH~EL~SH~CE~SH~MVI RMRD = Day 11 (DTM~375) | MVI submitted by CR1 with RMRD = Day 11 (Customer B) | 1
Day 5
| Day 6 | Day 02 | ERCOT | TDSP | 814_03 | LIN~1~SH~EL~SH~CE~SH~MVI RMRD = Day 11 (DTM~375) | ERCOT forwards MVI from CR1 with RMRD of Day 11 to the TDSP | 1 |  |  | CR1
| Day 6 |  | CR1 | ERCOT | 814_01 | RMRD = Day 07 ( DTM~MRR) LIN~1~SH~EL~SH~CE~SH~SW | CR1 Submits Self Selected SW with RMRD = Day 07 (Customer A - current Customer) | 2
Day 6
| Day 7 | Day 03 | ERCOT | TDSP | 814_03 | RMRD = Day 07 ( DTM~MRR) LIN~1~SH~EL~SH~CE~SH~SW | ERCOT forwards SW from CR1 with RMRD = Day 07 to the TDSP | 2 |  |  | CR1
| Day 7 |  | CR1 | ERCOT | 814_24 | RMRD = Day 14 (DTM~376) LIN~1~SH~EL~SH~CE~SH~MVO | CR1 submits MVO with RMRD = Day 14 (Customer B) | 3
| Day 7 |  | TDSP | ERCOT | 814_04 | LIN~1~SH~EL~SH~CE~SH~MVI SMRD = Day 11 (DTM~150) | SMRD = Day 11 | 1 |  |  | CR1
Day 7
| Day 8 | Day 04 | ERCOT | TDSP | 814_24 | RMRD = Day 14 (DTM~376) LIN~1~SH~EL~SH~CE~SH~MVO | ERCOT forwards CR1 MVO to TDSP with RMRD - Day 14 | 3 |  |  | CR1
| Day 8 |  | ERCOT | CR1 | 814_05 | SMRD = Day 11 (DTM~150) | SMRD = Day 11 | 1
| Day 8 |  | TDSP | ERCOT | 814_04 | SMRD = Day 07 (DTM~150) | TDSP responds to CR1 SW Request SMRD = Day 07 | 2 |  |  | CR1
Day 8
| Day 9 | Day 05 | ERCOT | CR1 | 814_05 | SMRD = Day 07 (DTM~150) | ERCOT forwards TDSP's Response SMRD = Day 07 | 2
| Day 9 |  | TDSP | ERCOT | 814_25 | SMRD = Day 14 (DTM~376) ASI~WQ~002 | TDSP responds to CR1 MVO with SMRD = Day 14 | 3 |  |  | CR1
|  |  | ERCOT | SIM CR2 | 814_06 SIM | FMVO DTM~151 = Day 20 | Force Move Out sent because of CR1 Switch | 2
[7 empty] | Day 1 of 2 day window for Day 07 SW |  |  | E
| Day 9 | [5 empty] | Validate ERCOT and TDSP have SW scheduled for Day 07; MVI scheduled for Day 11; MVO scheduled for Day 14
| Day10 | Day 06 | ERCOT | CR1 | 814_25 | SMRD = Day 14 (DTM~376) ASI~WQ~002 | ERCOT forwards TDSP response to CR1 SMRD = Day 14 | 3
| Day 10 | [5 empty] | Day 2 of 2 day window for Day 07 SW |  |  | E
| Day 11 | Day 07 |  |  |  |  | Day 07 SW Effectuates | 2 | SW
| Day 12 | Day 08
| Day 20 | Day 09 | ERCOT | CR1 | 814_06 | FMVO DTM~151 = Day 11 | ERCOT submits forced MVO due to CR1 MVI | 1
| Day 20 | [5 empty] | Day 1 of 2 day window for Day 11 MVI | 1 |  | E
| Day 21 | Day 10
|  |  | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Meter Read for CR1 SW - Customer A | 2 |  |  | CR1
Day 21
| Day 21 | [5 empty] | Day 2 of 2 day window for Day 11 MVI | 1 |  | E
Day 11
|  |  | ERCOT | CR1 | 867_04 | BPT01 = SU | Initial Meter Read for CR1 SW - Customer A | 2
| Day 22 | [5 empty] | Day 11 MVI Effectuates | 1 | MVI
Day 12
| Day 11 | [5 empty] | Day 1 of 2 day window for Day 14 MVO | 3 |  | E
|  | Day 13 |  |  |  |  | Day 2 of 2 day window for Day 14 MVO | 3 |  | E
Day 24
|  | Day 14 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Meter Read for CR1 MVI - Customer B | 1 |  |  | CR1
|  |  | TDSP | ERCOT | 867_03 | BPT07 = F | TDSP sends final meter read to ERCOT for Customer A | 1 |  |  | CR1
|  |  | TDSP | CR1 | 810_02 | BIG07 = FB | Final Bill for Customer A | 1
| Day 25 | [5 empty] | Day 14 MVO Effectuates | 3 | MVO
| Day 26 | Day 15
|  |  | ERCOT | CR1 | 867_04 | BPT01 = SU | Initial Meter Read for CR1 MVI - Customer B | 1
|  |  | ERCOT | CR1 | 867_03 | BPT07 = F | TDSP sends final meter read to ERCOT for Customer A | 1
Day 26
|  | Day 16 | TDSP | ERCOT | 867_03 | BPT07 = F | TDSP sends final meter read to ERCOT for Customer B | 3 |  |  | CR1
|  |  | TDSP | CR1 | 810_02 | BIG07 = FB | Final Bill for Customer B SAC10 and SAC11 to be populated | 3
Day 29
|  | Day 17 | ERCOT | CR1 | 867_03 | BPT07 = F | ERCOT forwards Final Meter Read for Customer B | 3
Day 29

## STK19
|  | Script ID | STK19
|  | Script Name | Multiple Tenant Based Permits
|  | Script Storyline | CR1 sends two MVI transactions on a premise that requires a tenant based permit. All requested dates pass before the permit is received. The permit is received for the Day 9 MVI. The Day 11 MVI stays in a permit pending status until the 20 day time limit is reached. At that point, it is cancelled by ERCOT. NOTE: The TDSP must look to match the Permit Name to the name(s) on the Move-In transaction. The TDSP will not look for a match on "Permit Name" if the permit is received with a blank Permit Name. If the permit is received with a Permit Name, the TDSP will compare against the Permit Name, the Contact Name and the Customer Name in the Move-In. If any one of these three fields is a reasonable match, the TDSP will apply the Permit to the Move-In. NOTE: TNMP does not execute this script
|  | Success Criteria | The first MVI (Day 9) is completed successfully; the second MVI (Day 11) is cancelled at the end of the 20 day permit period. Premise de-energized from Day 1 to Day 15 CR1 (customer A) has power from Day 15 to end of script
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential Small Commercial | Single Non IDR | None | De-Energized | No
|  | Operating Rule | E10, E26, T2, R4 |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01
Day 02
Day 03
Day 04
Day 05
|  | Day 06 | CR1 | ERCOT | 814_16 | RMRD = Day 9 (DTM~375) PER~PN | MVI requested for Day 9 for Customer A | 1 |  |  | CR1
|  | Day 07 | ERCOT | TDSP | 814_03 | RMRD = Day 9 (DTM~375) PER~PN | MVI requested for Day 9 for Customer A | 1 |  |  | CR1
|  |  | CR1 | ERCOT | 814_16 | RMRD = Day 11 (DTM~375) PER~PN | MVI Requested for Day 11 for Customer B | 2 |  |  | CR1
Day 4
| Day 1 | Day 08 | TDSP | ERCOT | 814_28 | BGN07 = PT | 814_28 indicates tenant based permit pending | 1 |  |  | CR1
| Day 1 |  | ERCOT | TDSP | 814_03 | RMRD = Day 11 (DTM~375) PER~PN | MVI Requested for Day 11 for Customer B | 2 |  |  | CR1
| Day 12 | Day 09 |  |  |  |  | Day 9 MVI for Customer A Does Not Effectuate (effectuates later) | 1 | MVI
| Day 12 |  | ERCOT | CR1 | 814_28 | BGN07 = PT | 814_28 indicates tenant based permit pending | 1 |  |  | CR1
|  |  | TDSP | ERCOT | 814_28 | BGN07 = PT | 814_28 indicates tenant based permit pending | 2 |  |  | CR1
| Day 13 | Day 10
| Day 13 |  | ERCOT | CR1 | 814_28 | BGN07 = PT | 814_28 indicates tenant based permit pending | 2 |  |  | CR1
Day 13
| Day 14 | Day 11 |  |  |  |  | Day 11 MVI for Customer B Does Not Effectuate | 2 | MVI
| Day 15 | Day 12
X |  | Day 13 |  |  |  |  | Validate that ERCOT and TDSP have both MVIs in permit pending status
Day 6
| Day 17 | Day 14 | TDSP | ERCOT | 814_04 | Indicates permit received for Day 9 MVI | Permit Received for lifecycle 2 - Day 9 MVI | 1 |  |  | CR1
|  | Day 15 |  |  |  |  | Day 9 MVI Effectuates | 1 | MVI
| Day 18 |  | ERCOT | CR1 | 814_05 | Indicates permit received | Permit Received for lifecycle 2 - Day 9 MVI | 1 |  |  | CR1
Day 16
| Day 8 | Day 17
| Day 21 | Day 18 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial read for CR1's Day 9 MVI for Customer A | 1 |  |  | CR1
| Day 22 | Day 19 | ERCOT | CR1 | 867_04 | BPT01 = SU | Initial read for CR1's Day 9 MVI for Customer A | 1 |  |  | CR1
| Day 23 | Day 20
| Day 24 | Day 21
| Day 25 | Day 22
| Day 26 | Day 23
| Day 28 | Day 24
| Day 28 | Day 25
Day 26
| Day 30 | Day 27
| Day 31 | Day 28
| Day 32 | Day 29
| Day 36 | Day 30
| Day 46 | Day 31 | ERCOT | TDSP | 814_08 | REF~1P~PNR | Permit is not received within 20 days of the requested date and ERCOT sends a cancel (Customer B) | 2 |  |  | CR1
| Day 47 | Day 32 | TDSP | ERCOT | 814_09 | ASI~WQ~024 REF~1P~PNR | Accept Response | 2 |  |  | CR1
| Day 47 |  | ERCOT | CR1 | 814_08 | REF~1P~PNR | Permit is not received within 20 days of the requested date and the request is cancelled. (Customer B) | 2 |  |  | CR1

## STK29
|  | Script ID | STK29
|  | Script Name | Move-In with Customer Information Change
|  | Script Storyline | CR1 initiates a MVI for Day 5. MVI effectuates on Day 5. On Day 8 CR sends updated contact name and critical care information to the TDSP.
|  | Success Criteria | Day 5 MVI is created in all systems and effectuates CR1 (Customer A) has power from Day 5 until end of script Customer information changes are sent from the CR to the TDSP
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | N/A | No
|  | Operating Rule |  |  | TRACK | Change of Service Provider
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01 | CR1 | ERCOT | 814_16 | LIN~1~SH~EL~SH~CE~SH~MVI RMRD = Day 5 (DTM~375) | MVI submitted by CR1 with RMRD = Day 5 (Customer A) | 1
| Day 3 | Day 02 | ERCOT | TDSP | 814_03 | LIN~1~SH~EL~SH~CE~SH~MVI RMRD = Day 5 (DTM~375) | ERCOT forwards MVI from CR1 with RMRD of Day 5 to the TDSP | 1 |  |  | CR1
|  | Day 03 | TDSP | ERCOT | 814_04 | LIN~1~SH~EL~SH~CE~SH~MVI SMRD = Day 5 (DTM~150) | SMRD = Day 5 | 1 |  |  | CR1
| Day 3 | [5 empty] | Day 1 of 2 day window for Day 5 MVI | 1 |  | E
|  | Day 04 | ERCOT | CR1 | 814_05 | LIN~1~SH~EL~SH~CE~SH~MVI SMRD = Day 5 (DTM~150) | SMRD = Day 5 | 1 |  |  | CR1
| Day 5 | [5 empty] | Day 2 of 2 day window for Day 5 MVI | 1 |  | E
| Day 6 | Day 05 |  |  |  |  | Day 5 MVI Effectuates | 1 | MVI |  | CR1
Day 06
| Day 7 | Day 07 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Meter Read for CR1 MVI - Customer A | 1 |  |  | CR1
Day 7
| Day 8 | Day 08 | ERCOT | CR1 | 867_04 | BPT01 = SU | Initial Meter Read for CR1 MVI - Customer A | 1 |  |  | CR1
Day 8
|  | Day 09 | CR1 | TDSP | 814_PC | REF~SU~Y N1~FJ | CR updates premise information with Special Needs Indicator and Customer Contact Name. | 2 |  |  | CR1
|  | Day 10 | TDSP | CR1 | 814_PD | ASI~WQ~001 | Response to CR1 indicating the premise has been updated. | 2 |  |  | CR1