## Sheet1
TX SET Meeting Notes / Action Items
01/22/2014and 01/23/2014 ( 2 day meeting)
Agenda Item: | Decision / Resolution | Action Items :
2014 Elections | • Chair Diana Rehfeldt • Vice Chair Kyle Patrick
December 2013 Meeting Notes | No Changes | Have document posted to December 2013 Meeting Page
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out. Review Proposed NPRR Draft to remove 867_02's from process for both Mass Transition and Acquisition Transfer. Other Ideas? | • ERCOT and TDSPs to analyze how many more transactions could be processed in a day by eliminating the 86702s. • Rob Bevill to speak with SMT to determine how quickly the data will be returned to the REP after historical data is requested. • John Schatz to have the SMT question added to the next AMWG meeting agenda.
o REPs prefer to obtain historical data from the 867_02s since SMT changes are still in progress that will allow REPs to obtain historical interval data. Also it may take time for the historical data to be returned in a timely manner.  The REPs requested additional analysis be completed that reflects how many more transactions can be processed per day if the 86702s are eliminated.  The group discussed the availability of historical interval data from the SMT site.
o The group discussed reducing the effective date on Mass Transitions from two days out to one day out.  The group stated that the current two day out transaction effective date is compliant with the existing POLR Rule, but if the rule changes to reduce the effective date to one day out, the market can support it.
 There were concerns from the group related to reducing transaction effective dates to one day out. • Two days out gives the customer more of a chance to switch to a REP of their choice • While one day out would help reduce the uplift or credit exposure of the wholesale market, the POLR would experience an increase in credit risk. • Two days out allows the REP a better opportunity to schedule power • It was noted that the Credit Working Group is also presenting some timing changes to TAC
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
ERCOT Market Testing | Review of current market testing process--The group continued to discuss and updatethe testing requirements matrix. | • Kyle Patrick to begin re-formatting the matrix • The MOU-ECs to review and give feedback for their testing requirements
Issues
134-Non-CSA CR sends a MVO with the indicator for bypass CSA at ERCOT. Non-CSA CR is not always the owner of the CSA, causing the ESI ID to become de-energized without CSA CRs knowledge | • NPRR583--Update from PRS--1/16 voted to table until next month to receive more information from ERCOT | Kyle Patrick, Rob Bevill and Kathryn Thurman to revise the NPRR language as discussed in the meeting
o ERCOT provided the number of occurrences (between 1/14 and 1/22) where a CR other than the CSA CR sent the de-energize code on Move outs. ERCOT will continue to pull these statistics until the next RMS meeting.  200 Move outs were sent where the CR was not the current CSA CR  739 Move outs were sent where there was no CSA CR relationship  2 CRs out of 27 total CRs sent the bulk of these occurrences  ERCOT to contact the CRs using the code inappropriately
o The group agreed that the NPRR should be modified to remove the validation request, but to add stronger language that instructs CRs when it is appropriate to use the de-energize code
139- Change the 814_20 to add submission to request the transmission load | Submitted by ERCOT--Withdrawn by submitter
RMGRR updates | • RMGRR116 Acquisition Transfer to TAC Jan--ERCOT noted that they made some minor changes to the document that were missed. ERCOT to send these to TX SET and RMS leadership for review. • RMGRR118 Non Standard Metering to TAC Jan • RMGRR119 TX SET Cleanup to TAC Jan
Other Business
IAG Market Procedure Question | Appropriate market procedures for Inadvertent Gains issues in cases of customer Opt Out
| o Scenario 1—An AMS OPT Out customer gives an incorrect address or ESI ID to the Gaining CR which belongs to a customer currently on a TOU plan account  The meter could be changed to a Non-standard meter in error  The group agreed that the error probably would be discovered before changes are made to the premise  The group agreed that the Gaining CR will absorb the cost to return the customer to its original state per the Rule if the error is not caught until after the changes are made to the premise | TDSPs to review Scenario 1 with their respective companies.
o Scenario 2—The Inadvertently Gained customer is currently receiving service with a non-standard meter  The group agreed that the correction will follow the current Inadvertent Gain process used in the market and the Gaining CR will absorb these costs as well
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Next Meeting |  Feb 17th RM 168 MET CENTER  Feb 18th cancelled to allow plenty of time for those attending the Sharyland REP Workshop to travel to Dallas
Attendees
Diana Rehfeldt TNMP | Kyle Patrick Reliant | Jesse Macias AEP
Gricelda Calzada AEP | Monica Jones Reliant | Paul Yockey ERCOT
Ed Echols ONCOR | Carolyn Reed Centerpoint Energy | Kathy Scott Centerpoint Energy
Kathryn Thurman ERCOT | Jim Lee Direct Energy | Paula Shadle Nueces
Kaci Jacobs TXU | Kim Wall PPL Solutions LLC | Rhonda Bell Nueces
John Schatz TXU | Michael Glass Sharyland
Mike Woolsey ONCOR | Rob Bevill CNRG/Green Mountain
Phone:
Amy Rafferty ESG | Barbara Goubeaud EC Infosystems | Sandra Tindall ERCOT
Joe Lindsay Systrends | Suzy Clifton ERCOT | Mary Sithihao Stream Energy
Rita Cardenas AEP | Heather Mesa Sharyland | Jacqueline Stevenson EC Infosystems
Roger Tenebown ISTA NA | Mandy Baud ERCOT