## PR010_03 UCs
Use Case | Description | Status | Notes | Priority
1 | Redirect PMVI Fees (new subtype) | Finalized | Implemented June 2012 w/TXSET 4.0 | Critical
13 | Create Usage and Billing Subtypes for LSE Data | Finalized | Implemented June 2012 w/TXSET 4.0 | Critical
18 | Creation of a single subtype for “Expedited Switch Rescission” | Finalized | Implemented June 2012 w/TXSET 4.0 | Critical
19 | New subtype(s) are needed for tampering-related issues (Switch hold four hour process) | Finalized | Implemented June 2012 w/TXSET 4.0 | Critical
29 | Catch-all subtype (Market Rule) | Finalized | Implemented June 2012 w/TXSET 4.0 | Critical
3 | Distinct Usage and Billing Subtypes (Missing and Dispute) | Finalized | (MTUB1; MTUB2) 02.25.14 | High
8 | Increase validations to prevent users from entering invalid information into pre-defined fields. | Finalized | Included with (MTUB2) 02.25.14 | High
9 | Changes to Inadvertent Losing workflow | Finalized | (MTIAG1; MTIAG2) 02.25.14 | High
17 | Add “First Touched by TDSP” to DEVLSE | Finalized | (DEVLSE) Use Cases 17 & 21 Combined 02.25.14 | High
21 | Add Service History to DEVLSE | Finalized | (DEVLSE) Use Cases 17 & 21 Combined 02.25.14 | High
23 | Add the ability to retrieve and download attachments via the API | Finalized | (API ATTCH) Use Cases 23 & 30 Combined 03.25.14 | High
24 | Add Additional Subtypes to the Contact Type field in the MarkeTrak Contact List (Rolodex) table | Finalized | (ADMIN24) 03.25.14 | High
25 | Validate submitting CR as ROR during service period (Usage and Billing) | Finalized | Included with (MTUB1 & MTUB2) 03.25.14 | High
27 | Duplicate ESIID message contains hyperlink | Finalized | Combined with (MTUB1) 03.25.14 | High
33 | Automatic transition for no regaining Siebel status (IAG) | Finalized | PR010_03 | High
34 | Change specific warning messages to error messages | Finalized | PR010_03 | High
35 | Add DUNS to MarkeTrak generated emails with MP names | Finalized | PR010_03 | High
36 | Add SMRD and MVI priority for Regaining Transaction | Finalized | PR010_03 | High
37 | Send an escalation email if an issue has been in a New state for 2 days | Finalized | PR010_03 | High
46 | Change field label from “Transaction Submit Date” to “Date Transaction Submitted”. Change “Submit Date” to “Regain Date” field. Add help function to this field. | Finalized | PR010_03 | High
4 | New "Add User" functionality to Administrator feature | Finalized | PR010_03 | Medium
15 | Description - The ability to return individual issue comments on GUI reports and background reports – date configurable | Finalized | PR010_03 | Medium
22 | Add 867_02 to Missing TXNS subtype | Finalized | Combine with MP 32 | Medium
32 | Add 814_PC and 814_PD in the current drop down selections (Missing TXN) | Finalized | Combine with MP 22 | Medium
26 | Review for add’l canned background reports | Finalized | PR010_03 | Medium
28 | Auto-close escalation message | Finalized | PR010_03 | Medium
30 | Create the ability for API users to execute BR(s) via Query List calls | Finalized | (API ATTCH) Use Cases 23 & 30 Combined 03.25.14 | Medium
31 | Require 814_20 field for Premise Type/Service Address subtypes | Finalized | PR010_03 | Medium
40 | Add Optional fields to the “997 Issues” sub-type that allow the REP to select the Trans Type or enter the ESI ID in question | Finalized | PR010_03 | Medium
44 | Add to the background reports the ability to display in the result set a designation of CR or TDSP on Cancel with Approval submittal. | Finalized | PR010_03 | Medium
5 | Change the name on the Submit Tree for subtype “Missing TRXN” to “Enrollment Transactions.” | Finalized | PR010_03 | Medium
43 | Create a notification for the Switch Hold process so that when the TDU creates the MT, the MT tool would automatically send an email to the CSG team members. | Finalized | PR010_03 | Medium
10 | Update Bulk Insert Templates - Remove columns and rows that are no longer deemed necessary and “script time stamp entry” to simplify the submission process. Check formatting of templates | No UseCase needed as BulkInserts will be updated at the end of P3 project - Deferred | End of Project to implement changes - No UseCase needed as BulkInserts will be updated at the end of P3 project - Deferred
38 | Allow for multiple entries into Search Criteria fields such as ESIID and Issue ID | Need UseCase for PartB - Deferred | Need UseCase for PartB - Deferred - Serena Upgrade Possibility - Search multiple MT Issue IDs separated by commas post Serena

## MTUB1-MISSING
|  | Script ID | MTUB1
|  | Script Name | Distinct Usage and Billing Subtype (Missing)
|  | Script Storyline | From start to finish create an entire Missing SubType Issue.
|  | Success Criteria | MarkeTrak is available and processing issues; ESI ID populated must be a valid ESI ID in existence within ERCOT Registration database; Issue is successfully created and able to be transitioned to a resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | Missing SubType is selected from the MarkeTrak Submit Tree | User enters all required information with a StartTime of '11.01.2013' and selects 'OK' to create issue. User will receive ESIID duplicate warning with the Issue ID in the form of a hyperlink. Submitter selects hyperlink and issue opens in new window. Submitter closes window. Error message is returned stating 'Submitting MP is not the ROR for the StartTime on the issue'. CR enters correct date of '01.01.2014'. CR selects 'Ok' | MT submitted for Monthly Usage Period(s) (867s) missing from the ERCOT Lode Star Database; This script includes testing validation for UseCase 25 and UseCase 27. Make sure dates match Siebel. | 1
Day 2
| Day 3 |  | CR | TDSP | MarkeTrak Issue is created and transitioned to 'Assignee (TDSP)' with "New Assignee" state. TDSP is Responsible Party | TDSP user selects 'Begin Working' with "In Progress (Assignee)" state. | Issue completed by TDSP with comments | 1
| Day 5 |  | TDSP | CR | MarkeTrak Issue transitioned back to CR (Submitter) with "Pending Complete" state and CR is Responsible Party. | CR reviews issue and selects 'Complete' and MT issue is in a "Complete" state | Issue should be completed under new SubType (D2D Usage and Billing - Missing) | 1
Day 6
Day 2
Day 3
Day 4

## MTUB2-DISPUTE
|  | Script ID | MTUB2
|  | Script Name | Distinct Usage and Billing Subtype (Dispute)
|  | Script Storyline | From start to finish create an entire Dispute SubType Issue.
|  | Success Criteria | MarkeTrak is available and processing issues; ESI ID populated must be a valid ESI ID in existence within ERCOT Registration database; Issue is successfully created and able to be transitioned to a resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | Dispute SubType is selected from the MarkeTrak Submit Tree | User enters all required information with a StartTime of '11.01.2013' and selects 'OK' to create issue. Error message is returned stating 'Submitting MP is not the ROR for the StartTime on the issue'. CR enters correct date of '01.01.2014' and enters 'Invalid Date' in BGN field as well as special characters '%' and selects 'OK' to create issue. Defined Value 'Other' is selected from the Dispute category field and user is prompted for required comments. | MT submitted to dispute Monthly Usage Period (867 KWH) loaded in the ERCOT Lode Star Database or (810 Invoice). This script includes testing validation for UseCase 8 and UseCase 25. Make sure dates match Siebel. | 1
Day 2
| Day 3 |  | CR | TDSP | MarkeTrak Issue is created and transitioned to Assignee (TDSP) with "New Assignee" state. TDSP is Responsible Party | TDSP user selects 'Begin Working' with state of "In Progress (Assignee)". | Issue completed by TDSP with comments | 1
| Day 3 |  | CR | TDSP | MarkeTrak Issue is created and transitioned to Assignee (TDSP) with "New Assignee" state. TDSP is Responsible Party | TDSP user selects 'Begin Working' with state of "In Progress (Assignee)". | Issue completed by TDSP with comments | 1
| Day 5 |  | TDSP | CR | MarkeTrak Issue transitioned back to CR (Submitter) in "Pending Complete" state and CR as Responsible Party. | CR (Submitter) reviews issue and selects 'Complete' and MT issue is in a "Complete" state | Issue should be completed under new SubType (D2D Usage and Billing - Dispute) | 1
Day 6
Day 2
Day 3
Day 4

## MTIAG1
|  | Script ID | MTIAG1
|  | Script Name | Changes to Inadvertent Losing Workflow
|  | Script Storyline | Losing CR submits Inadvertent Losing issue. Gaining CR selects agree. Losing CR forwards to TDSP and workflow completes with Happy Path
|  | Success Criteria | The 'Agree' transition functions as expected
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR1 (Losing CR) | CR2 (Gaining CR) | IAL SubType is selected from the MarkeTrak Submit Tree | User enters all required information and selects 'OK' to create issue |  | 1
Day 2
| Day 3 |  | CR1 (Losing CR) | CR2 (Gaining CR) | MarkeTrak Issue is created and transitioned to CR2 in the state of "New (Gaining CR)". CR2 is Responsible Party | CR2 user selects 'Begin Working' with "In Progress (Gaining CR)" state. | CR2 selects 'Agree' and the issue is transitioned to CR1 in state of "New (Losing CR)". Resume current workflow after this step. No further testing needed. | 1
Day 6
Day 2
Day 3
Day 4

## MTIAG2
|  | Script ID | MTIAG2
|  | Script Name | Changes to Inadvertent Losing Workflow
|  | Script Storyline | Losing CR submits Inadvertent Losing issue. Gaining CR selects 'Return to Losing CR' and Losing CR doesn't have the ability to forward to the TDSP
|  | Success Criteria | Losing CR attempts to transition issue back to TDSP and receives error message.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR1 (Losing CR) | CR2 (Gaining CR) | IAL SubType is selected from the MarkeTrak Submit Tree | User enters all required information and selects 'OK' to create issue |  | 1
Day 2
| Day 3 |  | CR1 (Losing CR) | CR2 (Gaining CR) | MarkeTrak Issue is created and transitioned to CR2 in the state of "New (Gaining CR)". CR2 is Responsible Party | CR2 user selects 'Begin Working' with "In Progress (Gaining CR)" state. | CR2 selects 'Return to Losing CR' and enters comments. The issue is transitioned to CR1 in state of "New (Losing CR)". | 1
| Day 3 |  | CR2 (Gaining CR) | CR1 (Losing CR) | CR1 Selects 'Begin Working' and Issues transitions to "In Progress (Losing CR)" state | CR1 selects 'Send to TDSP' and receives an error message. CR1 selects 'Send to Gaining CR' and issue transtions to CR2 in state of "New (Gaining CR)" | If all parties agree, resume current workflow. No additional testing needed. | 1
Day 6
Day 2
Day 3
Day 4

## DEVLSE
|  | Script ID | DEVLSE1
|  | Script Name | Combing use cases (17 & 21) in this test script
|  | Script Storyline | CR submits DEV LSE StartTime change. ERCOT passes analysis and assigns to TDSP. TDSP selects 'Begin Working' and 'First Touched by TDSP' field is populated with timestamp. TDSP selects 'Modify/Reassign' to enter a different set of dates.
|  | Success Criteria | Touch by TDSP is populated as expected and TDSP is prompted for REP of Record history via the Modify/Reassign transition.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | ERCOT | DEV LSE (StartTime Change) is selected from Submit Tree | User enters all required information and selects 'OK' to create issue |  | 1
Day 2
| Day 3 |  | ERCOT | TDSP | ERCOT passes analysis and transitions to TDSP | "New Pending Approval" state, TDSP selects 'Begin Working' and First Touched by TDSP field is automaticlly populated with accurate timestamp. | TDSP Selects 'Modify/Reassign' and enters different date in 'New StartTime' field and selects 'OK'. TDSP is prompted for REP of Record history. Issue transitions to CR in "New Pending Approval" state. Current workflow resumes and no additional testing is needed. | 1
Day 6
Day 2
Day 3
Day 4

## API ATTCH
|  | Script ID | Submission of BackGround reports and retrieval of attachments via API
|  | Script Name | Combing use cases (23 & 30) in this test script
|  | Script Storyline | TDSP submits Counts of Subtype (BackGround report) via API. Retrieves the issue attachment via the API. Execute query detail which includes attachment ID.
|  | Success Criteria | BackGround report successfully submitted and attachment retrieved.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | TDSP | TDSP | TDSPs API creates XML to submit a BackGround report (Report Type = Counts of Subtype) | Select Live and/or Archive; Report destination = Issue Attachment. Project = IAG, DEV LSE. StartTime is provided. | Confirm that BackGround report is closed with attachment present. TDSP executes query detail to retrieve atttachment ID and API executess 'A get attachment call' and file is returned successfully. | 1
Day 2
Day 6
Day 2
Day 3
Day 4

## ADMIN24
|  | Script ID | ADMIN24
|  | Script Name | New Rolodex subtype escalations
|  | Script Storyline | Market Participant Admin goes into rolodex to select - SwitchHold subtype; Test timing of issue in CERT and is assigned to the appropriate primary escalation
|  | Success Criteria | Confirms the issues are being routed to the appropriate escalation contact
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR Admin | CR Admin | CR selects 'Manage Data' and 'MarkeTrak contacts list rolodex' from dropdown menu. Provide 'Company DUNs' in company field. Select Contact Type 'D2D IAG'. Select Contact Level 'Primary/Secondary'. Select 'Look Up' next to contact name | Select 'Primary/Secondary' escalation contact; Select update 'D2D SW Hold'.
Day 2
Day 6
Day 2
Day 3
Day 4

## Sheet3
Script ID
Script Name
Script Storyline
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | Missing SubType is selected from the MarkeTrak Submit Tree | User enters all required information and selects 'OK' to create issue | MT submitted for Monthly Usage Period(s) (867s) missing from the ERCOT Lode Star Database | 1
Day 2
Day 6
Day 2
Day 3
Day 4

## Sheet4
Script ID
Script Name
Script Storyline
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | Missing SubType is selected from the MarkeTrak Submit Tree | User enters all required information and selects 'OK' to create issue | MT submitted for Monthly Usage Period(s) (867s) missing from the ERCOT Lode Star Database | 1
Day 2
Day 6
Day 2
Day 3
Day 4

## Sheet5
Script ID
Script Name
Script Storyline
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | Missing SubType is selected from the MarkeTrak Submit Tree | User enters all required information and selects 'OK' to create issue | MT submitted for Monthly Usage Period(s) (867s) missing from the ERCOT Lode Star Database | 1
Day 2
Day 6
Day 2
Day 3
Day 4