## Sheet1
TX SET Meeting Notes / Action Items
2014-02-17
Agenda Item: | Decision / Resolution | Action Items :
January 2014 Meeting Notes | No Changes | Have notes posted to meeting page key documents
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out. Review Proposed NPRR Draft to remove 867_02's from process for both Mass Transition and Acquisition Transfer. Other Ideas?
• The group reviewed the notes from the TDSP / ERCOT conference call and determined that elimination of the automatic request for 867_02 Historical Usage transactions would result in a marginal improvement. • The group also discussed how initiating transactions outside of regular business hours might affect processing congestion. • ERCOT explained that around or after the 3rd day of the Event the number of ESI IDs should fluctuate slightly as ESi IDs are added and others are completed.
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
Flight Testing Update | • 13 New CRs (includes 9 Additional DUNS) are testing • Existing CRs: 15 CRs are testing with Sharyland, and 2 CRs are testing for a bank change • 3003 tasks are scheduled • Flight signup began 01/08/14 • Flight deadline was 01/15/14 • Connectivity kick-off conference call was 01/21/14 • Flight kick-off conference call was 02/14/14 • Day 1 transactions begin 02/17/14 • Flight scheduled to conclude 04/01/14 (contingency period until 04/16/14)
ERCOT Market Testing | Review of current market testing process--The group reviewed and agreed that the updated Matrix provided by Reliant was a good change. The group continued to discuss how to approach scripts and how to consolidate business scenarios in order to streamline the testing process | • Reliant to make changes to the new matrix as requested by the group. • Texas SET leadership and a two other market participants will have a subgroup meeting to begin creating more streamlined scripts.
Issues
134-Non-CSA CR sends a MVO with the indicator for bypass CSA at ERCOT. Non-CSA CR is not always the owner of the CSA, causing the ESI ID to become de-energized without CSA CRs knowledge | • NPRR583--Update from PRS--1/16 voted to table until next month to receive more information from ERCOT
| Texas SET agreed to request at RMS that NPRR583 be withdrawn and let RMS know that Texas SET will address the issue in the Retail Market Guide. It was agreed that Texas SET can revisit the validation request in the next Texas SET release. | Texas SET leadership will draft the withdrawal form to send to RMS. Green Mountain, Reliant and ERCOT will draft language for the RMG.
RMGRR updates | No updates
Other Business
IAG Market Procedure Question | Appropriate market procedures for Issues that Involve an Opt Out Customer
o Scenario 1—An AMS OPT Out customer gives an incorrect address or ESI ID to the Gaining CR which belongs to a customer currently on a TOU plan account  The meter could be changed to a Non-standard meter in error  The group agreed that the error probably would be discovered before changes are made to the premise  The group agreed that the Gaining CR will absorb the cost to return the customer to its original state per the Rule if the error is not caught until after the changes are made to the premise
o Scenario 2—The Inadvertently Gained customer is currently receiving service with a non-standard meter  The group agreed that the correction will follow the current Inadvertent Gain process used in the market and the Gaining CR will absorb these costs as well
The group determined that all questions had been answered at the last meeting
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Next Meeting |  Mar 19th RM 168 MET CENTER  Mar 20th RM 168 Met CENTER
Attendees
Diana Rehfeldt TNMP | Kyle Patrick Reliant
Gricelda Calzada AEP | Monica Jones Reliant
Kathryn Thurman ERCOT | Carolyn Reed Centerpoint Energy
Kaci Jacobs TXU | Seth Connel ERCOT
John Schatz TXU | Bill Reily ONCOR
Mike Woolsey ONCOR | Kathy Scott CNP
Phone:
Amy Rafferty ESG | Angela Lewis Champion Energy | Sandra Tindall ERCOT
Joe Lindsay Systrends | Suzy Clifton ERCOT | Mary Sithihao Stream Energy
Paul Yockey ERCOT | Dave Louder Nueces
Roger Tenebown ISTA NA | Teresa Rodriquez Stream Energy
Ed Echols ONCOR | Becky Taylor CNP