## Slide 1
Flight Testing Update
Paul Yockey
Flight Administrator
Retail Market Subcommittee
04/01/14

## Slide 2
Retail Market Subcommittee
04/01/14
Flight 0214
Flight 0214 Summary
Flight 0214 is currently 96.93% complete
13 New CRs (includes 9 Additional DUNS) are testing
Existing CRs: 15 CRs are testing with Sharyland, and 2 CRs are testing for a bank change
All Connectivity and Penny tests for the original CRs including the child DUNS that needed to test with Sharyland completed by 2/20/2014 (Day 4 of the flight)
5 Existing CRs testing late entry (Emergency service provider change)
1 New CR withdrew from Flight 0214
4153 total tasks are scheduled

## Slide 3
Retail Market Subcommittee
04/01/14
Flight 0214
Schedule
Flight signup began 01/08/14
Flight deadline was 01/15/14
Connectivity kick-off conference call was 01/21/14
Flight kick-off conference call was 02/14/14
Day 1 transactions began 02/17/14
Flight scheduled to conclude 04/01/14 (contingency period until 04/16/14)

## Slide 4
Retail Market Subcommittee
04/01/14
Questions?