## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
April 10, 2014

## Slide 2: 2013 Project Update – Agenda
  Project Portfolio Update p. 3-7
    Recent/Upcoming Project Highlights
    2014 Release Targets
    2014 Project Spending Update
  Appendix
    Project Portfolio Gantt Chart p. 8-17
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent/Upcoming Project Highlights
2014 Release 2 Go-Lives (April 2014) In-Flight
  NPRR564 – Thirty-Minute Emergency Response Service (ERS) and Other ERS Services
  NPRR570 – Reduce RTM Settlement Timeline to Operating Day Plus Five
  CREZ Voltage Control and Coordination
  Various IT infrastructure projects
2014 Release 3 Go-Lives (June 2014) In-Flight
  2014 Market System Enhancements (June 1 release date)
    NPRR568 – Real-Time Reserve Price Adder Based on Operating Reserve Demand Curve
    NPRR555 – Load Resource Participation in Security-Constrained Economic Dispatch
    NPRR532 – Performance Measurement and Verification and Telemetry Requirements for Load Resources Providing Non-Spin
  Taylor Control Room Upgrade
Remaining 2014 Releases
  Due to the complexity and aggressive schedule of the 2014 Market System Enhancements project, great caution is being taken in launching additional projects that impact the systems involved in the June delivery
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2014 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
None
January
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
None
NPRR425(b) – GREDP, EIS portions
NPRR484(Ph1b) – Remaining Phase 1 items
SCR756(b) – Remaining portions of SCR
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
Moved to 2015
ü
ü
ü
June–1st week
Release Approach | Release 1 2/3 – 2/7 | Release 2 4/14 – 4/18 | Release 3 6/9 – 6/13 | Release 4 7/28 – 8/1 | Release 5 9/22–9/26 | Release 6 12/8–12/12 | 2014 TBD
On-Cycle | NPRR240 NPRR425(b) NOGRR105 NPRR509 | NPRR564 NPRR570 |  | NPRR491 NPRR571 SCR769 SCR772 SCR756(b) | NPRR485 NPRR500 NPRR543 NPRR559 | NPRR272 NPRR487 NPRR495 NPRR519 NPRR524 SCR771 | NPRR327 NPRR556 NPRR573 NPRR580 NPRR581 OBD(Shadow Price Caps) SCR774
Off-Cycle | NPRR416 NPRR575 |  | NPRR532 NPRR555 NPRR568 NPRR571 |  |  |  | SCR775 SCR777 SCR778 NPRR484(1b) NPRR527
Counts Total = 30 | 6 | 2 | 3 | 5 | 4 | 6 | 11
None
None
Retail: 2/22-2/23
Retail: 7/26-7/27

## Slide 5: 2014 Cash Flow Projection – Approved Projects
2014 project budget = $25M

## Slide 6: Business Integration Update – Appendix
  Appendix
    4/7/2014 Project Gantt
      In-flight items sorted by Project End Date
      “On Hold” projects listed separately
      “Not Started” items sorted by Project Start Date

## Slide 7
Project Portfolio Status – as of 4/7/2014

## Slide 8
Project Portfolio Status – as of 4/7/2014

## Slide 9
Project Portfolio Status – as of 4/7/2014

## Slide 10
Project Portfolio Status – as of 4/7/2014

## Slide 11
Project Portfolio Status – as of 4/7/2014

## Slide 12
Project Portfolio Status – as of 4/7/2014

## Slide 13
Project Portfolio Status – as of 4/7/2014

## Slide 14
Project Portfolio Status – as of 4/7/2014

## Slide 15
Project Portfolio Status – as of 4/7/2014