## Slide 1
Project Prioritization Review
April 10, 2013

## Slide 2: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR571 – ERS Weather-Sensitive Loads Requirements | Apr 2014 | 2014-R4 | $30k-$40k | Earth Networks
NPRR487 – QSGR Dispatch Adjustment | May 2014 | 2014-R6 | $25k-$45k | Luminant
NPRR495 – Changes to Ancillary Services Capacity Monitor | May 2014 | 2014-R6 | $105k-$125k | MISUG
NPRR500 – Posting of Generation that is Off but Available | May 2014 | 2014-R5 | $60k-$75k | Morgan Stanley
NPRR527 – Req. Combined Cycle Telemetry for Op. Awareness and PDCWG Analysis | May 2014 | 2014-R6 | $110k-$110k | ERCOT
NPRR543 – Message for Confirmed E-Tags | May 2014 | 2014-R5 | $40k-$60k | Tenaska
NPRR559 – Revisions to MCE Calculation | May 2014 | 2014-R5 | $10k-$15k | ERCOT
NPRR272 – Definition and Participation of Quick Start Generation Resources | Jul 2014 | 2014-R6 | $145k-$160k | ERCOT
NPRR327 – State Estimator Data Redaction Methodology | Jul 2014 | TBD | $155k-$175k | ERCOT
NPRR519 – Exemption of ERS-Only QSEs from Collateral & Capitalization Requirements | Jul 2014 | 2014-R6 | $40k-$60k | ERCOT
NPRR524 – Resource Limits in Providing Ancillary Service | Jul 2014 | 2014-R6 | $50k-$75k | GDF Suez
SCR771 – Allow Ind. Master QSE to Represent Split Gen. Resources | Jul 2014 | 2014-R6 | $95k-$110k | Sandy Creek
NPRR256 – Sync PRR787, Add Non-Compliance Lang. to QSE Performance Standards | Aug 2014 | 2015-R2 | $100k-$250k | Luminant
NOGRR084 – Daily Grid Operations Summary Report | Sep 2014 | 2015-R3 | $300k-$500k | MISUG
NPRR210 – Wind Forecasting Change to P50, Sync with PRR841 | Oct 2014 | 2015-R2 | $45k-$55k | Morgan Stanley
NPRR439 – Updating a Counter-Party’s Available Credit Limit for Current Day DAM | Oct 2014 | 2015-R2 | $125k-$135k | ERCOT
NPRR553 – Monthly BLT Payment and Charge for Presidio Exception | Oct 2014 | 2015-R2 | $10k-$25k | CSWG
NPRR455 – CRR Shift Factors Report | Nov 2014 | 2015-R3 | $245k-$270k | MISUG
ERCOT requests your input: Are these the most important revision requests to work on over the next few months?
Moved from April 2014
Moved from April 2014
Moved from April 2014