|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report March 2014 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 230 active generation interconnection requests totaling over 58,100 MW. This includes over 26,700 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $962.5 Million. - Transmission Projects endorsed in 2013 total $349.8 Million. No transmission projects endorsed in 2014 (Jan. through March, 2014). - All projects (in engineering, routing, licensing and construction) total approximately $4.4 Billion. - Transmission Projects energized in 2014 total about $123.3 Million. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Approved for Synchronization	1

1.3	New Generation Approved for Commercial Operations	1

1.4	Summary of Generation Interconnection Requests	1

1.5	Projects with Interconnection Agreements	5

1.6	Projects Undergoing Full Interconnection Studies with Confidentiality Waived	6

1.7	Generation Projects Undergoing Full Interconnection Studies	6

1.8	Wind Generation Capacity Installed by Year	10

2.	Regional Planning Group Project Reviews	10

3.	Asynchronous Tie Interconnection	11

4.	Planning Model Activities	12

5.	Other Notable Activities	12

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

14INR0047 – Wake Wind Energy – 299 MW in Floyd and Crosby Counties

## New Generation Approved for Synchronization

- 13INR0021 – Ferguson Replacement CT1 – 186 MW in Llano County

- 13INR0021 – Ferguson Replacement CT2 – 186 MW in Llano County

## New Generation Approved for Commercial Operations

No projects have been approved for commercial operations during March 2014.

The total installed wind capacity is now reported as 11,065 MW by the resource owners through the registration process. Capacity by North, South and West is 833 MW, 2,775 MW, and 7,456 MW respectively.  Eight-hundred fifty MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |
| --- | --- |
| Currently tracking 230 generation interconnection or change requests |  |
| As of March 31, 2014 | Total |
| Security Screening Study | 22 |
| SSS Completed | 28 |
| Full Interconnect Study | 107 |
| FIS Completed | 10 |
| Suspended Studies | 0 |
| Capacity of Suspended Study Projects | 0 |
| Cancelled Projects | 1 |
| Interconnect Agreement Completed | 63 |
| Capacity under Interconnection Agreements | 18,671 |
| Capacity for Grid, MW | 58,148 |
| Wind Capacity, MW | 26,726 |
| Capacity of Cancelled Projects | 280 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 1,893 | - | 8,395 |
| Gas-CombinedCycle |  |  | 7,628 | - | 18,826 |
| Total Gas | 5,690 | 12,010 | 9,521 | - | 27,221 |
| Nuclear | - | - | - | - | - |
| Coal | - | 30 | 240 | - | 270 |
| Wind | 5,538 | 12,476 | 8,712 | - | 26,726 |
| Solar | 1,375 | 1,764 | 198 | - | 3,337 |
| Biomass | - | - | - | - | - |
| Storage | - | 594 | - | - | 594 |
| Petroleum Coke | - | - | - | - | - |
| Grand Total | 12,603 | 26,874 | 18,671 | - | 58,148 |

Cumulative Installed MW Capacity of Interconnection Requests by Zone

## Projects with Interconnection Agreements

| Generation Interconnection Agreements as of March 31, 2014 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | County | COD | Fuel | MW For Grid | Change from Last Report | Sufficient Financial Security Received by TSP |
| 11INR0013 | Goldthwaite Wind Energy | Mills | 4/2014 | WIND | 149 |  | Yes |
| 13INR0048 | Spinning Spur Wind Two | Oldham | 6/2014 | WIND | 161 |  | Yes |
| 13INR0021 | Ferguson Replacement Project | Llano | 7/2014 | GAS | 570 |  | Yes |
| 14INR0012a | Miami Wind 1 Project | Gray | 7/2014 | WIND | 289 |  | Yes |
| 14INR0015 | Deer Park Energy Center | Harris | 7/2014 | GAS | 190 |  | Yes |
| 14INR0030a_2 | Panhandle Wind | Carson | 7/2014 | WIND | 218 |  | Yes |
| 10INR0020a | Panda Temple Power | Bell | 8/2014 | GAS | 717 |  | Yes |
| 10INR0021 | Panda Sherman Power | Grayson | 8/2014 | GAS | 720 |  | Yes |
| 11INR0050 | Moore Wind 1 | Crosby | 8/2014 | WIND | 149 |  | No |
| 13INR0040 | Rentech Project | Harris | 8/2014 | GAS | 15 |  | Yes |
| 14INR0024 | OCI Alamo 4 | Kinney | 8/2014 | SOLAR | 38 |  | Yes |
| 14INR0059 | Forney Power Plant Upgrade | Kaufman | 8/2014 | GAS | 34 |  | No |
| 13INR0059a | Hereford Wind | Castro | 9/2014 | WIND | 200 |  | Yes |
| 11INR0094 | White Camp Solar | Kent | 10/2014 | SOLAR | 100 | PRJ COD | No |
| 12INR0034a | Stephens Ranch Wind Energy Phase 1 | Borden | 10/2014 | WIND | 201 |  | Yes |
| 13INR0010a | Mariah Wind | Parmer | 10/2014 | WIND | 232 |  | No |
| 12INR0059 | Barilla Solar | Pecos | 11/2014 | SOLAR | 30 |  | Yes |
| 06INR0022c | Baffin (Penascal Wind Farm 3) | Kenedy | 12/2014 | WIND | 202 |  | Yes |
| 11INR0079a | South Clay Windfarm | Clay | 12/2014 | WIND | 200 |  | No |
| 13INR0005 | Conway Windfarm | Carson | 12/2014 | WIND | 600 |  | Yes |
| 13INR0052 | Los Vientos III | Starr | 12/2014 | WIND | 200 |  | Yes |
| 13INR0057 | Windthorst 2 | Archer | 12/2014 | WIND | 65 |  | No |
| 14INR0023 | Longhorn Energy Center | Briscoe | 12/2014 | WIND | 361 |  | Yes |
| 14INR0032a | Route66 Wind | Randall | 12/2014 | WIND | 150 |  | Yes |
| 14INR0049_2 | Keechi Wind 138 kV Joplin | Jack | 12/2014 | WIND | 102 |  | Yes |
| 14INR0053 | Spinning Spur Wind Three | Oldham | 12/2014 | WIND | 194 |  | Yes |
| 09INR0051 | Mesquite Creek | Borden | 1/2015 | WIND | 249 |  | Yes |
| 12INR0068 | Sendero Wind Energy Project | Jim Hogg | 2/2015 | WIND | 78 |  | Yes |
| 12INR0070 | Green Pastures | Knox | 2/2015 | WIND | 300 |  | Yes |
| 12INR0034b | Stephens Ranch Wind Energy Phase b | Borden | 4/2015 | WIND | 177 |  | No |
| 13INR0059b | Jumbo Road Wind | Castro | 4/2015 | WIND | 300 | SFS | No |
| 14INR0038 | PHR Peakers | Galveston | 4/2015 | GAS | 390 |  | No |
| 14INR0047 | Wake Wind Energy | Floyd and Crosby | 4/2015 | WIND | 299 | New | Yes |
| 13INR0020a | CPV Rattlesnake Den Ph 1 | Glasscock | 5/2015 | WIND | 201 |  | Yes |
| 13INR0050 | Logans Gap Wind I | Comanche | 5/2015 | WIND | 200 |  | No |
| 11INR0057 | Cameron County Wind | Cameron | 6/2015 | WIND | 165 |  | Yes |
| 14INR0039 | Goldsmith Peaking Facility | Ector | 6/2015 | GAS | 408 |  | No |
| 14INR0025a | South Plains Wind I | Floyd | 7/2015 | WIND | 200 |  | No |
| 08INR0018 | Gunsight Mountain | Howard | 8/2015 | WIND | 120 |  | No |
| 10INR0020b | Panda Temple Power II | Bell | 8/2015 | GAS | 717 | Project Name | Yes |
| 11INR0062 | Patriot (Petronilla) Wind | Nueces | 8/2015 | WIND | 178 |  | Yes |
| 14INR0012b | Miami Wind 1 Project | Gray | 8/2015 | WIND | 111 |  | No |
| 13INR0049 | Friendswood Energy Generation | Harris | 9/2015 | GAS | 316 |  | No |
| 11INR0054 | Midway Farms Wind | San Patricio | 10/2015 | WIND | 161 |  | Yes |
| 14INR0030b | Panhandle Wind 2 (Phase 2) | Carson | 11/2015 | WIND | 182 |  | Yes |
| 13INR0010b | Mariah Wind | Parmer | 12/2015 | WIND | 200 |  | No |
| 13INR0031 | Mustang Solar Project | Travis | 12/2015 | SOLAR | 30 |  | No |
| 14INR0025b | South Plains II | Floyd | 12/2015 | WIND | 300 |  | No |
| 14INR0072 | Briscoe Wind Farm | Briscoe | 12/2015 | WIND | 300 |  | Yes |
| 13INR0020b | CPV Rattlesnake Den Ph 2 | Glasscock | 5/2016 | WIND | 150 |  | No |
| 13INR0028 | Antelope Station | Hale | 6/2016 | GAS | 359 | SFS | Yes |
| 16INR0010 | FGE Texas 1 | Mitchell | 6/2016 | GAS | 799 |  | No |
| 15INR0032 | Antelope Station CT1 | Hale | 7/2016 | GAS | 197 |  | No |
| 15INR0033 | Antelope Station CT2 | Hale | 7/2016 | GAS | 197 |  | No |
| 06INR0006 | Cobisa-Greenville | Hunt | 12/2016 | GAS | 1792 |  | No |
| 12INR0029 | Comanche Run Wind | Swisher | 12/2016 | WIND | 500 |  | No |
| 13INR0010c | Mariah Wind | Parmer | 12/2016 | WIND | 168 |  | No |
| 12INR0018 | Pampa Wind Project | Gray | 3/2017 | WIND | 500 |  | No |
| 10INR0022 | Pondera King Power Project | Harris | 6/2017 | GAS | 1629 |  | No |
| 16INR0003 | Freeport LNG PreTreatment Facility | Brazoria | 6/2017 | GAS | 11 |  | No |
| 13INR0023 | Texas Clean Energy Project | Ector | 6/2018 | COAL | 240 |  | No |

## Projects Undergoing Full Interconnection Studies with Confidentiality Waived

| INR | Site Name | County | COD | Fuel | MW for Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- |

## Generation Projects Undergoing Full Interconnection Studies

| Interconnection Database Reference Number |  | County |  | Fuel |  | Capacity to Grid (MW) |  | Commercial Operation Date (as specified by the resource developer) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 14INR0076 |  | Galveston |  | Gas |  | 5 |  | 6/2014 |
| 14INR0069 |  | Milam |  | Coal |  | 30 |  | 8/2014 |
| 14INR0077 |  | Smith |  | Gas |  | 10 |  | 8/2014 |
| 14INR0013 |  | Cameron |  | Wind |  | 103 |  | 10/2014 |
| 13INR0036 |  | Hidalgo |  | Wind |  | 200 |  | 10/2014 |
| 14INR0066 |  | Lamar |  | Gas |  | 130 |  | 11/2014 |
| 10INR0085 |  | Ector |  | Solar |  | 57 |  | 12/2014 |
| 14INR0009 |  | Kent |  | Wind |  | 248 |  | 12/2014 |
| 14INR0043 |  | Sterling |  | Solar |  | 40 |  | 12/2014 |
| Interconnection Database Reference Number |  | County |  | Fuel |  | Capacity to Grid (MW) |  | Commercial Operation Date (as specified by the resource developer) |
| 15INR0074 |  | Deaf Smith/Randall/Castro |  | Wind |  | 156 |  | 12/2014 |
| 14INR0057b |  | Erath |  | Wind |  | 48 |  | 12/2014 |
| 13INR0010d |  | Parmer |  | Wind |  | 200 |  | 12/2014 |
| 14INR0048_2 |  | Wilbarger |  | Wind |  | 250 |  | 12/2014 |
| 14INR0045a |  | Webb |  | Wind |  | 502 |  | 12/2014 |
| 14INR0057a |  | Erath |  | Wind |  | 48 |  | 12/2014 |
| 14INR0048_1 |  | Wilbarger |  | Wind |  | 114 |  | 12/2014 |
| 14INR0056 |  | Mills |  | Wind |  | 101 |  | 12/2014 |
| 12INR0045 |  | Kleberg |  | Wind |  | 135 |  | 12/2014 |
| 14INR0049_1 |  | Jack |  | Wind |  | 102 |  | 12/2014 |
| 14INR0014 |  | Val Verde |  | Solar |  | 100 |  | 1/2015 |
| 15INR0069 |  | Pecos |  | Solar |  | 110 |  | 3/2015 |
| 15INR0070_1 |  | Pecos |  | Solar |  | 110 |  | 3/2015 |
| 14INR0050 |  | Uvalde |  | Solar |  | 40 |  | 3/2015 |
| 15INR0070_2 |  | Pecos |  | Solar |  | 110 |  | 3/2015 |
| 15INR0036 |  | Uvalde |  | Solar |  | 105 |  | 3/2015 |
| 14INR0020 |  | Floyd & Motley |  | Wind |  | 150 |  | 3/2015 |
| 10INR0009 |  | Castro |  | Wind |  | 300 |  | 3/2015 |
| 15INR0055 |  | Austin |  | Gas |  | 142 |  | 5/2015 |
| 15INR0054 |  | Reeves |  | Gas |  | 123 |  | 5/2015 |
| 15INR0053 |  | Winkler |  | Gas |  | 123 |  | 5/2015 |
| 15INR0021 |  | Starr |  | Wind |  | 200 |  | 5/2015 |
| 14INR0041a |  | Willacy |  | Wind |  | 115 |  | 6/2015 |
| 14INR0074 |  | Williamson |  | Gas |  | 92 |  | 6/2015 |
| 13INR0026 |  | Oldham |  | Wind |  | 201 |  | 6/2015 |
| 15INR0027 |  | Hidalgo |  | Gas |  | 79 |  | 6/2015 |
| 15INR0028 |  | Freestone |  | Gas |  | 160 |  | 6/2015 |
| 14INR0040 |  | Hidalgo |  | Gas |  | 225 |  | 6/2015 |
| 15INR0023 |  | Wharton |  | Gas |  | 700 |  | 6/2015 |
| 13INR0054 |  | Bee |  | Gas |  | 25 |  | 7/2015 |
| 12INR0055 |  | Baylor |  | Wind |  | 40 |  | 7/2015 |
| 11INR0082a |  | Val Verde |  | Wind |  | 50 |  | 8/2015 |
| 14INR0026 |  | Presidio |  | Solar |  | 30 |  | 9/2015 |
| 13INR0025 |  | Randall |  | Wind |  | 150 |  | 9/2015 |
| 14INR0062 |  | Gray |  | Wind |  | 200 |  | 9/2015 |
| 15INR0068 |  | Sterling |  | Solar |  | 20 |  | 10/2015 |
| 13INR0055 |  | Zapata |  | Wind |  | 250 |  | 10/2015 |
| 11INR0082b |  | Val Verde |  | Wind |  | 150 |  | 11/2015 |
| 14INR0030a_1 |  | Carson |  | Wind |  | 322 |  | 11/2015 |
| 15INR0034 |  | San Patricio |  | Wind |  | 201 |  | 12/2015 |
| Interconnection Database Reference Number | County |  | Fuel |  | Capacity to Grid (MW) |  | Commercial Operation Date (as specified by the resource developer) |  |
| 15INR0035 | Kenedy |  | Wind |  | 200 |  | 12/2015 |  |
| 14INR0041b | Willacy |  | Wind |  | 115 |  | 12/2015 |  |
| 11INR0065 | Nueces |  | Wind |  | 350 |  | 12/2015 |  |
| 08INR0019a | Gray |  | Wind |  | 250 |  | 12/2015 |  |
| 12INR0060 | Schleicher |  | Wind |  | 58 |  | 12/2015 |  |
| 14INR0044 | Reeves |  | Solar |  | 100 |  | 12/2015 |  |
| 15INR0042 | Hood |  | Gas |  | 460 |  | 12/2015 |  |
| 15INR0051 | Castro |  | Wind |  | 200 |  | 12/2015 |  |
| 14INR0060 | Haskell |  | Wind |  | 400 |  | 12/2015 |  |
| 15INR0073 | Armstrong/Carson |  | Wind |  | 170 |  | 12/2015 |  |
| 13INR0032 | Andrews |  | Solar |  | 30 |  | 12/2015 |  |
| 12INR0002a | Briscoe |  | Wind |  | 200 |  | 12/2015 |  |
| 13INR0010e | Parmer |  | Wind |  | 200 |  | 12/2015 |  |
| 13INR0038 | Swisher |  | Wind |  | 300 |  | 12/2015 |  |
| 15INR0049 | Zapata / Webb |  | Wind |  | 250 |  | 12/2015 |  |
| 14INR0045b | Webb |  | Wind |  | 251 |  | 12/2015 |  |
| 11INR0093 | San Patricio |  | Wind |  | 41 |  | 12/2015 |  |
| 14INR0033 | Armstrong |  | Wind |  | 500 |  | 12/2015 |  |
| 14INR0018 | Nolan |  | Solar |  | 20 |  | 12/2015 |  |
| 15INR0044 | Webb and Duval |  | Solar |  | 200 |  | 12/2015 |  |
| 13INR0045 | Castro |  | Wind |  | 288 |  | 12/2015 |  |
| 15INR0059 | Pecos / Crane |  | Solar |  | 102 |  | 12/2015 |  |
| 15INR0037 | Starr |  | Wind |  | 200 |  | 12/2015 |  |
| 14INR0028 | Live Oak |  | Wind |  | 300 |  | 4/2016 |  |
| 16INR0036 | Nolan |  | Gas |  | 280 |  | 4/2016 |  |
| 16INR0009 | Calhoun |  | Gas |  | 510 |  | 4/2016 |  |
| 13INR0056 | Scurry |  | Wind |  | 366 |  | 5/2016 |  |
| 16INR0008 | Grimes |  | Gas |  | 687 |  | 5/2016 |  |
| 16INR0023 | Dawson |  | Solar |  | 100 |  | 5/2016 |  |
| 15INR0057 | Wharton |  | Gas |  | 142 |  | 6/2016 |  |
| 16INR0004 | Cameron |  | Gas |  | 730 |  | 6/2016 |  |
| 16INR0007 | Hidalgo |  | Gas |  | 95 |  | 6/2016 |  |
| 16INR0006 | Angelina |  | Gas |  | 785 |  | 6/2016 |  |
| 16INR0005 | Cameron |  | Gas |  | 871 |  | 6/2016 |  |
| 14INR0027 | Guadalupe |  | Gas |  | 471 |  | 6/2016 |  |
| 16INR0038 | McLennan |  | Gas |  | 471 |  | 6/2016 |  |
| 17INR0004 | Hale |  | Gas |  | 202 |  | 6/2016 |  |
| 16INR0041 | Pecos |  | Solar |  | 100.00 |  | 6/2016 |  |
| 16INR0040 | Reeves |  | Solar |  | 50.00 |  | 6/2016 |  |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 16INR0039 | Reeves | Solar | 100.00 | 6/2016 |
| 14INR0011 | Swisher | Storage | 270.00 | 7/2016 |
| 08INR0019b | Gray | Wind | 250.00 | 7/2016 |
| 16INR0013 | Nacogdoches | Gas | 215.00 | 7/2016 |
| 16INR0024 | Hidalgo | Wind | 200.00 | 10/2016 |
| 16INR0037 | Floyd | Wind | 400.00 | 10/2016 |
| 16INR0019 | Coke/Sterling | Solar | 100.00 | 12/2016 |
| 16INR0018 | Upton | Solar | 40.00 | 12/2016 |
| 16INR0017 | Culberson | Solar | 70.00 | 12/2016 |
| 08INR0019c | Gray | Wind | 250.00 | 12/2016 |
| 13INR0006 | Gray | Wind | 750.00 | 12/2016 |
| 16INR0029 | Hill & Limestone | Wind | 100.00 | 12/2016 |
| 16INR0030 | Young & Jack | Wind | 201.00 | 12/2016 |
| 16INR0028 | Jack | Wind | 100.00 | 12/2016 |
| 16INR0027 | Grayson & Fannin | Wind | 100.00 | 12/2016 |
| 16INR0026 | Erath, Somervell & Bosque | Wind | 100.00 | 12/2016 |
| 16INR0025 | Sterling | Solar | 30.00 | 12/2016 |
| 13INR0010f | Parmer | Wind | 200.00 | 12/2016 |
| 12INR0002b | Briscoe | Wind | 200.00 | 12/2016 |
| 16INR0011a | Cameron | Wind | 18.00 | 12/2016 |
| 16INR0031 | Zapata & Starr | Wind | 100.00 | 12/2016 |
| 15INR0013 | Anderson | Storage | 324.00 | 5/2017 |
| 17INR0003 | Jackson | Gas | 965.00 | 6/2017 |
| 17INR0002 | Henderson | Gas | 489.00 | 6/2017 |
| 17INR0005 | Starr | Wind | 200.00 | 6/2017 |
| 17INR0009 | Hood | Gas | 1042.00 | 7/2017 |
| 17INR0007 | Wharton | Gas | 1141.00 | 7/2017 |
| 16INR0011b | Cameron | Wind | 132.00 | 12/2017 |
| 11INR0040 | Freestone | Gas | 640.00 | 3/2018 |

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- CenterPoint Energy submitted the Houston Region Import Capacity project. This is a Tier 1 project that is estimated to cost between $297 to $532 million. ERCOT has issued the independent review report on Feb. 20th.  ERCOT will present the project at the Board of Directors in April 2014 for their endorsement.

- Garland Power & Light (GP&L) and Cross Texas Transmission (CTT) have jointly submitted a Houston Import project. This is a Tier 1 project that is estimated to cost between $195 to $317 million. ERCOT has issued the independent review report on Feb. 20th.  ERCOT will present the project at the Board of Directors in April 2014 for their endorsement.

- Lone Star Transmission has submitted a Houston Import project. This is a Tier 1 project that is estimated to cost between $417 to $675 million. ERCOT will present the project at the Board of Directors in April 2014 for their endorsement.

- Oncor has submitted the West Texas Area project. This is a Tier 2 project that is estimated to cost $45 million. This project is currently under ERCOT independent review.

- CenterPoint has submitted the Katy Area project. This is a Tier 2 project that is estimated to cost $20.4 million. This project is currently under ERCOT independent review.

- LCRA TSC has submitted the Leander – Round Rock 138 kV project. This is a Tier 1 project that is estimated to cost $50.9 million. This project is currently under ERCOT independent review.

- Sharyland has submitted the Brady Area project. This is a Tier 2 project that is estimated to cost $18 million. This project has received several RPG comments and it is under study mode.

- Sharyland has submitted the West Texas projects for Stanton Area. This is a Tier 3 project that is estimated to cost $40.4 million. This project has received several RPG comments and it is under study mode.

- AEPSC has submitted the Brady Area Improvements project. This is a Tier 2 project that is estimated to cost $26.5 million. This project has received several RPG comments and it is under study mode.

- TNMP has submitted the Wink-Pecos Line 69E Rebuild project. This is a Tier 3 project that is estimated to cost $15 million. This project has received several RPG comments and it is under study mode.

- Denton Municipal Electric (DME), Oncor, TMPA, Brazos Electric Cooperative (BEC) and GP&L have jointly the Denton Area West 345/138 kV source project. This is a Tier 2 project that is estimated to cost $ 44.8 million. This project has been submitted for RPG comments.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Mar 4, 2014	Posted 14DSA and 14DSB updated cases

  - Mar 5, 2014	Posted MODTPIT

  - Mar 18, 2014	Posted Updated Contingency Definitions

  - Apr 1, 2014	Start 15DSA case build process

  - Jun 20, 2014	Projected completion of 15DSA and MODTPIT

  - Jul 11, 2014	Projected posting of Contingency Definitions

# Other Notable Activities

- The System Protection Working Group 2014 Current Year (CY) base creation process has been completed.  The Future Year (FY) base case creation will begin with ERCOT distributing pass 0 on April 11, 2014.

- ERCOT has entered into an agreement with Powertech Labs to perform a small signal stability study.

- ERCOT has begun the 2014 Regional Transmission Plan (RTP).

- Work has begun on the 2014 Long-Term System Assessment (LTSA).  Through a series of three workshops stakeholders developed ten scenarios for 2024 to 2029.  At the March 25 RPG meeting ERCOT presented the input assumptions for the “Current Trends” scenario along with assumptions for several of the other scenarios.  ERCOT is continuing to develop the input assumptions and will seek feedback at upcoming RPG meetings to ensure they appropriately correspond to the stakeholder developed scenario descriptions.