## Sheet1
TX SET Meeting Notes / Action Items
March 19-20 2014
Agenda Item: | Decision / Resolution | Action Items :
February 2014 Meeting Notes | No changes were made | Have ERCOT post the notes to the February 2014 meeting page
Change Control Call--Wed 10:15 3/19/14 | CC2013 –800 Muni-Coop guidelines are different than the IOU guidelines for meter removal--Texas SET agreed to send a recommendation to RMS to approve this change control.
TDTWG Test Script Discussion | • TDTWG leadership and the ERCOT SME for that group briefly discussed the NAESB v2.2 and v2.3 upgrade requirements as they relate to the Texas Market. • TDTWG will request that Texas SET develop connectivity test scripts for the upgrade, based on the list of test scenarios provided, if and when the market votes to upgrade to the newer version. | Future Action items to develop connectivity test scripts
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
Flight 0214 Testing Update | o 13 New CRs (includes 9 Additional DUNS) are testing o Existing CRs: 15 CRs are testing with Sharyland, and 2 CRs are testing for a bank change o 5 Existing CRs testing late entry (Emergency service provider change) o 4153 tasks are scheduled o Currently 87.66% complete o Flight scheduled to conclude 04/01/14 (contingency period until 04/16/14)
ERCOT Market Testing | Review of current market testing process-- o Script Sub-team update—Texas SET reviewed the changes made to some of the existing scripts and the notes from the Sub Team meeting |  Script Development Assignments • ERCOT Optional Scripts: Ad Hoc Usage Request and CSA • ONCOR SCR33 revisions, SCR33A & B, Add or modify a script to add a Switch Hold and send the subsequent 814_20 as well as a tampering invoice. Also develop new MVI, DNP and RNP scripts for both the IOU and MOU-EC TDSP’s • Reliant STK23 review and make changes (stacking, date change, unexecutable
 The group agreed that the script timelines should be reduced further since the flights currently have a contingency built in at the end of the flight for those trading partners that fall behind sending an initiating transaction. The group also agreed that the script timelines should run no longer than 15 days maximum.  The group agreed that there are instances where a previously tested CR making certain types of changes should only have to complete the connectivity test in order to obtain their certification.
The group will develop two different scripts for instances where there are differences between an IOU and a MOU-EC TDSP's processes.  The Texas SET MOU-EC TDSPs will provide input for testing scenarios that have unique processes in place for their requirements.  The group will continue the discussions at the next meeting in April.
Issues
134-Non-CSA CR sends a MVO with the indicator for bypass CSA at ERCOT. Non-CSA CR is not always the owner of the CSA, causing the ESI ID to become de-energized without CSA CRs knowledge | • NPRR583--Withdrawal status--PRS Approved the withdrawal
| Change to RMG Update | o Reliant, Green Mountain and ERCOT to draft Retail Market Guide (RMG) language to enforce the appropriate use of the bypass code in the market.
RMGRR updates | No other RMGRRs to discuss
Other Business | None discussed
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Next Meeting |  Apr 16th RM 168 MET CENTER  Apr 17th RM 168 Met CENTER
Attendees RM168
Diana Rehfeldt TNMP | Kaci Jacobs TXU Energy | Kathy Scott Centerpoint
Kathryn Thurman ERCOT | Carolyn Reed Centerpoint | Paula Shadle Nueces EC
Isabelle Durhan Centerpoint | Jim Lee Direct Energy | Rosana Adams Nueces EC
Ed Echols ONCOR | Kyle Patrick Reliant | Vikram Gupta ERCOT
Becky Taylor Centerpoint | Monica Jones Reliant | Seth Connel ERCOT
WebEx:
Gricelca Calzada AEP | Barbara Goubeau EC Infosystems | Joe Lindsay Systrends
Mary Sithihou Stream Energy | Jenny Evenson Sharyland U | Mike Woolsey ONCOR
Amy Rafferty ESG | Stephen Wilson Sharyland U | Roger Tenebown ISTA NA
John Schatz TXU Energy | Jacqueline Stevenson EC Infosystems | Suzanne Clark Liberty Power
Paul Yockey ERCOT | Connie Hermes Nueces CR | Teresa Rodriquez Stream Energy
Sandra Tindall ERCOT | Dave Louder Sharyland U