|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report April 2014 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 234 active generation interconnection requests totaling over 60,400 MW. This includes over 26,900 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $226 Million. - Transmission Projects endorsed in 2014 total $620 Million. - All projects (in engineering, routing, licensing and construction) total approximately $4.4 Billion. - Transmission Projects energized in 2014 total about $123.3 Million. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Approved for Synchronization	1

1.3	New Generation Approved for Commercial Operations	1

1.4	Summary of Generation Interconnection Requests	1

1.5	Projects with Interconnection Agreements	5

1.6	Projects Undergoing Full Interconnection Studies with Confidentiality Waived	6

1.7	Generation Projects Undergoing Full Interconnection Studies	7

1.8	Wind Generation Capacity Installed by Year	11

2.	Regional Planning Group Project Reviews	11

3.	Asynchronous Tie Interconnection	12

4.	Planning Model Activities	13

5.	Other Notable Activities	13

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

14INR0066 – Lamar Power Projects Upgrade – 130 MW in Lamar County

## New Generation Approved for Synchronization

- None reported for April 2014.

## New Generation Approved for Commercial Operations

None reported for April 2014.

The total installed wind capacity is now reported as 11,059 MW by the resource owners through the registration process. Capacity by North, South and West is 605 MW, 2,024 MW, and 8,431 MW respectively.  Eight-hundred fifty MW is able to switch between the West and South zones and is currently shown in the West Zone.

## Summary of Generation Interconnection Requests

| Summary of Generation Interconnection Requests |  |
| --- | --- |
| Currently tracking 234 generation interconnection or change requests |  |
| April 2014 | Total |
| Security Screening Study (SSS) Underway | 12 |
| SSS Completed | 40 |
| Full Interconnect Study (FIS) Underway | 110 |
| FIS Completed | 8 |
| Interconnection Agreement Executed, FIS Pending | 22 |
| Interconnection Agreement Executed | 42 |
| Total Interconnection Requests | 234 |
| Cancelled Studies (since last month) | 3 |
| Total Capacity Under Study, MW | 60,407 |
| Total Wind Capacity, MW | 26,984 |
| Interconnection Agreement Executed, MW | 18,720 |
| Cancelled Capacity, MW (since last month) | 454 |

| Fuel Type | Screening Study (MW)* | Screening Study w/ Public Letter (MW)** | Full Study (MW)* | Full Study w/ Public Letter (MW)** | IA Executed (MW)** | IA Executed FIS Pending (MW)** | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 0 | 0 | 1,140 | 753 |  |
| Gas-CCGT |  |  | 12,679 | 0 | 4,337 | 3,421 |  |
| Total Gas | 6,772 | 0 | 12,679 | 0 | 5,477 | 4,174 | 29,102 |
| Nuclear | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Coal | 0 | 0 | 30 | 0 | 0 | 240 | 270 |
| Wind | 5,809 | 0 | 12,544 | 0 | 4,896 | 3,734 | 26,983 |
| Solar | 1,333 | 0 | 1,926 | 0 | 198 | 0 | 3,457 |
| Biomass | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Storage | 0 | 0 | 594 | 0 | 0 | 0 | 594 |
| Petroleum Coke | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total | 13,914 | 0 | 27,773 | 0 | 10,571 | 8,148 | 60,406 |
| * Confidential Project Interconnection Requests |  |  |  |  |  |  |  |
| ** Public Project Interconnection Requests; i.e., waiver of confidential information received by ERCOT (“Public Letter”), or Interconnection Agreement executed |  |  |  |  |  |  |  |

Interconnection Requests by Zone (MW)

## Projects with Interconnection Agreements

| Generation Interconnection Agreements as of April 2014 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GINR Number | Project Name | County | Projected COD | Fuel | MW For Grid | Changes From Last Report | Sufficient Financial Security |
| 11INR0013 | Goldthwaite Wind Energy | Mills | 5/2014 | WIND | 149 | Projected COD | Yes |
| 13INR0048 | Spinning Spur Wind Two | Oldham | 6/2014 | WIND | 161 |  | Yes |
| 13INR0021 | Ferguson Replacement Project | Llano | 7/2014 | GAS | 570 |  | Yes |
| 14INR0012a | Miami Wind 1 Project | Gray | 7/2014 | WIND | 289 |  | Yes |
| 14INR0015 | Deer Park Energy Center | Harris | 7/2014 | GAS | 190 |  | Yes |
| 14INR0030a_2 | Panhandle Wind 1 | Carson | 7/2014 | WIND | 218 | Project Name | Yes |
| 10INR0020a | Panda Temple 1 | Bell | 8/2014 | GAS | 717 | Project Name | Yes |
| 10INR0021 | Panda Sherman Power | Grayson | 8/2014 | GAS | 720 |  | Yes |
| 13INR0040 | Rentech Project | Harris | 8/2014 | GAS | 15 |  | Yes |
| 14INR0024 | OCI Alamo 4 | Kinney | 8/2014 | SOLAR | 38 |  | Yes |
| 14INR0059 | Forney Upgrade | Kaufman | 8/2014 | GAS | 34 | Project Name | No |
| 11INR0094 | White Camp Solar | Kent | 10/2014 | SOLAR | 100 |  | No |
| 12INR0034a | Stephens Ranch Wind Energy Phase 1 | Borden | 10/2014 | WIND | 201 |  | Yes |
| 13INR0010a | Mariah Wind | Parmer | 10/2014 | WIND | 232 |  | No |
| 12INR0059 | Barilla Solar | Pecos | 11/2014 | SOLAR | 30 |  | Yes |
| 14INR0030b | Panhandle Wind 2 | Carson | 11/2014 | WIND | 182 | Project Name | Yes |
| 14INR0066 | Lamar Power Projects Upgrade | Lamar | 11/2014 | GAS | 130 | NEW | No |
| 13INR0005 | Grandview 1to3 (Conway Windfarm) | Carson | 12/2014 | WIND | 600 | Project Name | Yes |
| 13INR0052 | Los Vientos III | Starr | 12/2014 | WIND | 200 |  | Yes |
| 13INR0057 | Windthorst 2 | Archer | 12/2014 | WIND | 65 | SFS | Yes |
| 13INR0059a | Hereford Wind | Castro | 12/2014 | WIND | 200 | Projected COD | Yes |
| 14INR0023 | Longhorn Energy Center | Briscoe | 12/2014 | WIND | 361 |  | Yes |
| 14INR0032a | Route66 Wind | Randall | 12/2014 | WIND | 150 |  | Yes |
| 14INR0049_2 | Keechi Wind 138 kV Joplin | Jack | 12/2014 | WIND | 102 |  | Yes |
| 09INR0051 | Mesquite Creek | Borden | 1/2015 | WIND | 249 |  | Yes |
| 12INR0068 | Sendero Wind Energy Project | Jim Hogg | 2/2015 | WIND | 78 |  | Yes |
| 12INR0070 | Green Pastures | Knox | 2/2015 | WIND | 300 |  | Yes |
| 12INR0034b | Stephens Ranch Wind Energy Phase b | Borden | 4/2015 | WIND | 177 | SFS | Yes |
| 13INR0059b | Jumbo Road Wind | Castro | 4/2015 | WIND | 300 | SFS | Yes |
| 14INR0038 | PHR Peakers | Galveston | 4/2015 | GAS | 390 |  | No |
| 14INR0047 | Wake Wind | Floyd | 4/2015 | WIND | 299 | Project Name | Yes |
| 13INR0020a | CPV Rattlesnake Den Ph 1 | Glasscock | 5/2015 | WIND | 211 | MW For Grid | Yes |
| 13INR0050 | Logans Gap Wind I | Comanche | 5/2015 | WIND | 200 |  | No |
| 11INR0050 | Moore Wind 1 | Crosby | 6/2015 | WIND | 149 | Projected COD | No |
| 11INR0057 | Cameron County Wind | Cameron | 6/2015 | WIND | 165 |  | Yes |
| 11INR0079a | South Clay Windfarm | Clay | 6/2015 | WIND | 200 | Projected COD | No |
| 14INR0039 | Goldsmith Peaking Facility | Ector | 6/2015 | GAS | 408 |  | No |
| 14INR0053 | Spinning Spur Wind Three | Oldham | 6/2015 | WIND | 194 | Projected COD | Yes |
| 14INR0025a | South Plains Wind I | Floyd | 7/2015 | WIND | 200 |  | No |
| 08INR0018 | Gunsight Mountain | Howard | 8/2015 | WIND | 120 |  | No |
| 10INR0020b | Panda Temple Power II | Bell | 8/2015 | GAS | 717 |  | Yes |
| 11INR0062 | Patriot (Petronilla) Wind | Nueces | 8/2015 | WIND | 178 |  | Yes |
| 14INR0012b | Miami Wind 1 Project | Gray | 8/2015 | WIND | 111 |  | No |
| 13INR0049 | Friendswood Energy | Harris | 9/2015 | GAS | 316 | Project Name | No |
| 11INR0054 | Midway Farms Wind | San Patricio | 10/2015 | WIND | 161 |  | Yes |
| 06INR0022c | Baffin (Penascal Wind Farm 3) | Kenedy | 12/2015 | WIND | 202 |  | Yes |
| 13INR0010b | Mariah Wind | Parmer | 12/2015 | WIND | 200 |  | No |
| 13INR0031 | Mustang Solar Project | Travis | 12/2015 | SOLAR | 30 |  | No |
| 14INR0025b | South Plains II | Floyd | 12/2015 | WIND | 300 |  | No |
| 14INR0072 | Briscoe Wind Farm | Briscoe | 12/2015 | WIND | 201 | MW For Grid | Yes |
| 13INR0020b | CPV Rattlesnake Den Ph 2 | Glasscock | 5/2016 | WIND | 158 | MW For Grid | No |
| 13INR0028 | Antelope Station | Hale | 6/2016 | GAS | 359 |  | Yes |
| 15INR0032 | Antelope Station CT1 | Hale | 7/2016 | GAS | 197 |  | No |
| 15INR0033 | Antelope Station CT2 | Hale | 7/2016 | GAS | 197 |  | No |
| 16INR0010 | FGE Texas 1 | Mitchell | 7/2016 | GAS | 799 | Projected COD | No |
| 06INR0006 | Cobisa-Greenville | Hunt | 12/2016 | GAS | 1792 |  | No |
| 12INR0029 | Comanche Run Wind | Swisher | 12/2016 | WIND | 500 |  | No |
| 13INR0010c | Mariah Wind | Parmer | 12/2016 | WIND | 168 |  | No |
| 12INR0018 | Pampa Wind | Gray | 3/2017 | WIND | 500 | Project Name | No |
| 16INR0003 | Freeport LNG PreTreatment Facility | Brazoria | 6/2017 | GAS | 11 |  | No |
| 10INR0022 | Pondera King Power Project | Harris | 7/2017 | GAS | 1629 | Projected COD | No |
| 13INR0023 | Texas Clean Energy Project | Ector | 3/2019 | COAL | 240 | Projected COD | No |

## Projects Undergoing Full Interconnection Studies with Confidentiality Waived

| INR | Site Name | County | COD | Fuel | MW for Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- |

## Generation Projects Undergoing Full Interconnection Studies

| Full Interconnection Study Table |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| GINR Number | County | Fuel | Capacity to Grid (MW) | Projected COD (specified by developer) | Public Letter |
| 14INR0076 | Galveston | Gas | 5 | 6/2014 |  |
| 13INR0048 | Oldham | Wind | 161 | 6/2014 |  |
| 14INR0077 | Smith | Gas | 10 | 8/2014 |  |
| 14INR0069 | Milam | Coal | 30 | 8/2014 |  |
| 14INR0013 | Cameron | Wind | 103 | 10/2014 |  |
| 13INR0010a | Parmer | Wind | 232 | 10/2014 |  |
| 13INR0036 | Hidalgo | Wind | 200 | 10/2014 |  |
| 14INR0043 | Sterling | Solar | 40 | 12/2014 |  |
| 14INR0009 | Kent | Wind | 248 | 12/2014 |  |
| 10INR0085 | Ector | Solar | 57 | 12/2014 |  |
| 14INR0032a | Randall | Wind | 150 | 12/2014 |  |
| 14INR0023 | Briscoe | Wind | 361 | 12/2014 |  |
| 15INR0074 | Deaf Smith | Wind | 156 | 12/2014 |  |
| 14INR0057b | Erath | Wind | 48 | 12/2014 |  |
| 14INR0057a | Erath | Wind | 48 | 12/2014 |  |
| 14INR0056 | Mills | Wind | 101 | 12/2014 |  |
| 14INR0048_1 | Wilbarger | Wind | 114 | 12/2014 |  |
| 13INR0010d | Parmer | Wind | 200 | 12/2014 |  |
| 14INR0049_2 | Jack | Wind | 102 | 12/2014 |  |
| 13INR0059a | Castro | Wind | 200 | 12/2014 |  |
| 12INR0070 | Knox | Wind | 300 | 2/2015 |  |
| 15INR0070_2 | Pecos | Solar | 110 | 3/2015 |  |
| 15INR0070_1 | Pecos | Solar | 110 | 3/2015 |  |
| 15INR0036 | Uvalde | Solar | 105 | 3/2015 |  |
| 14INR0020 | Floyd | Wind | 150 | 3/2015 |  |
| 10INR0009 | Castro | Wind | 300 | 3/2015 |  |
| 13INR0059b | Castro | Wind | 300 | 4/2015 |  |
| 15INR0055 | Austin | Gas | 142 | 5/2015 |  |
| 15INR0054 | Reeves | Gas | 123 | 5/2015 |  |
| 13INR0056 | Scurry | Wind | 366 | 5/2015 |  |
| 15INR0021 | Starr | Wind | 200 | 5/2015 |  |
| 15INR0069 | Pecos | Solar | 110 | 6/2015 |  |
| 15INR0028 | Freestone | Gas | 160 | 6/2015 |  |
| 14INR0074 | Williamson | Gas | 92 | 6/2015 |  |
| 14INR0050 | Uvalde | Solar | 40 | 6/2015 |  |
| 14INR0041a | Willacy | Wind | 115 | 6/2015 |  |
| 13INR0026 | Oldham | Wind | 201 | 6/2015 |  |
| 14INR0053 | Oldham | Wind | 194 | 6/2015 |  |
| 11INR0057 | Cameron | Wind | 165 | 6/2015 |  |
| 14INR0040 | Hidalgo | Gas | 225 | 6/2015 |  |
| 15INR0023 | Wharton | Gas | 700 | 6/2015 |  |
| 12INR0055 | Baylor | Wind | 40 | 7/2015 |  |
| 13INR0054 | Bee | Gas | 25 | 7/2015 |  |
| 14INR0025a | Floyd | Wind | 200 | 7/2015 |  |
| 11INR0082a | Val Verde | Wind | 50 | 8/2015 |  |
| 14INR0026 | Presidio | Solar | 30 | 9/2015 |  |
| 13INR0025 | Randall | Wind | 150 | 9/2015 |  |
| 15INR0050 | Deaf Smith | Wind | 203 | 9/2015 |  |
| 14INR0062 | Gray | Wind | 200 | 9/2015 |  |
| 15INR0068 | Sterling | Solar | 20 | 10/2015 |  |
| 13INR0055 | Zapata | Wind | 250 | 10/2015 |  |
| 14INR0048_2 | Wilbarger | Wind | 250 | 10/2015 |  |
| 14INR0030c | Carson | Wind | 248 | 11/2015 |  |
| 11INR0082b | Val Verde | Wind | 150 | 11/2015 |  |
| 15INR0042 | Hood | Gas | 460 | 12/2015 |  |
| 15INR0035 | Kenedy | Wind | 200 | 12/2015 |  |
| 15INR0034 | San Patricio | Wind | 201 | 12/2015 |  |
| 14INR0044 | Reeves | Solar | 100 | 12/2015 |  |
| 14INR0041b | Willacy | Wind | 115 | 12/2015 |  |
| 14INR0014 | Val Verde | Solar | 100 | 12/2015 |  |
| 08INR0019a | Gray | Wind | 250 | 12/2015 |  |
| 12INR0060 | Schleicher | Wind | 58 | 12/2015 |  |
| 11INR0065 | Nueces | Wind | 350 | 12/2015 |  |
| 14INR0025b | Floyd | Wind | 300 | 12/2015 |  |
| 15INR0051 | Castro | Wind | 200 | 12/2015 |  |
| 12INR0045 | Kleberg | Wind | 135 | 12/2015 |  |
| 14INR0060 | Haskell | Wind | 400 | 12/2015 |  |
| 15INR0073 | Armstrong | Wind | 201 | 12/2015 |  |
| 15INR0059 | Pecos | Solar | 102 | 12/2015 |  |
| 15INR0049 | Zapata | Wind | 250 | 12/2015 |  |
| 15INR0044 | Webb | Solar | 200 | 12/2015 |  |
| 15INR0037 | Starr | Wind | 200 | 12/2015 |  |
| 14INR0045b | Webb | Wind | 251 | 12/2015 |  |
| 14INR0045a | Webb | Wind | 502 | 12/2015 |  |
| 14INR0033 | Armstrong | Wind | 500 | 12/2015 |  |
| 13INR0045 | Castro | Wind | 288 | 12/2015 |  |
| 13INR0038 | Swisher | Wind | 300 | 12/2015 |  |
| 13INR0032 | Andrews | Solar | 30 | 12/2015 |  |
| 13INR0010e | Parmer | Wind | 200 | 12/2015 |  |
| 12INR0002a | Briscoe | Wind | 200 | 12/2015 |  |
| 11INR0093 | San Patricio | Wind | 41 | 12/2015 |  |
| 14INR0018 | Nolan | Solar | 20 | 12/2015 |  |
| 14INR0072 | Briscoe | Wind | 201 | 12/2015 |  |
| 13INR0010b | Parmer | Wind | 200 | 12/2015 |  |
| 15INR0053 | Winkler | Gas | 123 | 3/2016 |  |
| 16INR0036 | Nolan | Gas | 280 | 4/2016 |  |
| 14INR0028 | Live Oak | Wind | 300 | 4/2016 |  |
| 16INR0009 | Calhoun | Gas | 510 | 4/2016 |  |
| 16INR0023 | Dawson | Solar | 100 | 5/2016 |  |
| 17INR0004 | Hale | Gas | 202 | 6/2016 |  |
| 16INR0038 | McLennan | Gas | 471 | 6/2016 |  |
| 16INR0007 | Hidalgo | Gas | 95 | 6/2016 |  |
| 16INR0006 | Angelina | Gas | 785 | 6/2016 |  |
| 16INR0005 | Cameron | Gas | 871 | 6/2016 |  |
| 15INR0057 | Wharton | Gas | 142 | 6/2016 |  |
| 15INR0027 | Hidalgo | Gas | 79 | 6/2016 |  |
| 14INR0027 | Guadalupe | Gas | 471 | 6/2016 |  |
| 13INR0028 | Hale | Gas | 359 | 6/2016 |  |
| 16INR0048 | Pecos | Solar | 150 | 6/2016 |  |
| 16INR0041 | Pecos | Solar | 100 | 6/2016 |  |
| 16INR0040 | Reeves | Solar | 50 | 6/2016 |  |
| 16INR0039 | Reeves | Solar | 100 | 6/2016 |  |
| 16INR0013 | Nacogdoches | Gas | 215 | 7/2016 |  |
| 14INR0011 | Swisher | Storage | 270 | 7/2016 |  |
| 08INR0019b | Gray | Wind | 250 | 7/2016 |  |
| 15INR0033 | Hale | Gas | 197 | 7/2016 |  |
| 15INR0032 | Hale | Gas | 197 | 7/2016 |  |
| 16INR0037 | Floyd | Wind | 400 | 10/2016 |  |
| 16INR0024 | Hidalgo | Wind | 200 | 10/2016 |  |
| 15INR0046 | Reeves | Solar | 42 | 10/2016 |  |
| 16INR0004 | Cameron | Gas | 730 | 11/2016 |  |
| 16INR0019 | Coke | Solar | 100 | 12/2016 |  |
| 16INR0018 | Upton | Solar | 40 | 12/2016 |  |
| 16INR0017 | Culberson | Solar | 70 | 12/2016 |  |
| 13INR0006 | Gray | Wind | 750 | 12/2016 |  |
| 08INR0019c | Gray | Wind | 250 | 12/2016 |  |
| 06INR0006 | Hunt | Gas | 1792 | 12/2016 | 5/2005 |
| 16INR0031 | Starr | Wind | 100 | 12/2016 |  |
| 16INR0030 | Young | Wind | 211 | 12/2016 |  |
| 16INR0029 | Hill | Wind | 100 | 12/2016 |  |
| 16INR0028 | Jack | Wind | 100 | 12/2016 |  |
| 16INR0027 | Grayson | Wind | 100 | 12/2016 |  |
| 16INR0026 | Erath | Wind | 100 | 12/2016 |  |
| 16INR0011a | Cameron | Wind | 18 | 12/2016 |  |
| 13INR0010f | Parmer | Wind | 200 | 12/2016 |  |
| 12INR0002b | Briscoe | Wind | 200 | 12/2016 |  |
| 13INR0010c | Parmer | Wind | 168 | 12/2016 |  |
| 16INR0008 | Grimes | Gas | 687 | 1/2017 |  |
| 12INR0018 | Gray | Wind | 500 | 3/2017 |  |
| 15INR0013 | Anderson | Storage | 324 | 5/2017 |  |
| 17INR0010 | Mitchell | Gas | 799 | 6/2017 |  |
| 17INR0002 | Henderson | Gas | 489 | 6/2017 |  |
| 17INR0003 | Jackson | Gas | 965 | 6/2017 |  |
| 17INR0005 | Starr | Wind | 200 | 6/2017 |  |
| 10INR0022 | Harris | Gas | 1629 | 7/2017 |  |
| 17INR0009 | Hood | Gas | 1042 | 7/2017 |  |
| 17INR0007 | Wharton | Gas | 1141 | 7/2017 |  |
| 16INR0011b | Cameron | Wind | 132 | 12/2017 |  |
| 11INR0040 | Freestone | Gas | 640 | 3/2018 |  |
| 13INR0023 | Ector | Coal | 240 | 3/2019 |  |

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- ERCOT has completed the independent review of the Houston Import Capacity project. This is a Tier 1 project that is estimated to cost $590 million. This project was endorsed by the Board of Directors on April 8, 2014.

- Oncor has submitted the West Texas Area project. This is a Tier 2 project that is estimated to cost $45 million. This project is currently under ERCOT independent review.

- CenterPoint has submitted the Katy Area project. This is a Tier 2 project that is estimated to cost $20.4 million. This project is currently under ERCOT independent review.

- LCRA TSC has submitted the Leander – Round Rock 138 kV project. This is a Tier 1 project that is estimated to cost $50.9 million. This project is currently under ERCOT independent review.

- Sharyland has submitted the Brady Area project. This is a Tier 2 project that is estimated to cost $18 million. This project has received several RPG comments and it is under study mode.

- Sharyland has submitted the West Texas projects for Stanton Area. This is a Tier 3 project that is estimated to cost $40.4 million. This project has received several RPG comments and it is under study mode.

- AEPSC has submitted the Brady Area Improvements project. This is a Tier 2 project that is estimated to cost $26.5 million. This project has received several RPG comments and it is under study mode.

- TNMP has submitted the Wink-Pecos Line 69E Rebuild project. This is a Tier 3 project that is estimated to cost $15 million. This project has completed the RPG review and EROT will send the RPG acceptance letter.

- CenterPoint has submitted the Dow-Velasco 345/138 kV autotransformer project. This is a Tier 3 project that is estimated to cost $15 million. This project has completed the RPG review and EROT will send the RPG acceptance letter.

- Denton Municipal Electric (DME), Oncor, TMPA, Brazos Electric Cooperative (BEC) and GP&L have jointly submitted the Denton Area West 345/138 kV source project. This is a Tier 2 project that is estimated to cost $44.8 million. This project is currently under ERCOT independent review.

- DUKE-American Transmission Company has submitted the Phoenix project. This is a Tier 2 project that is estimated to cost $39 million. This project has been submitted for RPG comments.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Apr 1, 2014	Started 15DSA case build process

  - Jun 20, 2014	Projected completion of 15DSA and MODTPIT

  - Jul 11, 2014	Projected posting of Contingency Definitions

# Other Notable Activities

- The System Protection Working Group 2014 Future Year (FY) base case creation is in progress with a projected completion date of July 3, 2014.

- ERCOT has entered into an agreement with Powertech Labs to perform a small signal stability study.

- ERCOT has begun the 2014 Regional Transmission Plan (RTP). The initial cases and list of overloads were posted for stakeholder review on April 29th 2014.

- ERCOT has begun the preparation for the 2014 Long Term System Assessment (LTSA). ERCOT is currently working on developing the generation expansion plan for the current trends scenario using UPLAN.