## Slide 1
Settlement System Upgrade
Project Status
Adam Martinez
Business Planning and Integration PMO
Commercial Operations Subcommittee (COPS)
May 14, 2014

## Slide 2: Settlement System Upgrade (PR10052_01) Current Status
Activities to Date
Project has completed code delivery of the system framework, as well as 5 of 10 functional code sets
Remaining 5 code sets to be completed by mid-August
Data Agg
  Integration testing of Data Agg components scheduled to start by end of June and complete by end of July
  Go-live scheduled with R4 Release (July 27)
Remainder of Settlement & Billing functionality
  Integration testing of S&B components scheduled to start by end of October and complete by early December.
  Go-live scheduled with R6 (December 7)
Will include 2 NPRRs:
  580 Congestion Revenue Rights Credit Calc & payments
  467 Balancing Account Resettlement Due to DAM Resettlement
Existing Challenges
Managing project resources and schedule against competing efforts, such as ORDC (and possible follow-on projects)

## Slide 3: Settlement System Upgrade (PR10052_01) Development Schedule
Area | Functional Component | Status of Development
Framework Components | Framework components for logic processing, error handling, common modules, etc. | Complete
Data Agg Componenents | Generation Aggregation IDR & NIDR Estimation NOIE Aggregation | Complete
 | Weather Responsiveness Determinant | In Progress
Settlement & Billing Components | AIEC Calculations | Complete
 | RTM Settlements | Complete
 | Settlement Statements & Invoices | Complete
 | DAM Settlements | Complete
 | RUC Settlements | In Progress
 | CRR Settlements | In Progress
 | Eligibility for RUC & DAM Make Whole | In Progress
 | Data Loading Usage Data Loading | In Progress