## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
May 15, 2014

## Slide 2: 2013 Project Update – Agenda
  Project Portfolio Update p. 3-7
    Recent/Upcoming Project Highlights
    Recent Internal Labor Results
    Planning Next Set of Project Bundles
    2014 Release Targets
    2015 Release Targets
    2014 Project Spending Update
  Appendix
    Project Portfolio Gantt Chart p. 8-17
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent/Upcoming Project Highlights
2014 Release 2 Go-Lives (April 2014) Complete
  NPRR564 – Thirty-Minute Emergency Response Service (ERS) and Other ERS Services
  NPRR570 – Reduce RTM Settlement Timeline to Operating Day Plus Five
  CREZ Voltage Control and Coordination – Phase 1
  Various IT infrastructure projects
2014 Release 3 Go-Lives (June 2014) In-Flight
  2014 Market System Enhancements (June 1 release date)
    NPRR568 – Real-Time Reserve Price Adder Based on Operating Reserve Demand Curve
    NPRR555 – Load Resource Participation in Security-Constrained Economic Dispatch
    NPRR532 – Performance Measurement and Verification and Telemetry Requirements for Load Resources Providing Non-Spin
  Taylor Control Room Upgrade
Remaining 2014 Releases
  ERCOT has made progress in identifying market-facing projects that will be launched after the current in-flight projects are implemented and stabilized
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Recent ERCOT Internal Labor Results
2014 Market System Enhancements (NPRR568, NPRR555, NPRR532) – on this project in March alone:
76 people in 18 departments worked 4,709 hours (equivalent to 27 full-time staff)
What is driving this increase in labor?

## Slide 5: Planning Next Set of Project Bundles
CMM Start = July 2014
  NPRR439 - Updating a Counter-Party’s Available Credit Limit for Current Day DAM
  NPRR559 - Revisions to MCE Calculation
  SCR778 - Credit Exposure Calculations for NOIE Options Linked to RTM PTP Obligations
CRR Start = May 2014
  SCR779 - Increase to the CRR Auction Trans. Limit
  Start = July 2014
  NPRR484 Phase 1b - Revisions to CRR Credit Calcs
  SCR777 - Bilateral CRR Interface Enhancement
CDR / EIS / MIS Start = June 2014
  NPRR495 - Changes to A/S Capacity Monitor
  NPRR500 - Posting of Generation that is Off but Avail.
  NPRR543 - Message for Confirmed E-Tags
  Start = August 2014
  NPRR256 – Add Non-Comp. Lang. to QSE Perf. Stds.
  SCR775 - Posting Results of Real-Time Data in a Display Format
EMS Start = August 2014
  NPRR524 - Resource Limits in Providing A/S
  NPRR573 - Alignment of PRC Calculation
  NPRR581 - Add FRRS as a Subset of Regulation Svc
  Start = October 2014
  NPRR272 - Definition and Participation of QSGRs
MMS Start = August 2014
  ORDC Phase 2
    Identified gray-boxes plus potential new NPRR(s)
  OBD for Shadow Price Caps
  NPRR556 - Resource Adequacy During Transmission Equipment Outage
  NPRR589 - A/S Offers in the SASM
Registration Start = August 2014
  NPRR519 - Collateral Exemption for ERS-Only QSEs
  SCR771 - Independent Master QSE for Split Gen.
S&B Start = October 2014
  NPRR487 - QSGR Dispatch Adjustment
  NPRR580 - Rolling CRR Balancing Account Fund
Market input on this plan is greatly appreciated!

## Slide 6: 2014 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
None
January
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR425(b) – GREDP, EIS portions
SCR756(b) – Remaining portions of SCR
(a), (b), etc. indicates multiple phases
None
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
ü
ü
ü
Release Approach | Release 1 2/3 – 2/7 | Release 2 4/14 – 4/18 | Release 3 6/9 – 6/13 | Release 4 7/28 – 8/1 | Release 5 9/22–9/26 | Release 6 12/8–12/12 | 2014 TBD
On-Cycle | NPRR240 NPRR425(b) NOGRR105 NPRR509 | NPRR564 NPRR570 | NPRR532 | NPRR491 NPRR571 SCR769 SCR772 SCR774 SCR756(b) | NPRR485 NPRR500 NPRR543 NPRR586 NPRR559 | NPRR272 NPRR327 NPRR487 NPRR495 NPRR500 NPRR519 NPRR524 NPRR543 NPRR556 NPRR559 NPRR589 SCR771 | NPRR327 NPRR484(1b) NPRR527 NPRR556 NPRR573 NPRR580 NPRR581 OBD(Shadow Price Caps) SCR774 SCR775 SCR777
Off-Cycle | NPRR416 NPRR575 |  | NPRR555 NPRR568 |  |  | SCR777 | SCR778
Counts Total = 27 | 6 | 2 | 3 | 6 | 2 | 7 | 1
June 1st
None
Retail: 2/22-2/23
Retail: 7/26-7/27
ü

## Slide 7: 2015 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
None
Release targets are subject to change
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portion of NPRR
None
None
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
Release Approach | Release 1 February | Release 2 April | Release 3 June | Release 4 July | Release 5 September | Release 6 December | 2015 TBD
On-Cycle | NPRR439 NPRR484(1b) NPRR487 NPRR519 NPRR524 NPRR527 NPRR573 NPRR581 SCR771 SCR778 SCR779 | NPRR210 NPRR256 NPRR493 SCR775 | NPRR272 NPRR419 NPRR455 NPRR467 NPRR484(2) NPRR495 NPRR553 NOGRR084 |  | NPRR580 |  | NPRR515
Off-Cycle |  |  |  |  |  |  | 
Counts Total = 25 | 11 | 4 | 8 | 0 | 1 | 0 | 1
None
None
None

## Slide 8: 2014 Cash Flow Projection – Approved Projects
2014 project budget = $25M

## Slide 9: Business Integration Update – Appendix
  Appendix
    5/5/2014 Project Gantt
      In-flight items sorted by Project End Date
      “On Hold” projects listed separately
      “Not Started” items sorted by Project Start Date

## Slide 10
Project Portfolio Status – as of 5/5/2014

## Slide 11
Project Portfolio Status – as of 5/5/2014

## Slide 12
Project Portfolio Status – as of 5/5/2014

## Slide 13
Project Portfolio Status – as of 5/5/2014

## Slide 14
Project Portfolio Status – as of 4/7/2014

## Slide 15
Project Portfolio Status – as of 5/5/2014

## Slide 16
Project Portfolio Status – as of 5/5/2014

## Slide 17
Project Portfolio Status – as of 5/5/2014

## Slide 18
Project Portfolio Status – as of 5/5/2014