## Slide 1: SMT Joint TDSPs AMWG 17 Change Requests Update To RMS
May 6, 2014
Bob Frazier
Senior Director of Electric Technology
CenterPoint Energy
(representing SMT JDOA)

## Slide 2: AMWG CR 2013 017 - Q2 2014 Implementation
    Backfill of Historical Usage Data for Existing Customers
  Ability for the REP of Record to request a one-time retrieval of historical interval usage data (up to 12 months) for some or all of its existing customer base (backfill requests) - Available
    Subscription for New Customer Historical Usage
    Ability for the REP of Record to subscribe to automatically receive a one-time report of historical interval usage data (up to 12 months) for customers/ESIIDs that are newly served by them (MVI & Switches) – Acceptance testing
Short term solutions –
  in production and available for use soon
  Long term permanent solution -scheduled for future release
  Documentation and forms will be available at: http://www.ercot.com/committees/board/tac/rms/amwg/

## Slide 3: 5 More Change Requests Coming Soon
5 AMWG Change Requests Targeted for Delivery in Q2 or early Q3 2014
  AMWG CR 2013 002, AMWG CR 2013 005, AMWG CR 2013 006, AMWG CR 2013 007, and AMWG CR 2013 009
  These 5 AMWG Change Requests are reports already existing from IBM to Joint TDSPs but restricted by contract.
  These require minimal effort to repurpose to the Texas Market and will have zero cost
  Minor contract revisions are required between SMT vendor and TDSPs to publish these slightly modified existing reports externally These Revisions will be Complete in Q2 2014

## Slide 4: Status of Additional AMWG Change Requests
3 AMWG Change Requests in Delivery for Q4 2014 with Third Party
  AMWG CR 2013 012, AMWG CR 2013 013, and AMWG CR 2013 014
  The SMT Usability Study Conducted in 2013 Identified Enhancements Approved for Implementation to SMT
  These 3 AMWG Change Requests are covered by the approved enhancements from the Usability Study and are targeted to be delivered with Third Party functionality
7 AMWG Change Requests in Process for SMT Joint TDSP Estimation Process Step
  AMWG CR 2013 001, AMWG CR 2013 003, AMWG CR 2013 004, AMWG CR 2013 008, AMWG CR 2013 010, AMWG CR 2013 011, and AMWG CR 2013 015
  These 7 AMWG Change Requests are all New Requirements requiring New Development and will be in Process of Estimation with the SMT Joint TDSPs as Resources are Available in 2014 for development in 2015

## Slide 5: Time Requirements For SMT Joint TDSPs Response on Q3 2013 AMWG Change Requests
AMWG Change Requests to SMT Joint TDSPs in Q3 2013
Challenges in Response
  SMT Resources Full Capacity Consumed by Work and Planning of the Following two Items
  SMT Third Party Release Project Design to Understand Resource Capacity for Work in 2014 – Completed February 2014
  SMT 2014 Infrastructure Refresh Project Planning to Understand Resource Capacity for Work in 2014 – Completed April 2014
Previous Belief Confirmed - All Available SMT Resources will be Utilized to Full Capacity Through Most of 2014
Henceforth – Conduct Monthly Updates to AMWG Webex
Propose Periodic (Quarterly?) Updates to RMS

## Slide 6
AMWG Change Request | AMWG CR Document | Status | Estimated Delivery Date | Estimated Cost
AMWG CR 2013 001 – Report for AMWG Data Monitoring – Data Completeness Measurements |  | JDOA Estimation | 2015 | In Process
AMWG CR 2013 002 – Reports for AMWG Data Monitoring – Data Timeliness Measurements |  | Development | Q2 2014 | Existing Report Zero Dollar
AMWG CR 2013 003 – Reports for AMWG Data Monitoring – Measurement of Percentage of Actual Meter Reads |  | JDOA Estimation | 2015 | In Process
AMWG CR 2013 004 – Reports for AMWG Data Monitoring – Measurement of Estimates |  | JDOA Estimation | 2015 | In Process
AMWG CR 2013 005 – Reports for AMWG Data Monitoring – Number of SMT Help Desk Tickets Monthly by Ticket Type |  | Development | Q2 2014 | Existing Report Zero Dollar
AMWG CR 2013 006 – Reports for AMWG Data Monitoring – Availability of SMT API |  | Development | Q2 2014 | Existing Report Zero Dollar
AMWG CR 2013 007 – Reports for AMWG Data Monitoring – Availability of SMT FTPS |  | Development | Q2 2014 | Existing Report Zero Dollar
AMWG CR 2013 008 – Reports for AMWG Data Monitoring – Average Time to Deliver HAN Messages |  | JDOA Estimation | 2015 | In Process
AMWG CR 2013 009 – Reports for AMWG Data Monitoring – Number of Accounts by Type |  | Development | Q2 2014 | Existing Report Zero Dollar
AMWG CR 2013 010 – Reports for AMWG Data Monitoring – Number of Reports Requested by GUI (Portal) and Number of FTPS Accesses |  | JDOA Estimation | 2015 | In Process
AMWG / RMS Change Requests

## Slide 7
AMWG Change Request | AMWG CR Document | Status | Estimated Delivery Date | Estimated Cost
AMWG CR 2013 011 – Average Time from HAN Provision Request to Meter Ready Status |  | JDOA Estimation | 2015 | In Process
AMWG CR 2013 012 – Bypass redundant screen for Users with only one meter when accessing HAN device information |  | Development | Q4 2014 | Already in Third-Party
AMWG CR 2013 013 – Timeout on SMT takes user to “incorrect login” screen |  | Development | Q4 2014 | Already in Third-Party
AMWG CR 2013 014 – Allow SMT user to toggle between 15-Minute Reads and Daily Reads without having to reset the date range |  | Development | Q4 2014 | Already in Third-Party
AMWG CR 2013 015 – Expand Daily Usage Graph to show 35 days of daily usage on the SMT GUI |  | JDOA Estimation | 2015 | In Process
AMWG CR 2013 016 – Capability for RORs to grant access to vendors on their behalf to the ROR’s customers via API (energy usage, HAN messaging , and HAN provisioning) and FTPS files |  | Development | Q2 2014 | Ready for AMWG Design Review
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Backfill of Historical Usage Data for Existing Customers- “Interim”) | See Below CR 2013 017 Permanent | Complete (12-18-2013) | Q4 2013 | Completed
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Subscription for New Customer Historical Usage – “Interim”) | See Below CR 2013 017 Permanent | Development | Q2 2014 | Ready for AMWG Design Review
AMWG CR 2013 017 – REP API for Energy Usage on SMT – Permanent Solution to Replace Interim Solution |  | JDOA Estimation | 2015 | In Process
AMWG / RMS Change Requests (Cont.)

## Slide 8: 3rd Party Functionality
    Third Party
  Contract to Receive Customer’s Energy Data
  Contract to Provision / Deprovision Customer HAN Device
  Contract to Provide Customer with HAN Services
    Ratings and Reviews
  Will allow customers to rate and update that rating of the third party they contract with and will allow a customer to see previous ratings by other customers before they enter into a contract with a third party
    Usability Enhancements
  Dashboard (authenticated landing page), navigation, cleaner simplified flow, and content improvements

## Slide 9: 3rd Party Project Timeline
Third-Party Security Independent Review
1st Quarter
2nd Quarter
2013
3rd Quarter
4th Quarter
2014
Third-Party Customer Experience Review
SMT Customer Experience Changes
Third-Party Technical Design & Development
Security Validation
Additional Solution Requirements
Third-Party Solution SIT and UAT Testing
Third-Party Implementation
Third-Party Design AMIT / SMT DO
Third-Party Volunteer Testers Technical Integration Sessions and Testing
Security Validation
SMT Design Assessment
Legend
Completed
In Process
Future Task
1st Quarter
2nd Quarter
3rd Quarter
4th Quarter
Third-Party Market Integration / Instruction Webinars