## Sheet1
TX SET Meeting Notes / Action Items
May 19-20 2014
Agenda Item: | Decision / Resolution | Action Items :
April 2014 Meeting Notes | There were no changes to the notes | Have changes posted to the Texas SET meeting page key documents for April
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
Issues
134-Non-CSA CR sends a MVO with the indicator for bypass CSA at ERCOT. Non-CSA CR is not always the owner of the CSA, causing the ESI ID to become de-energized without CSA CRs knowledge | April Texas SET meeting will be used to create the RMGRR and submit to RMS for a vote at the July RMS meeting. | Reliant to complete the RMGRR draft
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Flight 0614 Testing Update | • The ERCOT flight administrator presented the Flight 0614 update o Summary  3 New CRs (includes 2 Additional DUNS testing as new CRs) will be testing  Existing CRs: 7 CRs are testing for new territories, and 1 CR is testing for a bank change  1796 tasks are scheduled o Schedule  Flight signup began 05/07/14  Flight deadline was 05/14/14  Connectivity kick-off conference call is scheduled for 05/20/14  Flight kick-off conference call is scheduled for 05/30/14  Day 1 transactions begin 06/02/14  Flight 0614 is scheduled to concluded 07/15/14 (contingency period until 08/05/14)
Other Business
Centerpoint (CNP) SAC04 Change Project 42359 | CNP discussed their request for a new SAC04 code needed for Surcharge Energy Efficiency from Project No. 42359. A change control will be submitted and discussed during a June Texas SET meeting change control call. | Centerpoint to submit the change control
RMS assignment: Review and present options for the Proposed REP Certification Matrix Upload to the Retail Market Testing Website | • The group reviewed the matrix, making modifications where needed • The group agreed that the matrix should continue to be provided on an ad hoc basis in the short term o ERCOT noted that the ad hoc request must come from one of the Authorized Representatives listed at ERCOT for the requesting REP o Future discussions related to long term placement will occur when the group begins discussing Testing Website enhancement
ERCOT Market Testing | • Market Test Scripts developed by the sub-team were reviewed and changes made where needed o Assignments were made to various attendees to update and / or develop scripts o The group reviewed the need to add the TDSP’s move-in Priority Codes to the scripts or where to find these lists in the Market. It was noted that there is no specific location listed in a market document for move-in Priority Codes • The TTPT was reviewed to determine which sections should be updated and how these changes will affect future flight tests | • ERCOT to investigate how the elimination of parts of the test scripts would affect the ability to upload these scripts to the testing website • ERCOT to review the CON scripts to determine what changes can be made to simplify these scripts • Reliant to update the test script workbook from the changes noted at the meeting • Nueces to review the modified test script to determine which of the IOU scripts will work for the MOUs and also identify any separate scripts needed for the MOU territories • Texas SET will discuss options for the best location of each TDSP’s move-in Priority codes at a future meeting
Next Meeting | · June 18th & 19th ERCOT Met Center Rm 168
Attendees RM168
Diana Rehfeldt TNMP | Becky Taylor CNP | Carolyn Reed CNP
Kathryn Thurman ERCOT | Kathy Scott CNP | Jim Lee Direct Energy
Ed Echols ONCOR | Paul Yockey ERCOT | Kyle Patrick Reliant
Gricelda Calzada AEP | Paula Shadle NEC
Kaci Jacobs TXU | Rosana Adams NEC
WebEx:
Amy Rafferty ESG | Sandra Tindall ERCOT
Roger Tenebown ISTA NA
Barbara Goubeaud EC Info Systems
Deb Belin ISTA NA
Seth Connel ERCOT
Suzanne Clark Liberty Power
Dave Louder NEC
Jim O'Brien