|  |  | System Planning |
| --- | --- | --- |
|  |  | Monthly Status Report May 2014 |
|  | Report Highlights |  |
|  | ERCOT is currently tracking 233 active generation interconnection requests totaling over 59,700 MW. This includes over 26,400 MW of wind generation. |  |
|  | ERCOT is currently reviewing proposed transmission improvements with a total cost of $224.5 Million. Transmission Projects endorsed in 2014 total $640.2 Million. All projects (in engineering, routing, licensing and construction) total approximately $4.4 Billion. Transmission Projects energized in 2014 total about $123.3 Million. |  |

Table of Contents

1.	Generation Interconnection	1

2.	Regional Planning Group Project Reviews	1

3.	Asynchronous Tie Interconnection	2

4.	Planning Model Activities	3

5.	Other Notable Activities	3

# 1.	Generation Interconnection

Generator interconnection information has been moved to the Generator Interconnection Status (GIS) Report to be published monthly starting in early June 2014 under the Grid Information / Resource Adequacy section of the ercot.com website.  Please  see the exact web link below.

http://www.ercot.com/gridinfo/resource/index

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

# Regional Planning Group Project Reviews

- Oncor has submitted the West Texas Area project. This is a Tier 2 project that is estimated to cost $45 million. This project is currently under ERCOT independent review.

- CenterPoint has submitted the Katy Area project. This is a Tier 2 project that is estimated to cost $20.4 million. This project has completed the ERCOT independent review. EROT will send the RPG acceptance letter.

- LCRA TSC has submitted the Leander – Round Rock 138 kV project. This is a Tier 1 project that is estimated to cost $50.9 million. ERCOT issued the independent review report on May 22, 2014.  ERCOT will present the project at the Board of Directors in June 2014 for their endorsement.

- Sharyland has submitted the Brady Area project. This is a Tier 2 project that is estimated to cost $18 million. This project has received several RPG comments and it is under study mode.

- Sharyland has submitted the West Texas projects for Stanton Area. This is a Tier 3 project that is estimated to cost $40.4 million. This project is currently under ERCOT independent review.

- AEPSC has submitted the Brady Area Improvements project. This is a Tier 2 project that is estimated to cost $26.5 million. This project has received several RPG comments and it is under study mode.

- Denton Municipal Electric (DME), Oncor, TMPA, Brazos Electric Cooperative (BEC) and GP&L have jointly submitted the Denton Area West 345/138 kV source project. This is a Tier 2 project that is estimated to cost $44.8 million. This project is currently under ERCOT independent review.

- Duke-American Transmission Company has submitted the Phoenix project. This is a Tier 2 project that is estimated to cost $39 million. This project has received several RPG comments and it is under study mode.

- CPS Energy has submitted the Howard Road - Somerset 138 kV upgrade project. This is a Tier 2 project that is estimated to cost $18.3  million. This project is currently under ERCOT independent review.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Apr 1, 2014	Started 15DSA case build process

  - Jun 20, 2014	Projected completion of 15DSA and MODTPIT

  - Jul 11, 2014	Projected posting of Contingency Definitions

- ERCOT has created a tracking sheet to help identify units that have met Planning Guides Section 6.9 since many Market Participants do not have access to the modeling data submitted by Interconnecting Entities.  The assumption has been made that those entities meeting section 6.9 (1) meet the requirements to be added to the planning models.  This is not true as section 6.9 (2) also has to be met.  ERCOT will begin next month displaying a table of interconnection requests that meet section 6.9 (1) but do not meet section 6.9 (2) and will not be added to the planning models.

# Other Notable Activities

- The System Protection Working Group 2014 Future Year (FY) base case creation is in progress with a projected completion date of July 3, 2014.

- ERCOT’s reliability analysis of the 2014 Regional Transmission Plan (RTP) is underway. The initial cases and list of overloads were updated and posted for stakeholder review on May 15th 2014.

- ERCOT has begun the 2014 Long Term System Assessment (LTSA). ERCOT presented the results for the generation expansion plan build-out for the Current Trends scenario at the May Regional Planning Group (RPG) meeting. ERCOT continues to gather input data and develop generation expansion plans for remaining scenarios.

- ERCOT is planning on conducting a West-North stability limit assessment.  This will be a joint study between ERCOT System Planning and Operations.

- ERCOT is planning on performing a review of the ERCOT responsive reserve requirements taking into account the new BAL-003 standard.