## PR010_03 UCs
Use Case | Description | Status | Notes | Priority
1 | Redirect PMVI Fees (new subtype) | Finalized | Implemented June 2012 w/TXSET 4.0 | Critical
13 | Create Usage and Billing Subtypes for LSE Data | Finalized | Implemented June 2012 w/TXSET 4.0 | Critical
18 | Creation of a single subtype for “Expedited Switch Rescission” | Finalized | Implemented June 2012 w/TXSET 4.0 | Critical
19 | New subtype(s) are needed for tampering-related issues (Switch hold four hour process) | Finalized | Implemented June 2012 w/TXSET 4.0 | Critical
29 | Catch-all subtype (Market Rule) | Finalized | Implemented June 2012 w/TXSET 4.0 | Critical
3 | Distinct Usage and Billing Subtypes (Missing and Dispute) | Finalized | (MTUB1 & MTUB2) | High
8 | Increase validations to prevent users from entering invalid information into pre-defined fields. | Finalized | MTUB2 | High
9 | Changes to Inadvertent Losing workflow | Finalized | (MTIAG1 & MTIAG2) | High
17 | Add “First Touched by TDSP” to DEVLSE | Finalized | DEVLSE | High
21 | Add Service History to DEVLSE | Finalized | DEVLSE | High
23 | Add the ability to retrieve and download attachments via the API | Finalized | API ATTCH | High
24 | Add Additional Subtypes to the Contact Type field in the MarkeTrak Contact List (Rolodex) table | Finalized | ADMIN1 | High
25 | Validate submitting CR as ROR during service period (Usage and Billing) | Finalized | (MTUB1 & MTUB2) | High
27 | Duplicate ESIID message contains hyperlink | Finalized | MTUB1 | High
33 | Automatic transition for no regaining Siebel status (IAG) | Finalized | MTIAG1 | High
34 | Change specific warning messages to error messages | Finalized | VALD1 | High
35 | Add DUNS to MarkeTrak generated emails with MP names | Finalized | EMAIL1 | High
36 | Add SMRD and MVI priority for Regaining Transaction | Finalized | SIEBEL | High
37 | Send an escalation email if an issue has been in a New state for 3 days | Finalized | EMAIL2 | High
46 | Change field label from “Transaction Submit Date” to “Date Transaction Submitted”. Change “Submit Date” to “Regain Date” field. Add help function to this field. | Finalized | SIEBEL | High
4 | New "Add User" functionality to Administrator feature | Finalized | ADMIN2 | Medium
15 | Description - The ability to return individual issue comments on GUI reports and background reports – date configurable | Finalized | BCKGRND1 | Medium
22 | Add 867_02 to Missing TXNS subtype | Finalized | MISSENRL | Medium
32 | Add 814_PC and 814_PD in the current drop down selections (Missing TXN) | Finalized | MISSENRL | Medium
26 | Review for add’l canned background reports | Finalized | BCKGRND1 | Medium
28 | Auto-close escalation message | Finalized | EMAIL3 | Medium
30 | Create the ability for API users to execute BR(s) via Query List calls | Finalized | API ATTCH | Medium
31 | Require 814_20 field for Premise Type/Service Address subtypes | Finalized | (PRMISE & SRVC ADD) | Medium
40 | Add Optional fields to the “997 Issues” sub-type that allow the REP to select the Trans Type or enter the ESI ID in question | Finalized | 997 | Medium
44 | Add to the background reports the ability to display in the result set a designation of CR or TDSP on Cancel with Approval submittal. | Finalized | BCKGRND1 | Medium
5 | Change the name on the Submit Tree for subtype “Missing TRXN” to “Enrollment Transactions.” | Finalized | MISSENRL | Medium
10 | Update Bulk Insert Templates - Remove columns and rows that are no longer deemed necessary and “script time stamp entry” to simplify the submission process. Check formatting of templates | ERCOT | ERCOT WILL UPDATE BULK INSERT TEMPLATES FOR PR010_03 ENHANCEMENTS
USE CASES BELOW THIS LINE NOT PART OF PR010_03
43 | Create a notification for the Switch Hold process so that when the TDU creates the MT, the MT tool would automatically send an email to the CSG team members. | Finalized | NOT PART OF PR010_03 | Medium | TAMMY WILL LOOK OVER MTTF ARCHIVED NOTES TO SEE WHO UCASE 43 CAME FROM AND IT MAY BE CONSIDERED FOR NEXT RELEASE
38 | Allow for multiple entries into Search Criteria fields such as ESIID and Issue ID | DEFERRED NOT PART OF SERENA FUNCIONALITY | DEFERRED NOT PART OF SERENA FUNCIONALITY |  | Need UseCase for PartB - Deferred - Serena Upgrade Possibility - Search multiple MT Issue IDs separated by commas post Serena

## MTUB1-MISSING
|  | Script ID | MTUB1 - USE CASEs 3, 25 & 27 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | Distinct Usage and Billing Subtype (Missing)
|  | Script Storyline | From start to finish create an entire Missing SubType Issue.
|  | Success Criteria | MarkeTrak is available and processing issues; ESI ID populated must be a valid ESI ID in existence within ERCOT Registration database; Issue is successfully created and able to be transitioned to a resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | Missing SubType is selected from the MarkeTrak Submit Tree | User enters all required information with a StartTime of '11.01.2013' and selects 'OK' to create issue. User will receive ESIID duplicate warning with the Issue ID in the form of a hyperlink. Submitter selects hyperlink and issue opens in new window. Submitter closes window. Error message is returned stating 'Submitting MP is not the ROR for the StartTime on the issue'. CR enters correct date of '01.01.2014'. CR selects 'Ok' | MT submitted for Monthly Usage Period(s) (867s) missing from the ERCOT Lode Star Database; This script includes testing validation for UseCase 25 and UseCase 27. Make sure dates match Siebel. | 1
Day 2
| Day 3 |  | CR | TDSP | MarkeTrak Issue is created and transitioned to 'Assignee (TDSP)' with "New Assignee" state. TDSP is Responsible Party | TDSP user selects 'Begin Working' with "In Progress (Assignee)" state. | Issue completed by TDSP with comments | 1
| Day 5 |  | TDSP | CR | MarkeTrak Issue transitioned back to CR (Submitter) with "Pending Complete" state and CR is Responsible Party. | CR reviews issue and selects 'Complete' and MT issue is in a "Complete" state | Issue should be completed under new SubType (D2D Usage and Billing - Missing) | 1
Day 6
Day 2
Day 3
Day 4

## MTUB2-DISPUTE
|  | Script ID | MTUB2 - USE CASEs 3, 8 & 25 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | Distinct Usage and Billing Subtype (Dispute)
|  | Script Storyline | From start to finish create an entire Dispute SubType Issue.
|  | Success Criteria | MarkeTrak is available and processing issues; ESI ID populated must be a valid ESI ID in existence within ERCOT Registration database; Issue is successfully created and able to be transitioned to a resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | Dispute SubType is selected from the MarkeTrak Submit Tree | User enters all required information with a StartTime of '11.01.2013' and selects 'OK' to create issue. Error message is returned stating 'Submitting MP is not the ROR for the StartTime on the issue'. CR enters correct date of '01.01.2014' and enters 'Invalid Date' in BGN field as well as special characters '%' and selects 'OK' to create issue. Defined Value 'Other' is selected from the Dispute category field and user is prompted for required comments. | MT submitted to dispute Monthly Usage Period (867 KWH) loaded in the ERCOT Lode Star Database or (810 Invoice). This script includes testing validation for UseCase 8 and UseCase 25. Make sure dates match Siebel. | 1
Day 2
| Day 3 |  | CR | TDSP | MarkeTrak Issue is created and transitioned to Assignee (TDSP) with "New Assignee" state. TDSP is Responsible Party | TDSP user selects 'Begin Working' with state of "In Progress (Assignee)". | Issue completed by TDSP with comments | 1
| Day 3 |  | CR | TDSP | MarkeTrak Issue is created and transitioned to Assignee (TDSP) with "New Assignee" state. TDSP is Responsible Party | TDSP user selects 'Begin Working' with state of "In Progress (Assignee)". | Issue completed by TDSP with comments | 1
| Day 5 |  | TDSP | CR | MarkeTrak Issue transitioned back to CR (Submitter) in "Pending Complete" state and CR as Responsible Party. | CR (Submitter) reviews issue and selects 'Complete' and MT issue is in a "Complete" state | Issue should be completed under new SubType (D2D Usage and Billing - Dispute) | 1
Day 6
Day 2
Day 3
Day 4

## MTIAG1
|  | Script ID | MTIAG1 - USE CASEs 9 & 33 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | Changes to Inadvertent Losing Workflow and combines use cases 9 & 33
|  | Script Storyline | Losing CR submits Inadvertent Losing issue. Gaining CR selects agree. Losing CR forwards to TDSP and workflow transitions back to Losing CR after no 'Complete' siebel status in 14 days
|  | Success Criteria | The 'Agree' transition functions as expected
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR1 (Losing CR) | CR2 (Gaining CR) | IAL SubType is selected from the MarkeTrak Submit Tree | User enters all required information and selects 'OK' to create issue |  | 1
Day 2
| Day 3 |  | CR1 (Losing CR) | CR2 (Gaining CR) | MarkeTrak Issue is created and transitioned to CR2 in the state of "New (Gaining CR)". CR2 is Responsible Party | CR2 user selects 'Begin Working' with "In Progress (Gaining CR)" state. | CR2 selects 'Agree' and the issue is transitioned to CR1 in state of "New (Losing CR)". Resume current workflow after this step. No further testing needed. | 1
| Day 6 |  | CR1 (Losing CR) | TDSP (New TDSP) | MarkeTrak Issue is transitioned to TDSP in the state of "New (TDSP)". TDSP is responsible … | TDSP selects 'Begin Working' with "In Progress (TDSP)" state. | TDSPs selects 'Provide BGN' and the issue is transitioned to state 'Regaining Transaction Submitted'. Issue pending Siebel status of Complete.
Day 2
| Day 6 |  | Siebel | CR1 (Losing CR) | BGN not 'Complete' after 14 days and issue is transitioned to CR1 "New (Losing CR submit)". CR1 is responsible … | CR1 selects 'Begin Working' | CR1 resubmits correct BGN and Siebel status updated to 'Complete' and issue transitions to 'Complete'
Day 4

## MTIAG2
|  | Script ID | MTIAG2 - USE CASE 9 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | Changes to Inadvertent Losing Workflow
|  | Script Storyline | Losing CR submits Inadvertent Losing issue. Gaining CR selects 'Return to Losing CR' and Losing CR doesn't have the ability to forward to the TDSP
|  | Success Criteria | Losing CR attempts to transition issue back to TDSP and receives error message.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR1 (Losing CR) | CR2 (Gaining CR) | IAL SubType is selected from the MarkeTrak Submit Tree | User enters all required information and selects 'OK' to create issue |  | 1
Day 2
| Day 3 |  | CR1 (Losing CR) | CR2 (Gaining CR) | MarkeTrak Issue is created and transitioned to CR2 in the state of "New (Gaining CR)". CR2 is Responsible Party | CR2 user selects 'Begin Working' with "In Progress (Gaining CR)" state. | CR2 selects 'Return to Losing CR' and enters comments. The issue is transitioned to CR1 in state of "New (Losing CR)". | 1
| Day 3 |  | CR2 (Gaining CR) | CR1 (Losing CR) | CR1 Selects 'Begin Working' and Issues transitions to "In Progress (Losing CR)" state | CR1 selects 'Send to TDSP' and receives an error message. CR1 selects 'Send to Gaining CR' and issue transtions to CR2 in state of "New (Gaining CR)" | If all parties agree, resume current workflow. No additional testing needed. | 1
Day 6
Day 2
Day 3
Day 4

## DEVLSE
|  | Script ID | DEVLSE1 - USE CASEs 17 & 21 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | Combing use cases (17 & 21) in this test script
|  | Script Storyline | CR submits DEV LSE StartTime change. ERCOT passes analysis and assigns to TDSP. TDSP selects 'Begin Working' and 'First Touched by TDSP' field is populated with timestamp. TDSP selects 'Modify/Reassign' to enter a different set of dates.
|  | Success Criteria | Touch by TDSP is populated as expected and TDSP is prompted for REP of Record history via the Modify/Reassign transition.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | ERCOT | DEV LSE (StartTime Change) is selected from Submit Tree | User enters all required information and selects 'OK' to create issue |  | 1
Day 2
| Day 3 |  | ERCOT | TDSP | ERCOT passes analysis and transitions to TDSP | "New Pending Approval" state, TDSP selects 'Begin Working' and First Touched by TDSP field is automaticlly populated with accurate timestamp. | TDSP Selects 'Modify/Reassign' and enters different date in 'New StartTime' field and selects 'OK'. TDSP is prompted for REP of Record history. Issue transitions to CR in "New Pending Approval" state. Current workflow resumes and no additional testing is needed. | 1
Day 6
Day 2
Day 3
Day 4

## API ATTCH
|  | Script ID | API ATTACH - USE CASEs 23 & 30 |  |  | API QUERY ONLY
|  | Script Name | Combing use cases (23 & 30) in this test script
|  | Script Storyline | TDSP submits Counts of Subtype (BackGround report) via API. Retrieves the issue attachment via the API. Execute query detail which includes attachment ID.
|  | Success Criteria | BackGround report successfully submitted and attachment retrieved.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | TDSP | TDSP | TDSPs API creates XML to submit a BackGround report (Report Type = Counts of Subtype) | Select Live and/or Archive; Report destination = Issue Attachment. Project = IAG, DEV LSE. StartTime is provided. | Confirm that BackGround report is closed with attachment present. TDSP executes query detail to retrieve atttachment ID and API executess 'A get attachment call' and file is returned successfully. | 1
Day 2
Day 6
Day 2
Day 3
Day 4

## ADMIN1
|  | Script ID | ADMIN - USE CASE 24 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION | MAY NOT BE NEEDED FOR ADMIN
|  | Script Name | New Rolodex subtype escalations
|  | Script Storyline | Market Participant Admin goes into rolodex to select - SwitchHold subtype; Test timing of issue in CERT and is assigned to the appropriate primary escalation
|  | Success Criteria | Confirms the issues are being routed to the appropriate escalation contact
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR Admin | CR Admin | CR selects 'Manage Data' and 'MarkeTrak contacts list rolodex' from dropdown menu. Provide 'Company DUNs' in company field. Select Contact Type 'D2D IAG?'. Select Contact Level 'Primary/Secondary'. Select 'Look Up' next to contact name | Select 'Primary/Secondary' escalation contact; Select update 'D2D SW Hold'. |  | 1
Day 2
Day 6
Day 2
Day 3
Day 4

## VALD1
|  | Script ID | VALD 1 - USE CASE 34 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION | MAY NOT BE NEEDED FOR VALD
|  | Script Name | Test ESIID/TDSP association inaccuracy prompts an 'Error Message'
|  | Script Storyline | Issue is submitted with 'CNP' as assignee but has ONCOR ESIID. Issue will prompt submitter with 'Error Message' and submitter will have to provide the accurate CNP ESIID.
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | Missing SubType is selected from the MarkeTrak Submit Tree | User enters all required information and selects 'OK' to create issue | MT prompts submitter with 'Error Message' and submitter provides correct TDSP/ESIID information. | 1
Day 2
Day 6
Day 2
Day 3
Day 4

## EMAIL1
|  | Script ID | EMAIL 1 - USE CASE 35 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION | MAY NOT BE NEEDED FOR EMAILS
|  | Script Name | Add DUNs and ESIID to GUI Alert emails
|  | Script Storyline | Submit 'Other' issue and submitter selects 'Exclamation' button via the GUI. Email will contain all involved parties DUNs and ESIID in the first line of the email body
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | Other SubType is selected from the MarkeTrak Submit Tree | User enters all required information and selects 'OK' to create issue | Once created, submitter selects 'Exclamation' button to send email and the first line of the email will contain all involved parties DUNs and ESIID | 1
Day 2
Day 6
Day 2
Day 3
Day 4

## SIEBEL
|  | Script ID | SIEBEL - USE CASEs 36 & 46 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | Siebel will populate two new fields 'Regaining BGN Priority Code' and 'Regaining BGN Request Date'. 'Regaining Transaction Submit Date' (already exist) but will automatically populate date from BGN
|  | Script Storyline | Submitter files Customer Rescission subtype; ERCOT validates ESIID submission timeframe and valid originating transaction. Once validation is complete, MT is created and ERCOT updates MT with following: Losing CR Name and DUNs, TDSP Name and DUNs, Gaining CR ROR=YorN, Gaining CR Start Date and Regaining Date is autopoluated by ERCOT. Continue current Customer Rescission workflow and provide Regaining BGN. Once provided, ERCOT will auto populate these fields: Regaining BGN Priority Code, Regaining BGN Request Date, Regaining Tranaction Submit Date. Hover mouse over three new fields to validate help text
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR (Gaining) | Siebel | Customer Rescission SubType is selected from the MarkeTrak Submit Tree | User enters all required information and selects 'OK' to create issue. Siebel proceeds with validations and populates the following: -Losing CR Name and DUNs -TDSP Name and DUNs -Gaining CR ROR=YorN -Gaining CR Start Date -Regaining Date is autopoluated by Siebel | Current Customer Rescission workflow continues and Losing CR provides Regaining BGN. Once provided, ERCOT will auto populate these fields: -Regaining BGN Priority Code -Regaining BGN Request Date -Regaining Tranaction Submit Date | 1
Day 2
| Day 1 |  | Siebel | CR (Losing) |  | Losing CR provides Regaining BGN. | Siebel will auto populate these fields: -Regaining BGN Priority Code -Regaining BGN Request Date -Regaining Tranaction Submit Date CR Losing - verifies help text exist for all three new fields | 1
Day 6
Day 2
Day 3
Day 4

## EMAIL2
|  | Script ID | EMAIL 2 - USE CASE 37 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION | MAY NOT BE NEEDED FOR EMAILS
|  | Script Name | Escalation email sent if in 'New State' more than 3 calendar days
|  | Script Storyline | Issue submitted and prior to 'Begin Working' the issue is in state of 'New' for more than 3 days and escalation email is sent to primary and/or secondary escalation contact
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | D2D Subtype Other is selected from the MarkeTrak Submit Tree | User enters all required information and selects 'OK' to create issue. Issue remains in 'New' for more than 3 calendar days | Escalation email is sent to primary and/or secondary escalation contact | 1
Day 2
Day 6
Day 2
Day 3
Day 4

## BCKGRND1
|  | Script ID | BCKGRND - USE CASE 15, 26A & 44 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | Return date configurable comments on BackGround reports
|  | Script Storyline | BackGround 'Issue Details by ESIID' submitted by MP; Enter 'Y' for comments provided field; Enter Comment Start Date and Comment End Date; BackGround will provide comments within date range specified
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | ERCOT | BackGround 'Issues Details by ESIID' report is selected from the submit tree and created; Submitter enters: -'Y' for 'Comments Provided' field -Date ranges entered for comment Start and Stop dates | User verifies help text exist for the new parameters; User selects: -Report destination = Issue or MIS -Data returned = Lived, Archived or both -Select projects subtype = Cancel with Approval -User verifies the report description notes 'First Available Date' will be used in the report | Parmeter 1: Includes Comments = Y/N; Parameter 2 & 3: Comments Start date and Stop date; Prior to execution, work with ERCOT to identify particular ESIID and MarkeTrak Issue; Verify "Submitting MP" column exists and proper values are displayed. Also verify in the results file that the expected data is returned. | 1
Day 2
Day 6
Day 2
Day 3
Day 4

## MISSENR
|  | Script ID | D2D MISS ENRLTXN - USE CASEs 22, 32 &5 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | Add 867_02, 814_PC and 814_PD to drop down menu for D2D Missing TRX subtype
|  | Script Storyline | Select new values in the Tran_ID drop down field
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | CR first verifys D2D SubType under submit Tree is 'Missing Enrollment TXNs' and submits D2D issue 'Missing Enrollment Transcation SubType' and selects 814_PC from drop down menu. | Verify '814_PC, 814_PD and 867_02' all exist in the drop down field. |  | 1
Day 2
Day 6
Day 2
Day 3
Day 4

## PRMISE
|  | Script ID | D2D PREMISE - USE CASE 31 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | CR submits Premise subtype and TDSP enters 81420 Tran_ID upon completion
|  | Script Storyline | CR submits Premise subtype and TDSP enters 81420 Tran_ID upon completion
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | CR creates and submits 'Premise Type' issue with all required fields |  |  | 1
Day 2
| Day 1 |  | TDSP | TDSP | TDSP verifies 81420 for ESIID and enters 81420 Tran_ID upon the "Sent/Complete" transition state | CR verifies 81420 Transaction exists in CERT environment |  | 1
Day 2
Day 3
Day 4

## SRV ADD
|  | Script ID | D2D SRVC ADDR - USE CASE 31 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | CR submits Service Address subtype and TDSP enters 81420 Tran_ID upon completion
|  | Script Storyline | CR submits Service Address subtype and TDSP enters 81420 Tran_ID upon completion
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | CR creates and submits 'Service Address' issue with all required fields |  |  | 1
Day 2
| Day 1 |  | TDSP | TDSP | TDSP verifies 81420 for ESIID and enters 81420 Tran_ID upon the "Sent/Complete" transition state | CR verifies 81420 Transaction exists in CERT environment |  | 1
Day 2
Day 3
Day 4

## 997
|  | Script ID | 997 - USE CASE 40 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | Add additional optional fields to the '997' subtype upon submission
|  | Script Storyline | Additional optional fields should be visible via the D2D 997 subtype: ESIID, StartTime, StopTime and Original_Tran_ID
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | CR creates and submits '997' issue with all required fields | CR provides ESIID, StartTime and StopTime and Original_Tran_ID and submits issue. |  | 1
Day 2
Day 2
Day 3
Day 4

## ADMIN2
|  | Script ID | ADMIN WORKFLOW - USE CASE 4 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | Add/Update/Delete User Workflows
|  | Script Storyline | Market Participant Admin adds, updates and deletes a MarkeTrak user through the Admin Workflows.
|  | Success Criteria | User is successfully added, then updated, then deleted in MarkeTrak.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR Admin | CR Admin | CR Admin selects the MarkeTrak Admin tab . | User Administration workflows display under the Submit Tree.
| Day 1 |  | CR Admin | CR Admin | CR Admin selects Browse and Submit to a Project. CR Admin selects Add User from the Submit Tree. | Add User Submit pane displays
|  |  | CR Admin | CR Admin | CR Admin enters the following required information: -Employee ID -First Name -Last Name -Telephone -Email Address CR Admin selects OK | Add User issue transitions to state of 'Parameters Provided'
|  |  | CR Admin | CR Admin | CR Admin selects 'Commit' transition | User is created and issue transitions to state of 'Closed'
| Day 2 |  | CR Admin | CR Admin | CR Admin selects the Submit transition . | User Administration workflows display under the Submit Tree.
| Day 3 |  | CR Admin | CR Admin | CR Admin selects Browse and Submit to a Project. CR Admin selects Update User from the Submit Tree. | Select Update User fields display
| Day 4 |  | CR Admin | CR Admin | CR Duns is auto populated in the Company field. CR Admin clicks the Find button next to the Contact field and selects the user created with the Add functionality on line 28 above. CR Admin selects OK. | Update User issue transitions to state of 'User Selected'
|  |  | CR Admin | CR Admin | CR Admin selects 'Edit User' transition | Fields that are available for edit appear in green.
|  |  | CR Admin | CR Admin | CR Admin edits the Email Address field and selects OK. | Update User issue transitions to state of 'Parameters Provided'
|  |  | CR Admin | CR Admin | CR Admin selects 'Commit' transition | User is Updated and issue transitions to state of 'Closed'
| Day 3 |  | CR Admin | CR Admin | CR Admin selects Browse and Submit to a Project. CR Admin selects Delete User from the Submit Tree. | Select Delete User fields display
| Day 4 |  | CR Admin | CR Admin | CR Duns is auto populated in the Company field. CR Admin clicks the Find button next to the Contact field and selects the user created with the Add functionality on line 28 above. CR Admin selects OK. | Delete User issue transitions to state of 'User Selected'
|  |  | CR Admin | CR Admin | CR Duns is auto populated in the Company field. CR Admin clicks the Find button next to the Replacement Contact for Active Issues field and selects a different user. CR Admin selects OK. | Delete User issue transitions to state of 'Replacement Selected'
|  |  | CR Admin | CR Admin | CR Admin selects 'Commit' transition | User is Updated and issue transitions to state of 'Closed'

## EMAIL3
|  | Script ID | EMAIL3 - USE CASE 28 |  |  | API USERs PERFORM QUERY DETAIL/QUERY LIST TO SEE RESULTS AFTER SUBMISSION
|  | Script Name | Auto-close escalation message
|  | Script Storyline | An issue is put in 'Pending Issue' state not yet submitted and remains in 'Pending Issue' state more than 3 calendar days
|  | Success Criteria | After 3 calendar days the issue 'auto closes' and an email is sent by the MarkeTrak tool to the submitter advising the issue is now closed
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  | None | Energized | No
|  | Operating Rule |  |  | TRACK
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 |  | CR | TDSP | Submitter selects 'Other' Subtype and enters required information and checks the "Pending Box" | Submitter selects 'Ok' and issue is in 'Pending Issue' state. | ERCOT will determine escalated timeline for auto-close in CERT | 1
Day 2
| Day 6 |  | CR | CR |  | Issue remains in 'Pending Issue' state for pre-determined CERT time. The issue then auto-closes and an email is sent to the Submitting CR advising them the issue has been closed | May be some lag time in between when the issue auto-closes and email is sent from the tool. Maximum amount of time it may take is '45' minutes.
Day 2
Day 3
Day 4