## PROJECTS
Generator Interconnection Status Report | June 2014
Date: 7/1/2014 8:11:49 AM

## New Units
New Executed Interconnection Agreements
INR | Project | MW | County | Signed IA Date
14INR0076 | GCWA_Gen_1 | 5 | Galveston | 2014-05-21
15INR0079 | Pullman Road | 300 | Randall | 2014-05-29
New Resources Available for Synchronization
INR | Project | MW | County | Part2 Synch Apprv
14INR0012a | Miami Wind 1 Project | 289 | Gray | 2014-06-26
New Resources Approved for Commercial Operations
INR | Project | MW | County | Part3 Commercial Apprv
13INR0048 | Spinning Spur Wind Two | 161 | Oldham | 2014-06-19
11INR0013 | Goldthwaite Wind Energy | 149 | Mills | 2014-06-02
14INR0030a_2 | Panhandle Wind 1 | 218 | Carson | 2014-06-27

## Summary of GIR
Summary of Generation Interconnection Requests |  | Fuel Type | Screening Study (MW)* | Screening Study w/ PL (MW)** | Full Study (MW)* | Full Study w/ PL (MW)** | IA Executed (MW)** | IA Executed FIS Pending (MW)** | Grand Total (MW)
Currently tracking 230 generation interconnection or change requests |  | Gas-AllOther |  |  | 4408 | 0 | 1141 | 758 | 6307
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  | Gas-CombinedCycle |  |  | 8653 | 0 | 4337 | 2948 | 15938
June 2014 | Total | Total Gas | 8259 | 0 | 13061 | 0 | 5478 | 3706 | 30504
Security Screening Study (SSS) Underway | 12 | Nuclear | 0 | 0 | 0 | 0 | 0 | 0 | 0
SSS Completed | 28 | Coal | 0 | 0 | 30 | 0 | 0 | 240 | 270
Full Interconnect Study (FIS) Underway | 116 | Wind | 2824 | 0 | 13727 | 0 | 4292 | 4173 | 25016
FIS Completed | 8 | Solar | 1323 | 0 | 2110 | 0 | 198 | 0 | 3631
Interconnection Agreement Executed -> FIS Pending | 25 | Biomass | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interconnection Agreement Executed | 40 | Storage | 0 | 0 | 594 | 0 | 0 | 0 | 594
Total Interconnection Requests | 230 | Petroleum Coke | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cancelled Studies (since last month) | 5 | Total | 12406 | 0 | 29522 | 0 | 9968 | 8119 | 60015
Total Capacity Under Study, MW | 60404.3 | * Confidential project interconnection requests
Total Wind Capacity, MW | 25405.3 | ** Public project interconnection requests; waiver of confidential information received by ERCOT ("Public Letter") or IA executed.
Interconnection Agreement Executed, MW | 9967.7
Cancelled Capacity, MW (since last month) | 655

## IA Table
Generation Interconnection Agreements as of June 2014
GINR Reference Number | Project Name | County | Projected COD | Fuel | MW For Grid | Changes From Last Report | Sufficient Financial Security Received by TSP | Meets Requirements of PG Section 6.9
13INR0021 | Ferguson Replacement Project | Llano | 2014-07-01 | GAS | 570 |  | Yes | Yes
14INR0012a | Miami Wind 1 Project | Gray | 2014-07-01 | WIND | 289 |  | Yes | Yes
14INR0015 | Deer Park Energy Center | Harris | 2014-07-01 | GAS | 190 |  | Yes | Yes
14INR0076 | GCWA_Gen_1 | Galveston | 2014-07-01 | GAS | 5 | NEW | No | No
10INR0020a | Panda Temple 1 | Bell | 2014-08-01 | GAS | 717 |  | Yes | Yes
10INR0021 | Panda Sherman Power | Grayson | 2014-08-01 | GAS | 720 |  | Yes | Yes
13INR0040 | Rentech Project | Harris | 2014-08-01 | GAS | 16 |  | Yes | Yes
14INR0024 | OCI Alamo 4 | Kinney | 2014-08-01 | SOLAR | 38 |  | Yes | Yes
14INR0059 | Forney Upgrade | Kaufman | 2014-08-01 | GAS | 34 |  | No | No
11INR0094 | White Camp Solar | Kent | 2014-10-01 | SOLAR | 100 |  | No | No
12INR0034a | Stephens Ranch Wind Energy Phase 1 | Borden | 2014-10-01 | WIND | 201 |  | Yes | Yes
12INR0059 | Barilla Solar | Pecos | 2014-11-01 | SOLAR | 30 |  | Yes | Yes
14INR0030b | Panhandle Wind 2 | Carson | 2014-11-01 | WIND | 182 |  | Yes | Yes
14INR0066 | Lamar Power Projects Upgrade | Lamar | 2014-11-01 | GAS | 130 | SFS, PG Section 6.9 | Yes | Yes
13INR0005a | Grandview Phase I (Conway Windfarm) | Carson | 2014-12-01 | WIND | 211 |  | Yes | Yes
13INR0010d | Scandia Wind | Parmer | 2014-12-01 | WIND | 200 |  | No | No
13INR0052 | Los Vientos III | Starr | 2014-12-01 | WIND | 200 |  | Yes | Yes
13INR0057 | Windthorst 2 | Archer | 2014-12-01 | WIND | 65 |  | Yes | Yes
13INR0059a | Hereford Wind | Castro | 2014-12-01 | WIND | 200 |  | Yes | Yes
14INR0023 | Longhorn Energy Center | Briscoe | 2014-12-01 | WIND | 361 |  | Yes | Yes
14INR0049_2 | Keechi Wind 138 kV Joplin | Jack | 2014-12-01 | WIND | 102 |  | Yes | Yes
09INR0051 | Mesquite Creek | Borden | 2015-01-01 | WIND | 249 |  | Yes | Yes
12INR0068 | Sendero Wind Energy Project | Jim Hogg | 2015-02-01 | WIND | 78 |  | Yes | Yes
12INR0070 | Green Pastures | Knox | 2015-02-01 | WIND | 300 |  | Yes | Yes
12INR0034b | Stephens Ranch Wind Energy Phase b | Borden | 2015-04-01 | WIND | 177 |  | Yes | Yes
13INR0059b | Jumbo Road Wind | Castro | 2015-04-01 | WIND | 300 |  | Yes | Yes
14INR0038 | PHR Peakers | Galveston | 2015-04-01 | GAS | 390 |  | Yes | No
14INR0047 | Wake Wind | Floyd | 2015-04-01 | WIND | 299 |  | Yes | Yes
13INR0020a | CPV Rattlesnake Den Ph 1 | Glasscock | 2015-05-01 | WIND | 211.2 |  | Yes | Yes
13INR0050 | Logans Gap Wind I | Comanche | 2015-05-01 | WIND | 200 |  | No | No
11INR0079a | South Clay Windfarm | Clay | 2015-06-01 | WIND | 200 | SFS, PG Section 6.9 | Yes | Yes
14INR0039 | Goldsmith Peaking Facility | Ector | 2015-06-01 | GAS | 408 |  | No | No
14INR0053 | Spinning Spur Wind Three | Oldham | 2015-06-01 | WIND | 194 |  | Yes | Yes
14INR0025a | South Plains Wind I | Floyd | 2015-07-01 | WIND | 200 |  | No | No
08INR0018 | Gunsight Mountain | Howard | 2015-08-01 | WIND | 120 |  | No | No
10INR0020b | Panda Temple Power II | Bell | 2015-08-01 | GAS | 717 |  | Yes | Yes
11INR0062 | Patriot (Petronilla) Wind | Nueces | 2015-08-01 | WIND | 178 |  | Yes | Yes
14INR0012b | Miami Wind 1 Project | Gray | 2015-08-01 | WIND | 111 |  | No | No
14INR0032a | Route66 Wind | Randall | 2015-08-01 | WIND | 150 | Projected COD | Yes | Yes
11INR0057 | Cameron County Wind | Cameron | 2015-09-01 | WIND | 165 |  | No | No
13INR0049 | Friendswood Energy | Harris | 2015-09-01 | GAS | 316 |  | No | No
15INR0079 | Pullman Road | Randall | 2015-09-01 | WIND | 300 | NEW | No | No
11INR0054 | Midway Farms Wind | San Patricio | 2015-10-01 | WIND | 161 |  | Yes | Yes
13INR0010a | Mariah Wind | Parmer | 2015-10-01 | WIND | 232 |  | No | No
06INR0022c | Baffin (Penascal Wind Farm 3) | Kenedy | 2015-12-01 | WIND | 202 |  | Yes | Yes
13INR0010b | Mariah Wind | Parmer | 2015-12-01 | WIND | 200 |  | No | No
13INR0010e | Scandia Wind | Parmer | 2015-12-01 | WIND | 200 |  | No | No
13INR0031 | Mustang Solar Project | Travis | 2015-12-01 | SOLAR | 30 |  | No | No
14INR0025b | South Plains II | Floyd | 2015-12-01 | WIND | 300 |  | No | No
14INR0072 | Briscoe Wind Farm | Briscoe | 2015-12-01 | WIND | 201 |  | Yes | Yes
13INR0020b | CPV Rattlesnake Den Ph 2 | Glasscock | 2016-05-01 | WIND | 157.5 |  | No | No
13INR0028 | Antelope Station | Hale | 2016-06-01 | GAS | 359 | PG Section 6.9 | Yes | Yes
15INR0032 | Antelope Station CT1 | Hale | 2016-07-01 | GAS | 197 |  | No | No
15INR0033 | Antelope Station CT2 | Hale | 2016-07-01 | GAS | 197 |  | No | No
16INR0010 | FGE Texas 1 | Mitchell | 2016-07-01 | GAS | 799 |  | No | No
06INR0006 | Cobisa-Greenville | Hunt | 2016-12-01 | GAS | 2023 | MW For Grid | No | No
12INR0029 | Comanche Run Wind | Swisher | 2016-12-01 | WIND | 500 |  | No | No
13INR0010c | Mariah Wind | Parmer | 2016-12-01 | WIND | 168 |  | No | No
13INR0010f | Scandia Wind | Parmer | 2016-12-01 | WIND | 200 |  | No | No
12INR0018 | Pampa Wind | Gray | 2017-03-01 | WIND | 500 |  | No | No
16INR0003 | Freeport LNG PreTreatment Facility | Brazoria | 2017-06-01 | GAS | 11 |  | No | No
10INR0022 | Pondera King Power Project | Harris | 2017-08-01 | GAS | 925 |  | No | No
13INR0023 | Texas Clean Energy Project | Ector | 2019-03-01 | COAL | 240 |  | No | No

## Full Study Table
GINR Reference Number | County | Fuel | Capacity to Grid (MW) | Projected COD (as specified by the resource developer) | Public Letter
14INR0076 | Galveston | Gas | 5 | 2014-07-01
14INR0077 | Smith | Gas | 10 | 2014-08-01
14INR0069 | Milam | Coal | 30 | 2014-08-01
14INR0013 | Cameron | Wind | 103 | 2014-10-15
14INR0009 | Kent | Wind | 248 | 2014-12-01
10INR0085 | Ector | Solar | 57 | 2014-12-01
14INR0023 | Briscoe | Wind | 361 | 2014-12-01
15INR0074 | Deaf Smith | Wind | 156 | 2014-12-30
14INR0057b | Erath | Wind | 48 | 2014-12-31
14INR0057a | Erath | Wind | 48 | 2014-12-31
14INR0056 | Mills | Wind | 101 | 2014-12-31
14INR0048_1 | Wilbarger | Wind | 114 | 2014-12-31
14INR0049_2 | Jack | Wind | 102 | 2014-12-31
13INR0059a | Castro | Wind | 200 | 2014-12-31
13INR0010d | Parmer | Wind | 200 | 2014-12-31
15INR0075 | Nueces | Gas | 51 | 2015-02-28
15INR0070_1 | Pecos | Solar | 110 | 2015-03-01
14INR0020 | Floyd | Wind | 150 | 2015-03-01
10INR0009 | Castro | Wind | 300 | 2015-03-31
13INR0059b | Castro | Wind | 300 | 2015-04-15
15INR0055 | Austin | Gas | 142 | 2015-05-01
15INR0054 | Reeves | Gas | 123 | 2015-05-01
13INR0056 | Scurry | Wind | 366 | 2015-05-01
15INR0021 | Starr | Wind | 200 | 2015-05-15
15INR0069 | Pecos | Solar | 110 | 2015-06-01
15INR0028 | Freestone | Gas | 160 | 2015-06-01
14INR0074 | Williamson | Gas | 92 | 2015-06-01
14INR0050 | Uvalde | Solar | 40 | 2015-06-01
14INR0041a | Willacy | Wind | 115 | 2015-06-01
13INR0026 | Oldham | Wind | 201 | 2015-06-01
14INR0053 | Oldham | Wind | 194 | 2015-06-01
14INR0040 | Hidalgo | Gas | 225 | 2015-06-07
15INR0023 | Wharton | Gas | 700 | 2015-06-15
12INR0055 | Baylor | Wind | 40 | 2015-07-01
13INR0054 | Bee | Gas | 25 | 2015-07-01
14INR0025a | Floyd | Wind | 200 | 2015-07-31
11INR0082a | Val Verde | Wind | 96 | 2015-08-01
14INR0032a | Randall | Wind | 150 | 2015-08-15
14INR0026 | Presidio | Solar | 30 | 2015-09-01
13INR0025 | Randall | Wind | 150 | 2015-09-01
11INR0057 | Cameron | Wind | 165 | 2015-09-01
15INR0050 | Deaf Smith | Wind | 203 | 2015-09-30
14INR0062 | Gray | Wind | 200 | 2015-09-30
15INR0079 | Randall | Wind | 300 | 2015-09-30
15INR0084 | Brewster | Solar | 120 | 2015-10-01
15INR0068 | Sterling | Solar | 20 | 2015-10-01
13INR0055 | Zapata | Wind | 250 | 2015-10-01
13INR0010a | Parmer | Wind | 232 | 2015-10-01
14INR0048_2 | Wilbarger | Wind | 250 | 2015-10-15
14INR0030c | Carson | Wind | 248.4 | 2015-11-01
11INR0082b | Val Verde | Wind | 82 | 2015-11-01
15INR0036 | Uvalde | Solar | 105 | 2015-11-02
15INR0082 | Comanche | Wind | 400 | 2015-11-15
15INR0035 | Kenedy | Wind | 200 | 2015-12-01
15INR0034 | San Patricio | Wind | 201 | 2015-12-01
14INR0044 | Reeves | Solar | 100 | 2015-12-01
14INR0043 | Sterling | Solar | 40 | 2015-12-01
14INR0041b | Willacy | Wind | 115 | 2015-12-01
14INR0014 | Val Verde | Solar | 100 | 2015-12-01
12INR0060 | Schleicher | Wind | 201 | 2015-12-01
08INR0019a | Gray | Wind | 250 | 2015-12-01
14INR0025b | Floyd | Wind | 300 | 2015-12-01
15INR0051 | Castro | Wind | 200 | 2015-12-15
15INR0047 | Presidio | Solar | 42 | 2015-12-15
15INR0045 | Pecos | Solar | 42 | 2015-12-15
12INR0045 | Kleberg | Wind | 135 | 2015-12-15
14INR0060 | Haskell | Wind | 400 | 2015-12-19
15INR0073 | Armstrong | Wind | 201 | 2015-12-30
15INR0064 | Glasscock | Wind | 360 | 2015-12-30
15INR0063 | Castro | Wind | 301 | 2015-12-30
15INR0062 | Hale | Wind | 301 | 2015-12-30
15INR0059 | Pecos | Solar | 102 | 2015-12-31
15INR0049 | Zapata | Wind | 250 | 2015-12-31
15INR0044 | Webb | Solar | 200 | 2015-12-31
15INR0037 | Starr | Wind | 200 | 2015-12-31
14INR0045b | Webb | Wind | 251 | 2015-12-31
14INR0045a | Webb | Wind | 502 | 2015-12-31
14INR0033 | Armstrong | Wind | 500 | 2015-12-31
13INR0045 | Castro | Wind | 288 | 2015-12-31
13INR0038 | Swisher | Wind | 300 | 2015-12-31
13INR0032 | Andrews | Solar | 30 | 2015-12-31
12INR0002a | Briscoe | Wind | 200 | 2015-12-31
11INR0093 | San Patricio | Wind | 41 | 2015-12-31
14INR0072 | Briscoe | Wind | 201 | 2015-12-31
13INR0010e | Parmer | Wind | 200 | 2015-12-31
13INR0010b | Parmer | Wind | 200 | 2015-12-31
16INR0050 | Brewster | Solar | 50 | 2016-03-01
15INR0053 | Winkler | Gas | 123 | 2016-03-30
16INR0036 | Nolan | Gas | 280 | 2016-04-01
14INR0028 | Live Oak | Wind | 300 | 2016-04-01
16INR0009 | Calhoun | Gas | 494 | 2016-04-14
15INR0042 | Hood | Gas | 460 | 2016-05-01
16INR0023 | Dawson | Solar | 100 | 2016-05-30
17INR0004 | Hale | Gas | 202 | 2016-06-01
16INR0038 | McLennan | Gas | 471 | 2016-06-01
16INR0007 | Hidalgo | Gas | 95 | 2016-06-01
16INR0006 | Angelina | Gas | 785 | 2016-06-01
16INR0005 | Cameron | Gas | 871 | 2016-06-01
15INR0057 | Anderson | Gas | 142 | 2016-06-01
15INR0027 | Hidalgo | Gas | 79 | 2016-06-01
14INR0027 | Guadalupe | Gas | 362 | 2016-06-01
13INR0028 | Hale | Gas | 359 | 2016-06-01
16INR0048 | Pecos | Solar | 150 | 2016-06-30
16INR0041 | Pecos | Solar | 100 | 2016-06-30
16INR0040 | Reeves | Solar | 50 | 2016-06-30
16INR0039 | Reeves | Solar | 100 | 2016-06-30
16INR0014a | Castro | Wind | 200 | 2016-07-01
16INR0013 | Nacogdoches | Gas | 229 | 2016-07-01
16INR0012 | Kenedy | Wind | 200 | 2016-07-01
14INR0011 | Swisher | Storage | 270 | 2016-07-01
08INR0019b | Gray | Wind | 250 | 2016-07-01
15INR0033 | Hale | Gas | 197 | 2016-07-01
15INR0032 | Hale | Gas | 197 | 2016-07-01
16INR0037 | Floyd | Wind | 400 | 2016-10-01
16INR0024 | Hidalgo | Wind | 200 | 2016-10-01
15INR0046 | Reeves | Solar | 42 | 2016-10-01
15INR0040 | Presidio | Solar | 60 | 2016-10-01
16INR0004 | Cameron | Gas | 730 | 2016-11-01
16INR0019 | Coke | Solar | 100 | 2016-12-01
16INR0018 | Upton | Solar | 40 | 2016-12-01
16INR0017 | Culberson | Solar | 70 | 2016-12-01
16INR0014b | Castro | Wind | 200 | 2016-12-01
13INR0006 | Gray | Wind | 750 | 2016-12-01
08INR0019c | Gray | Wind | 250 | 2016-12-01
06INR0006 | Hunt | Gas | 2023 | 2016-12-01 | 2005-05-03
11INR0065 | Nueces | Wind | 350 | 2016-12-20
16INR0031 | Starr | Wind | 100 | 2016-12-31
16INR0030 | Young | Wind | 211.2 | 2016-12-31
16INR0029 | Hill | Wind | 100 | 2016-12-31
16INR0028 | Jack | Wind | 100 | 2016-12-31
16INR0027 | Grayson | Wind | 100 | 2016-12-31
16INR0011a | Cameron | Wind | 18 | 2016-12-31
12INR0002b | Briscoe | Wind | 200 | 2016-12-31
13INR0010f | Parmer | Wind | 200 | 2016-12-31
13INR0010c | Parmer | Wind | 168 | 2016-12-31
12INR0018 | Gray | Wind | 500 | 2017-03-31
16INR0008 | Grimes | Gas | 687 | 2017-04-01
17INR0018 | McLennan | Gas | 471 | 2017-05-01
15INR0013 | Anderson | Storage | 324 | 2017-05-01
17INR0010 | Mitchell | Gas | 799 | 2017-06-01
17INR0002 | Henderson | Gas | 527 | 2017-06-01
17INR0003 | Jackson | Gas | 916 | 2017-06-01
17INR0005 | Starr | Wind | 200 | 2017-06-30
17INR0009 | Hood | Gas | 1042 | 2017-07-31
17INR0007 | Wharton | Gas | 1128 | 2017-07-31
10INR0022 | Harris | Gas | 925 | 2017-08-01
16INR0011b | Cameron | Wind | 132 | 2017-12-30
11INR0040 | Freestone | Gas | 640 | 2018-03-01
13INR0023 | Ector | Coal | 240 | 2019-03-31

## Wind Chart
INR | ProjectName | County | Status | COD Projection | IA Signed | Fuel | TypeCode | MWForGrid | Year
14INR0012a | Miami Wind 1 Project | Gray | PLANNED | 2014-07-31 | 2013-03-01 | WIND | WT | 289 | 2014
12INR0034a | Stephens Ranch Wind Energy Phase 1 | Borden | PLANNED | 2014-10-05 | 2012-03-26 | WIND | WT | 201 | 2014
14INR0030b | Panhandle Wind 2 | Carson | PLANNED | 2014-11-01 | 2013-10-02 | WIND | WT | 182 | 2014
13INR0005a | Grandview Phase I (Conway Windfarm) | Carson | PLANNED | 2014-12-01 | 2012-10-24 | WIND | WT | 211 | 2014
14INR0023 | Longhorn Energy Center | Briscoe | PLANNED | 2014-12-01 | 2012-12-10 | WIND | WT | 361 | 2014
13INR0010d | Scandia Wind | Parmer | PLANNED | 2014-12-31 | 2014-04-25 | WIND | WT | 200 | 2014
13INR0052 | Los Vientos III | Starr | PLANNED | 2014-12-31 | 2013-10-18 | WIND | WT | 200 | 2014
13INR0057 | Windthorst 2 | Archer | PLANNED | 2014-12-31 | 2013-08-15 | WIND | WT | 65 | 2014
13INR0059a | Hereford Wind | Castro | PLANNED | 2014-12-31 | 2013-06-10 | WIND | WT | 200 | 2014
14INR0049_2 | Keechi Wind 138 kV Joplin | Jack | PLANNED | 2014-12-31 | 2013-11-08 | WIND | WT | 102 | 2014
09INR0051 | Mesquite Creek | Borden | PLANNED | 2015-01-17 | 2012-09-18 | WIND | WT | 249 | 2015
12INR0070 | Green Pastures | Knox | PLANNED | 2015-02-17 | 2013-12-17 | WIND | WT | 300 | 2015
12INR0068 | Sendero Wind Energy Project | Jim Hogg | PLANNED | 2015-02-28 | 2013-06-26 | WIND | WT | 78 | 2015
12INR0034b | Stephens Ranch Wind Energy Phase b | Borden | PLANNED | 2015-04-01 | 2012-03-26 | WIND | WT | 177 | 2015
13INR0059b | Jumbo Road Wind | Castro | PLANNED | 2015-04-15 | 2013-06-10 | WIND | WT | 300 | 2015
14INR0047 | Wake Wind | Floyd | PLANNED | 2015-04-15 | 2014-03-17 | WIND | WT | 299 | 2015
13INR0020a | CPV Rattlesnake Den Ph 1 | Glasscock | PLANNED | 2015-05-01 | 2013-06-28 | WIND | WT | 211.2 | 2015
13INR0050 | Logans Gap Wind I | Comanche | PLANNED | 2015-05-17 | 2013-12-11 | WIND | WT | 200 | 2015
14INR0053 | Spinning Spur Wind Three | Oldham | PLANNED | 2015-06-01 | 2013-12-20 | WIND | WT | 194 | 2015
11INR0079a | South Clay Windfarm | Clay | PLANNED | 2015-06-15 | 2013-04-05 | WIND | WT | 200 | 2015
14INR0025a | South Plains Wind I | Floyd | PLANNED | 2015-07-31 | 2014-01-02 | WIND | WT | 200 | 2015
08INR0018 | Gunsight Mountain | Howard | PLANNED | 2015-08-01 | 2007-11-12 | WIND | WT | 120 | 2015
11INR0062 | Patriot (Petronilla) Wind | Nueces | PLANNED | 2015-08-15 | 2013-07-15 | WIND | WT | 178 | 2015
14INR0012b | Miami Wind 1 Project | Gray | PLANNED | 2015-08-15 | 2013-03-01 | WIND | WT | 111 | 2015
14INR0032a | Route66 Wind | Randall | PLANNED | 2015-08-15 | 2013-10-31 | WIND | WT | 150 | 2015
11INR0057 | Cameron County Wind | Cameron | PLANNED | 2015-09-01 | 2013-08-09 | WIND | WT | 165 | 2015
15INR0079 | Pullman Road | Randall | PLANNED | 2015-09-30 | 2014-05-29 | WIND | WT | 300 | 2015
13INR0005b | Grandview Phase II (Conway Windfarm) | Carson | PLANNED | 2015-10-01 | 2014-04-23 | WIND | WT | 389 | 2015
13INR0010a | Mariah Wind | Parmer | PLANNED | 2015-10-01 | 2013-01-31 | WIND | WT | 232 | 2015
11INR0054 | Midway Farms Wind | San Patricio | PLANNED | 2015-10-31 | 2012-09-24 | WIND | WT | 161 | 2015
06INR0022c | Baffin (Penascal Wind Farm 3) | Kenedy | PLANNED | 2015-12-01 | 2009-05-08 | WIND | WT | 202 | 2015
14INR0025b | South Plains II | Floyd | PLANNED | 2015-12-01 | 2014-01-02 | WIND | WT | 300 | 2015
13INR0010b | Mariah Wind | Parmer | PLANNED | 2015-12-31 | 2013-01-31 | WIND | WT | 200 | 2015
13INR0010e | Scandia Wind | Parmer | PLANNED | 2015-12-31 | 2014-04-25 | WIND | WT | 200 | 2015
14INR0072 | Briscoe Wind Farm | Briscoe | PLANNED | 2015-12-31 | 2014-01-10 | WIND | WT | 201 | 2015
13INR0020b | CPV Rattlesnake Den Ph 2 | Glasscock | PLANNED | 2016-05-01 | 2013-06-28 | WIND | WT | 157.5 | 2016
12INR0029 | Comanche Run Wind | Swisher | PLANNED | 2016-12-31 | 2013-07-24 | WIND | WT | 500 | 2016
13INR0010c | Mariah Wind | Parmer | PLANNED | 2016-12-31 | 2013-01-31 | WIND | WT | 168 | 2016
13INR0010f | Scandia Wind | Parmer | PLANNED | 2016-12-31 | 2014-04-25 | WIND | WT | 200 | 2016
12INR0018 | Pampa Wind | Gray | PLANNED | 2017-03-31 | 2013-11-12 | WIND | WT | 500 | 2017

## ProjectMatrix
Note on CD15: Katheiser, Jenell: Frontera Chillers 5/17/2013
Note on CE15: Katheiser, Jenell: WA Parish Addition, Bryan Solar
Note on CF15: Murray, Douglas: Sandy Creek
Note on CH15: Murray, Douglas: Los vientos