## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
July 17, 2014

## Slide 2: 2014 Project Update – Agenda
  Project Portfolio Update p. 3-7
    Recent/Upcoming Project Highlights
    Recent Internal Labor Results
    Planning Next Set of Project Bundles
    2014 Release Targets
    2015 Release Targets
    2014 Project Spending Update
  Appendix
    Project Portfolio Gantt Chart p. 8-17
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent/Upcoming Project Highlights
2014 Release 4 Go-Lives (July 2014) In Flight
  SCR756 – MarkeTrak Enhancements – Remaining SCR756 Items
  SCR769 – CRRAH Digital Certificate New Role for Read Only Access
  NPRR491 – Updated Distribution Generation and Demand Response Information for ERCOT
    The postings will not be available behind these links until the implementation of NPRR634:
      Monthly ERCOT Demand Response from ERS (NP3-107, Report Type ID 13241)
      Monthly ERCOT Demand Response from Load Resources (NP3-108, Report Type ID 13242)
      Monthly ERCOT Demand Response from Pilot Projects (NP3-109, Report Type ID 13243)
      Annual Report on ERCOT Demand Response (NP3-110, Report Type ID 13244)
Release Management
  ERCOT has added a Release Management function within the Business Planning & Integration dept.
  Release Management is the identification, assessment, approval, planning, scheduling and reporting of changes releases across the company. It includes managing the inter-dependencies among projects.
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Recent ERCOT Internal Labor Results
Delivery of 2014 Market System Enhancements project in early June

## Slide 5: Planning Next Set of Project Bundles
CMM Start = July 2014
  NPRR559 - Revisions to MCE Calculation
  SCR778 - Credit Exposure Calculations for NOIE Options Linked to RTM PTP Obligations
  NPRR597 - Utilize Initial Estimated Liability (IEL) Only During Initial Market Activity
  NPRR601 - Inclusion of Incremental Exposure in Mass Transitions to Counter-Parties that are Registered as QSEs and LSEs and Provide POLR Service
CRR Start = July 2014
  SCR777 - Bilateral CRR Interface Enhancement
MMS / CDR / MIS Start = July 2014
  NPRR500 - Posting of Generation that is Off but Avail.
  NPRR543 - Message for Confirmed E-Tags
  SCR775 - Posting Results of Real-Time Data in a Display Format
EMS Start = August 2014
  NPRR524 - Resource Limits in Providing A/S
  NPRR573 - Alignment of PRC Calculation
  NPRR581 - Add FRRS as a Subset of Regulation Svc
  Start = October 2014
  NPRR272 - Definition and Participation of QSGRs
MMS Start = August 2014
  ORDC Phase 2
    Identified gray-boxes plus potential new NPRRs (NPRR626?)
  OBD for Shadow Price Caps
    Revision to “Methodology for Setting the Constraint Shadow Price Cap for a Constraint that is Irresolvable in SCED”
  NPRR556 - Resource Adequacy During Transmission Equipment Outage
  NPRR589 - A/S Offers in the SASM
Registration Start = August 2014
  NPRR519 - Collateral Exemption for ERS-Only QSEs
  SCR771 - Independent Master QSE for Split Gen.
Market input on this plan is greatly appreciated!
Initiated
Initiated

## Slide 6: 2014 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
None
January
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR425(b) – GREDP, EIS portions
NPRR589(a) – MMS portion
SCR756(b) – Remaining portions of SCR
(a), (b), etc. indicates multiple phases
None
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
ü
ü
ü
Release Approach | Release 1 2/3 – 2/7 | Release 2 4/14 – 4/18 | Release 3 6/9 – 6/13 | Release 4 7/28 – 8/1 | Release 5 9/22–9/26 | Release 6 12/8–12/12 | 2014 TBD
On-Cycle | NPRR240 NPRR425(b) NOGRR105 NPRR509 | NPRR564 NPRR570 | NPRR532 | NPRR491 SCR769 SCR774 SCR756(b) | NPRR485 NPRR571 NPRR586 SCR774 SCR778 | NPRR327 NPRR467 NPRR500 NPRR543 NPRR556 NPRR559 NPRR580 NPRR589(a) NPRR597 NPRR601 SCR772 SCR777 | OBD(Shadow Price Caps)
Off-Cycle | NPRR416 NPRR575 |  | NPRR555 NPRR568 |  |  |  | 
Counts Total = 31 | 6 | 2 | 3 | 3 | 5 | 11 | 1
June 1st
None
Retail: 2/22-2/23
Retail: 7/26-7/27
ü
ü

## Slide 7: 2015 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
None
Release targets are subject to change
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portion of NPRR
NPRR589(b) – S&B portion
None
None
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
Release Approach | Release 1 February | Release 2 April | Release 3 June | Release 4 July | Release 5 September | Release 6 December | 2015 TBD
On-Cycle | NPRR439 NPRR484(1b) NPRR519 NPRR524 NPRR527 NPRR543 NPRR573 NPRR581 SCR771 SCR775 SCR778 SCR779 | NPRR210 NPRR256 NPRR493 SCR775 | NPRR272 NPRR419 NPRR455 NPRR484(2) NPRR487 NPRR495 NPRR553 NOGRR084 |  |  |  | NPRR439 NPRR484(1b) NPRR515 NPRR589(b)
Off-Cycle |  |  |  |  |  |  | 
Counts Total = 23 | 9 | 3 | 8 | 0 | 0 | 0 | 4
None
None
None

## Slide 8: 2014 Cash Flow Projection – Approved Projects
2014 project budget = $25M

## Slide 9: Business Integration Update – Appendix
  Appendix
    7/1/2014 Project Gantt
      In-flight items sorted by Project End Date
      “On Hold” projects listed separately
      “Not Started” items sorted by Project Start Date

## Slide 10
Project Portfolio Status – as of 7/1/2014

## Slide 11
Project Portfolio Status – as of 7/1/2014

## Slide 12
Project Portfolio Status – as of 7/1/2014

## Slide 13
Project Portfolio Status – as of 7/1/2014

## Slide 14
Project Portfolio Status – as of 7/1/2014

## Slide 15
Project Portfolio Status – as of 7/1/2014

## Slide 16
Project Portfolio Status – as of 7/1/2014

## Slide 17
Project Portfolio Status – as of 7/1/2014

## Slide 18
Project Portfolio Status – as of 7/1/2014