## Sheet1
TX SET Meeting Notes / Action Items
June 18-19 2014
Agenda Item: | Decision / Resolution | Action Items :
Change Control Call--CC2014_803— PUCT Docket 42359, Remand of Docket No. 36952, ET AL - (Application of CenterPoint Houston Electric, LLC to Defer Energy Efficiency Cost Recovery and for Approval of an Energy Efficiency Cost Recovery Factor): |  The group agreed to send the change control to RMS with a recommendation for approval as an emergency change to meet the Sept 1 effective date | • RMS conduct email vote • If RMS approves—Texas SET review redline changes to guides at July Meeting • If Texas SET agrees to send back to RMS—RMS will vote on the guides at the August Meeting
May 2014 Meeting Notes | • The group made minor language changes to the May 2014 meeting notes and action items
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
RMS assignment: Update Transition Contacts documents • Review ERCOT updated documents o RMG Section 09 Appendix F1 Retail Customer Transition Contact List o NCI—Notice of Change in Information • Create changes to submit for approval | o ERCOT reviewed proposed changes to the RMG section 7 Market Processes, 7.11 Transition Process and section 9 Appendix F1 Retail Customer Transition Contact List  ERCOT proposed removing Appendix F1; then require the market to update their NCI—“Notice of Change in Information” with the Transition contacts o Texas SET agreed to work with ERCOT to sponsor and submit these change requests o Also to be included in the RMGRR will be some changes to be made to the RMG Section 9 Appendices F2 & F3 transition timelines. The chair will work with the RMS Chair to include these in the RMGRR | The Texas SET Chair will work with ERCOT and the RMS Chair to compile the RMGRR for submission
Issues
134-Non-CSA CR sends a MVO with the indicator for bypass CSA at ERCOT. Non-CSA CR is not always the owner of the CSA, causing the ESI ID to become de-energized without CSA CRs knowledge | The Texas SET Chair noted that RMGRR124 New REP Operating Rule 13, CSA Bypass Code has been submitted for RMS approval
Flight 0614 Testing Update | • The ERCOT Flight Administrator presented an update for Market Test Flight 0614 o Summary  Flight 0614 is 56.32% complete through 06/17/2014  3 New CRs (includes 2 Additional DUNS testing as new CRs) will be testing  Existing CRs: 7 CRs are testing for new territories, and 1 CR is testing for a bank change  3 Existing CRs (Adding New Territory) withdrew from testing  1 Existing CR adding new territory joined the flight late  1793 tasks are scheduled o Schedule  Flight signup began 05/07/14  Flight deadline was 05/14/14  Connectivity kick-off conference call was 05/20/14  Flight kick-off conference call was 05/30/14  Day 1 transactions began 06/02/14  Flight 0614 is scheduled to concluded 07/15/14 (contingency period until 08/05/14)
ERCOT Market Testing • Script Review • Continue TTPT Review • Other items? | o Texas SET reviewed and made further changes to the script pack; o Texas SET reviewed the Texas Market Test Plan document and noted the sections that need to be re-analyzed and modifications necessary to make terminology consistent throughout the document. | the Texas SET Vice Chair will review and make cosmetic changes to be reviewed at next month’s meeting
Other Business
o ERCOT expressed concern that the current Nodal Protocol section 19 does not completely support the current Texas SET process for submitting emergency changes for the SAC04 codes.The way the Protocol is currently written creates questions about the proper use of the “emergency” designation from higher level ERCOT governing bodies |  The group agreed to sponsor a Nodal Protocol change to replace the word “and” in the 2nd sentence with “or” and to add some additional language for clarification. ERCOT Market Rules will assist in drafting the language for the overall NPRR • Section 19 Texas Standard Electric Transaction, 19.4.7.1 Emergency Change— Request Changes/enhancements to the guidelines must be updated as soon as reasonably practicable. If the current standards cannot accommodate Customer Choice and an urgent modification of the standard is required, the appropriate TAC subcommittee will classify a requested change as an emergency change | The Texas SET chair will work with ERCOT Market Rules to submit the NPRR
REP Certification Matrix—Long-term solution | On hold
Texas SET Procedures Document | On hold
Next Meeting | July 23rd & 24th ERCOT Met Center Rm 168
Attendees RM168
Diana Rehfeldt TNMP | Ed Echols ONCOR | Kaci Jacobs TXU
Kathryn Thurman ERCOT | Ted Hailu ERCOT | Juliana Morehead ERCOT
Gricelda Calzada AEP | Paul Yockey ERCOT | Sandra Tindall ERCOT
Kathy Scott Centerpoint Energy | Becky Taylor Centerpoint Energy | Carolyn Reed Centerpoint Energy
Kyle Patrick Reliant | David Gonzales ERCOT
WebEx:
Amy Rafferty ESG | Suzy Clifton ERCOT
Barbara Boubeaud EC Info Systems | Teresa Rodriquez Stream Energy
Deb Belin Ista NA | Suzanne Clark Liberty Power
Joe Lindsay Systrends | Dave Michelsen ERCOT
Michael Glass SU | Seth Connell ERCOT
Mike Woolsey ONCOR | Ivan Valaquez ONCOR
Roger Tenebown ISTA NA | Dave Louder Nueces
Sarah Heselmeyer ERCOT | Ahmed Shobbir