## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
August 14, 2014

## Slide 2: 2014 Project Update – Agenda
  Project Portfolio Update p. 3-9
    Recent/Upcoming Project Highlights
    Recent Internal Labor Results
    Planning Next Set of Project Bundles
    2014 Release Targets
    2015 Release Targets
      Please note new release calendar structure
    2014 Project Spending Update
    NPRR or SCR?
  Appendix
    Project Portfolio Gantt Chart p. 11-20
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent/Upcoming Project Highlights
2014 Release 4 Off-Cycle Go-Live (August 2014) In Flight
  SCR756 – MarkeTrak Enhancements – Remaining SCR756 Items
    Originally planned for implementation on 7/26/2014
    Rescheduled to Sunday, 8/17/2014
    Final phase of SCR756 implementation
  Client Digital Certificate Upgrade
2014 Release 5 Go-Lives (September 2014) In Flight
  NPRR485 – Clarification for Fuel Adder Provisions
  NPRR571 – ERS Weather-Sensitive Loads Requirements
  NPRR586 – Align Credit Lock for CRR Auctions with Transaction Submission Deadline
  SCR774 – Enhancement to Outage Scheduler and Reports
    Phase 1 – All new fields except for Comments (pending NPRR643 approval)
  Planning Site Transition to MIS
  Reactive Test Forms Revision
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Recent ERCOT Internal Labor Results
Delivery of 2014 Market System Enhancements project in early June

## Slide 5: Planning Next Set of Project Bundles
CMM Start = July 2014
  NPRR559 - Revisions to MCE Calculation
  SCR778 - Credit Exposure Calculations for NOIE Options Linked to RTM PTP Obligations
  NPRR597 - Utilize Initial Estimated Liability (IEL) Only During Initial Market Activity
  NPRR601 - Inclusion of Incremental Exposure in Mass Transitions to Counter-Parties that are Registered as QSEs and LSEs and Provide POLR Service
CRR Start = July 2014
  SCR777 - Bilateral CRR Interface Enhancement
MMS / CDR / MIS Start = July 2014
  NPRR500 - Posting of Generation that is Off but Avail.
  NPRR543 - Message for Confirmed E-Tags
  SCR775 - Posting Results of Real-Time Data in a Display Format
EMS Start = October 2014
  NPRR524 - Resource Limits in Providing A/S
  NPRR573 - Alignment of PRC Calculation
  NPRR581 - Add FRRS as a Subset of Regulation Svc
  NPRR272 - Definition and Participation of QSGRs
MMS Start = August 2014
  NPRR626 - Reliability Deployment Price Adder
  OBD for Shadow Price Caps
    Revision to “Methodology for Setting the Constraint Shadow Price Cap for a Constraint that is Irresolvable in SCED”
  NPRR556 - Resource Adequacy During Transmission Equipment Outage
  NPRR589 - A/S Offers in the SASM
Registration Start = October 2014
  NPRR519 - Collateral Exemption for ERS-Only QSEs
  NPRR588 - Clarifications for PV Generation Resources
  NPRR615 - PVGR Forecasting
  SCR771 - Independent Master QSE for Split Gen.
Market input on this plan is greatly appreciated!
Initiated
Initiated
Initiated

## Slide 6: 2014 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
None
January
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR425(b) – GREDP, EIS portions
NPRR589(a) – MMS portion
SCR756(b) – Remaining portions of SCR
SCR774(a) – All new fields except Comments
(a), (b), etc. indicates multiple phases
None
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
ü
ü
ü
Release Approach | Release 1 2/3 – 2/7 | Release 2 4/14 – 4/18 | Release 3 6/9 – 6/13 | Release 4 7/28 – 8/1 | Release 5 9/22–9/26 | Release 6 12/8–12/12 | 2014 TBD
On-Cycle | NPRR240 NPRR425(b) NOGRR105 NPRR509 | NPRR564 NPRR570 | NPRR532 | NPRR491 SCR769 SCR756(b) | NPRR485 NPRR571 NPRR586 SCR774(a) SCR778 | NPRR327 NPRR467 NPRR500 NPRR556 NPRR559 NPRR580 NPRR589(a) NPRR597 NPRR601 SCR772 SCR777 SCR778 | OBD(Shadow Price Caps)
Off-Cycle | NPRR416 NPRR575 |  | NPRR555 NPRR568 |  | NPRR527 |  | 
Counts Total = 27 | 6 | 2 | 3 | 3 | 5 | 8 | 0
June 1st
Oct/Nov
Retail: 2/22-2/23
Retail: 8/17
ü
ü
ü
2015

## Slide 7: 2015 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portion of NPRR
NPRR589(b) – S&B portion
SCR774(b) – Addition of Comments field
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
Release 1 January | Release 2 February | Release 3 March | Release 4 May | Release 5 June | Release 6 August | Release 7 September | Release 8 November | Release 9 December
NPRR559 NPRR597 NPRR601 SCR772 | NPRR519 NPRR524 NPRR527 NPRR543 NPRR573 NPRR581 SCR771 SCR775 SCR779 | NPRR210 NPRR256 NPRR493 NPRR524 NPRR573 NPRR581 SCR771 | NPRR272 NPRR419 NPRR455 NPRR484(2) NPRR487 NPRR495 NPRR553 NPRR588 NPRR615 NOGRR084 |  | NPRR626 OBD(Shadow Price Caps) |  |  | 
 |  |  |  |  | NPRR515 | NPRR589(b) | NPRR439 NPRR484(1b) | NOGRR084 SCR774(b)
4 | 4 | 7 | 8 | 0 | 2 | 0 | 0 | 0
2014
May 2014
2015 TBD Items (and month they became “TBD”)
June 2014
July 2014
Aug 2014

## Slide 8: 2014 Cash Flow Projection – Approved Projects
2014 project budget = $25M

## Slide 9: NPRR or SCR?
When is an NPRR required?
  When Protocol language is being changed
When is an SCR required?
  When there is a request for a change to ERCOT systems that doesn't impact Protocol language
Important considerations
  Protocol language requires explicit approval to post information so if the request includes a new posting, an NPRR is required to authorize the posting
  In some cases, the changes proposed by an SCR were not anticipated in the current Protocols. Prior to filing the SCR, it is advantageous to consider whether the requirements of the SCR should be added to the Protocols (thus requiring an NPRR, not an SCR)
(3) ERCOT shall evaluate the SCR to determine whether the request should be submitted as an NPRR. If ERCOT determines that the SCR should be submitted as an NPRR, ERCOT will notify the submitter within five Business Days of receipt, and the submitter shall withdraw its SCR and may submit an NPRR in its place.
Protocol Section 21.4.2

## Slide 10: Business Integration Update – Appendix
  Appendix
    8/1/2014 Project Gantt
      In-flight items sorted by Project End Date
      “On Hold” projects listed separately
      “Not Started” items sorted by Project Start Date

## Slide 11
Project Portfolio Status – as of 8/1/2014

## Slide 12
Project Portfolio Status – as of 8/1/2014

## Slide 13
Project Portfolio Status – as of 8/1/2014

## Slide 14
Project Portfolio Status – as of 8/1/2014

## Slide 15
Project Portfolio Status – as of 8/1/2014

## Slide 16
Project Portfolio Status – as of 8/1/2014

## Slide 17
Project Portfolio Status – as of 8/1/2014

## Slide 18
Project Portfolio Status – as of 8/1/2014

## Slide 19
Project Portfolio Status – as of 8/1/2014

## Slide 20
Project Portfolio Status – as of 8/1/2014