## Sheet1
TX SET Meeting Notes / Action Items
July 23-24 2014
Agenda Item: | Decision / Resolution | Action Items :
CC2014_803— PUCT Docket 42359, Remand of Docket No. 36952, ET AL - (Application of CenterPoint Houston Electric, LLC to Defer Energy Efficiency Cost Recovery and for Approval of an Energy Efficiency Cost Recovery Factor): Redline Review | Texas SET recommends the redlined Implementation Guide be sent to RMS for approval as an emergency change to be effective 9/1/2014
June 2014 Meeting Notes | No changes were made to the notes
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
• NPRRxx Draft section 19—Tentative Discussion : ERCOT expressed concern that the current Nodal Protocol section 19 does not completely support the current Texas SET process for submitting emergency changes for the SAC04 codes.The way the Protocol is currently written creates questions about the proper use of the “emergency” designation from higher level ERCOT governing bodies | Texas SET reviewed language changes and determined that further review is necessary. A subteam was formed to complete this review. | Subteam: Kathryn Thurman ERCOT, Sandra Tindal ERCOT, Kathy Scott CNP and Diana Rehfeldt TNMP. Action item: review Protocol Chapter 19 Sections, make changes where needed and bring redlines back to the August Meeting.
• Tariff Project 41121--RMG Section 7 Market Processes updates related to TDSP tariff changes effective Jan 2015 o DNP / RNP timelines o Safety Net timelines | Texas SET reviewed the RMG Chapter 7 Market Processes sections; marked possible section changes and recommended forming a subteam to continue the review and comparison of the Tariff timing changes.The Subteam will meet August 21st at the MET Center. There will be no WebEx offered as the regular Texas SET meeting will not be held. | Subteam: Kathy Scott CNP, Kyle Patrick Reliant, Kaci Jacobs TXU, Ed Echols ONCOR, Sandra Tindal ERCOT, Gricelda Calzada AEP, Becky Taylor CNP, Mike Glass Sharyland and Diana Rehfeldt TNMP Action Item: Continue to review RMG Section 7 Market Processes and compare to Tariff timing changes made to determine if changes are needed in the RMG.
Issues | No Issues submitted for discussion this month
Flight 0614 Testing Update | ERCOT updated Texas SET with the flight stats :• Summary o Flight 0614 is 99.67% complete through 07/22/2014 o 3 New CRs (includes 2 Additional DUNS that tested as new CRs) tested o Existing CRs: 7 CRs tested for new territories, and 1 CR tested for a bank change o 3 Existing CRs (Adding New Territory) withdrew from testing o 3 Existing CR adding new territory joined the flight late (2 are currently completing connectivity and penny testing to add Sharyland Utilities) o Contingency period until 08/05/2014 o 1845 tasks were scheduled
• Schedule o Flight signup begins 09/03/14 o Flight signup deadline is 09/10/14 o Connectivity kick-off conference call is 09/16/14 o Flight kick-off conference call is 10/03/14 o Day 1 transactions begin 10/06/14 o Flight 1014 is scheduled to concluded 11/18/14 (contingency period until 12/09/14)
ERCOT Market Testing • Script Review • Continue TTPT Review • Other items? | • Texas SET reviewed the script pack and made further updates where needed o Reviewed and updated, where changes were necessary, the Inventory List, IOU Testing Matrix and MOU Testing Matrix tabs o Renumber the CON scripts o Removed I-HU01 as duplicate effort; the transactions are requested and sent in script STK01 o Script development needed for CRs that serve their own load • Texas SET reviewed the Texas Market Test Plan (TMTP) and marked sections needing further review and possible changes. | • Reliant o Re-number CON scripts and clean up the test script pack o Work with NEC to review and recommend MOU EC test scripts and track • ERCOT o Develop New TDSP scripts o Review TMTP to determine what changes will need to be approved in time to create the 2015 testing schedule using the updated script requirements o Create draft 2015 testing schedule • TDSPs to research and provide location of EFT forms used during a Flight
Other Business
Possible new code / transaction development request for the new Curtailment Service Provider entity type. | David Power (Private Citizen) spoke to Texas SET regarding a possible request from the Demand Side Working Group (DSWG) to assist in developing a new code or transaction for a new type of service provider (Curtailment). The future request will be submitted through the appropriate TAC subcommittee, depending on the outcome of the current discussions around Loads in SCED and Demand Response. Mr. Power will be updating other subcommittees and working groups on this subject. | Texas SET will wait for RMS direction.
REP Certification Matrix—Long-term solution | On hold
Texas SET Procedures Document | On hold
Next Meeting | August 20th t ERCOT Met Center Rm 168 | August 21st will be a subcommitte only working session in the same room, but the Webex will not be available
Attendees RM168
Gricelda Calzada AEP | Becky Taylor CNP | Ed Echols ONCOR
Kyle Patrick Reliant | Kathryn Thurman ERCOT | Paul Yockey ERCOT
Michael Glass SU | Carolyn Reed CNP | John Schatz TXU Energy
Rosanna Adams NEC | Paula Shadle NEC | David Power Private Citizen
Kaci Jacobs TXU Energy | Sandra Tindal ERCOT | Diana Rehfeldt TNMP
WebEx:
Babara Gobeaud EC InfoSystems | Amy Rafferty ESG | Deb Belin ISTA NA
Joe Lindsay Systrends | Mary Sithihou Stream | Teresa Rodriquez Stream
Ivan Velasquez ONCOR | Mike Woolsey ONCOR | Dave Louder NEC