|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report July 2014 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 231 active generation interconnection requests totaling over 63,000 MW. This includes over 25,300 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $445.7 Million. - Transmission Projects endorsed in 2014 total $736.1 Million. - All projects (in engineering, routing, licensing and construction) total approximately $4.98 Billion. - Transmission Projects energized in 2014 total about $438.2 Million. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

2.	Regional Planning Group Project Reviews	1

3.	Asynchronous Tie Interconnection	2

4.	Planning Model Activities	3

5.	Other Notable Activities	3

# 1.	Generation Interconnection

Generator interconnection information has been moved to the Generator Interconnection Status (GIS) Report, which is published monthly under the Grid Information / Resource Adequacy section of the ercot.com website.  Please  see the exact web link below.

http://www.ercot.com/gridinfo/resource/index

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

# Regional Planning Group Project Reviews

- Oncor has submitted the West Texas Area project. This is a Tier 2 project that is estimated to cost $45 million. This project has completed the RPG review and ERCOT will send the RPG acceptance letter.

- Sharyland has submitted the Brady Area project. This is a Tier 2 project that is estimated to cost $18 million. This project is currently under ERCOT independent review.

- Sharyland has submitted the West Texas projects for Stanton Area. This is a Tier 3 project that is estimated to cost $40.4 million. This project has completed the RPG review and ERCOT will send the RPG acceptance letter.

- AEPSC has submitted the Brady Area Improvements project. This is a Tier 2 project that is estimated to cost $26.5 million. This project is currently under ERCOT independent review.

- Denton Municipal Electric (DME), Oncor, TMPA, Brazos Electric Cooperative (BEC) and GP&L have jointly submitted the Denton Area West 345/138 kV source project. This is a Tier 2 project that is estimated to cost $44.8 million. This project is currently under ERCOT independent review.

- Duke-American Transmission Company has submitted the Phoenix project. This is a Tier 2 project that is estimated to cost $39 million. This project has received several RPG comments and it is under study mode.

- CPS Energy has submitted the Howard Road - Somerset 138 kV upgrade project. This is a Tier 2 project that is estimated to cost $18.3  million. This project is currently under ERCOT independent review.

- CPS Energy and LCRA Transmission Services Corporation (TSC) have jointly submitted the Transmission System Additions project to address the reliability needs in the northeast San Antonio area. This is a Tier 1 project that is estimated to cost $237.3 million. This project is currently under ERCOT independent review.

- CenterPoint Energy has submitted the Jones Creek project. This is a Tier 1 project that is estimated to cost $79.8 million. This project has received RPG comments and it is under study mode.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Jul 14, 2014	Contingency Definitions Posted

  - Jul 23, 2014	Start 15DSB case build

  - Oct 10, 2014	Post 15DSA updates and 15DSB Cases and MODTPIT

  - Oct 29, 2014	Post Contingency Definitions and Planning Data Dictionary

  - Dec 5, 2014	Complete Transmission Loss Factors

- The following table shows updates since last month of interconnection projects that met Planning Guide section 6.9 (1) and were either modeled or not modeled based on submitted RARF data in accordance with Planning Guide section 6.9 (2).  A non-null value in the Project ID column signifies that the project was modeled and a null value means it was not modeled.  The Notes column may provide further explanation.

# Other Notable Activities

- ERCOT’s reliability analysis of the 2014 Regional Transmission Plan (RTP) is underway. The initial N-1 SCOPF reliability analysis is complete. The generation and transformer outage screening studies are in progress.

- ERCOT's 2014 Long Term System Assessment (LTSA) study is in progress. ERCOT staff is currently working on reliability analysis for the “Current Trends” scenario of the LTSA. Additionally, ERCOT staff presented the results for the generation expansion plan build-out for the all scenarios at the July Regional Planning Group (RPG) meeting.

- ERCOT is planning on conducting a West-North stability limit assessment.  This will be a joint study between ERCOT System Planning and Operations.

- ERCOT is planning on performing a review of the ERCOT responsive reserve requirements taking into account the new BAL-003 standard.