|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report August 2014 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 230 active generation interconnection requests totaling over 62,800 MW. This includes over 25,300 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $393.6 Million. - Transmission Projects endorsed in 2014 total $754.4 Million. - All projects (in engineering, routing, licensing and construction) total approximately $4.98 Billion. - Transmission Projects energized in 2014 total about $438.2 Million. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

2.	Regional Planning Group Project Reviews	1

3.	Asynchronous Tie Interconnection	2

4.	Planning Model Activities	3

5.	Other Notable Activities	3

# 1.	Generation Interconnection

Generator interconnection information has been moved to the Generator Interconnection Status (GIS) Report, which is published monthly under the Grid Information / Resource Adequacy section of the ercot.com website.  Please  see the exact web link below.

http://www.ercot.com/gridinfo/resource/index

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

# Regional Planning Group Project Reviews

- Sharyland has submitted the Brady Area project. This is a Tier 2 project that is estimated to cost $18 million. This project is currently under ERCOT independent review.

- AEPSC has submitted the Brady Area Improvements project. This is a Tier 2 project that is estimated to cost $26.5 million. This project is currently under ERCOT independent review.

- Denton Municipal Electric (DME), Oncor, TMPA, Brazos Electric Cooperative (BEC) and GP&L have jointly submitted the Denton Area West 345/138 kV source project. This is a Tier 2 project that is estimated to cost $44.8 million. ERCOT has completed the independent review and ERCOT is not  recommending a project at this time.

- Duke-American Transmission Company has submitted the Phoenix project. This is a Tier 2 project that is estimated to cost $39 million. This project is currently under ERCOT independent review.

- CPS Energy has submitted the Howard Road - Somerset 138 kV upgrade project. This is a Tier 2 project that is estimated to cost $18.3  million. This project has completed the RPG review and EROT will send the RPG acceptance letter.

- CPS Energy and LCRA Transmission Services Corporation (TSC) have jointly submitted the Transmission System Additions project to address the reliability needs in the northeast San Antonio area. This is a Tier 1 project that is estimated to cost $237.3 million. This project is currently under ERCOT independent review.

- CenterPoint Energy has submitted the Jones Creek project. This is a Tier 1 project that is estimated to cost $79.8 million. This project has received RPG comments and it is under study mode.

- Sharyland has submitted the North Loop Load Integration project. This is a Tier 2 project that is estimated to cost $11 million. This project has been submitted for RPG comments.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Jul 23, 2014	Started 15DSB case build

  - Oct 10, 2014	Post 15DSA updates and 15DSB Cases and MODTPIT

  - Oct 29, 2014	Post Contingency Definitions and Planning Data Dictionary

  - Dec 5, 2014	Complete Transmission Loss Factors

- The following table shows updates since last month of interconnection projects that met Planning Guide section 6.9 (1) and were either modeled or not modeled based on submitted RARF data in accordance with Planning Guide section 6.9 (2).  A non-null value in the Project ID column signifies that the project was modeled and a null value means it was not modeled.  The Notes column may provide further explanation.

# Other Notable Activities

- ERCOT’s reliability analysis of the 2014 Regional Transmission Plan (RTP) is underway. The initial N-1 SCOPF, G-1+N-1 and X-1+N-1 reliability analysis are complete. Final reliability case preparation is in progress.

- ERCOT's 2014 Long Term System Assessment (LTSA) study is in progress. ERCOT staff is currently working on reliability analysis for the “Current Trends” scenario of the LTSA.

- ERCOT has completed the small signal stability analysis and is scheduled to present the results to ROS in September.