## Sheet1
TX SET Meeting Notes / Action Items
September 17th - 18th 2014
Agenda Item: | Decision / Resolution | Action Items :
August 2014 Meeting Notes | No changes were made
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
• NPRRxx Draft section 19—Sub Team Update: ERCOT expressed concern that the current Nodal Protocol section 19 does not completely support the current Texas SET process for submitting emergency changes for the SAC04 codes.The way the Protocol is currently written creates questions about the proper use of the “emergency” designation from higher level ERCOT governing bodies | Texas SET determined that ERCOT needed more time to review the changes made to the Protocol. | ERCOT to review internally and bring comments back to the October meeting
Issue 2014-I139: Would like to discuss how Critical Care (CC) status re-establishes itself for a customer after an IAG has occurred | Texas SET determined that the MarkeTrak IAG issue will be used by the regaining CR to request that any prior Critical Care status be re-instated after the Losing and Gaining CR agree to return the ESI ID to the Losing CR. | NRG will review the Retail Market Guide (RMS) to determine any language changes needed to support this decision and bring those back to the October meeting
Flight 1014 Testing Update | ERCOT provided Texas SET an update of the status for the October Flight.
ERCOT Market Testing • Script Review--IOU; MOU EC, New TDSPs • Continue TMTP Review • EFT Form Location--TDSPs | • Texas SET reviewed the Texas Market Test Plan (TMTP) changes necessary to support the proposed 2015 Flight Schedule and recommended that the document be presented to RMS for a vote at the October Meeting. • Texas SET reviewed and recommended that the proposed 2015 Flight Schedule be presented to RMS for a vote at the October meeting. • It was noted that RMS will need to approve the TMTP changes first; then vote on the Flight Schedule | Texas SET leadership to present both documents to RMS vote the vote in October.
• Tariff Project 41121--RMG Section 7 Market Processes updates related to TDSP tariff changes effective Jan 2015 o DNP / RNP timelines o Safety Net timelines | Texas SET agreed that the group needs more time to review the Retail Market Guide (RMG) redlines created by TXU. | Texas SET will review and make RMG changes needed; then bring those changes for review at the October meeting
Other Business
• RMS assignments
• Review Current documents to determine where to add clarifying language on issues experienced during the Sharyland Transition (e. g. How to create ESI IDs; How do you handle readings for unmetered services; 814_04 reject; etc.) | • Sharyland reviewed the Lessons Learned document from the new territory transition with Texas SET and identified areas where information is needed for new Market Participants entering the ERCOT Retail market. • How to create the 867 reads / consumption for unmetered services • How are the premise type and POLR Class determined and who updates these in the ERCOT system. Explain the difference • What stored information requires an update to be on a loaded read date at ERCOT (i. e. load profile) • Unmetered services require a cycle assignment by the TDSP • What guidelines do TDSPs use when creating new ESI IDs • Use of the TDSP premise supplemental addresses by CRs • Texas SET agreed to form a sub team to develop helpful information for new Market Participants entering the ERCOT Retail Market (TDSPs or CRs) and determine where the information should be stored. (e. g. do some require RMG changes, etc.) c.) | Sub Team members: to meet and begin forming a list of items to be referenced and determine the location of each • Kyle Patrick NRG • Kathryn Thurman ERCOT • Kathy Scott CNP • Pam Shaw SU • Sandra Tindall ERCOT • Ed Echols ONCOR • Kaci Jacobs TXU • Diana Rehfeldt TNMP
• Add STTF Transition Documents (Lessons Learned) to key documents | No discussion this month | Review next month
• Add Master Customer List (MCL) guide back to the Texas SET Guides | No discussion this month | Review next month
• Possible CBCI File validations | Texas SET reviewed the RMG and determine the changes need in section 7.11.3.2 and Appendix F6 | TNMP to draft an RMGRR to submit to RMS for approval. Texas SET will review at the October meeting prior to the RMS October 28th meeting.
REP Certification Matrix—Long-term solution | On hold
Texas SET Procedures Document | On hold
Next Meeting | October 15th & 16th Rm 168 ERCOT Met Center
Attendees
Diana Rehfeldt TNMP | Gricelda Calzada AEP | Kathryn Thurman ERCOT
Paul Yockey ERCOT | Kaci Jacobs TXU | Kathy Scott CNP
Becky Taylor CNP | Ed Echols ONCOR | Pam Shaw SU
Kyle Patrick NRG | Carolyn Reed CNP
WebEx:
Rosana Adams NEC | Roger Tenenbown Aurea Energy Services | Sandra Tindall ERCOT
Seth Connel ERCOT | Stephen Wilson SU | Deb Belin Aurea Energy Services
Amy Rafferty ESG | Scott Brusaw Systrends | Michael Glass SU
Barbar Goueaud EC-Info Systems | Jim Lee Direct Energy | Dave Louder NEC
Heather Mesa SU | BJ Flowers SU