## General S1
Commissioning Plan
|  | Resource Site Name: | Generic Resource LLC
|  | Resource Site Code: | GR | MIAMI WIND I LLC
|  | Resource Entity Name: | Generic Resource (RE)
|  | Resource QSE Name: | Generic Resource (QSE)
|  | Submittal Date: | 2014-10-21
Commissioning Plan Section 1: Resource Site Description
● | The Resource Category for Generic Resource LLC is
● | Total Number of Generation Units at Generic Resource LLC is
● | Total Capacity of Generation Units at Generic Resource LLC is |  |  | 0
● | Total Number of Modeled Loads at Generic Resource LLC is
● | Total Capacity of the Modeled Load at Generic Resource LLC is |  |  | 0 | 0
● | Total Number of Reactive Devices at Generic Resource LLC is
● | Total Capacity of Reactive Devices at Generic Resource LLC is |  |  | 0
● | Generic Resource LLC is located in the following county or counties.
● | The Point Of Interconnection (POI) TSP for Generic Resource LLC is
● | The POI Station Code (Mnemonic) for Generic Resource LLC is
● | The POI Voltage Level at Generic Resource LLC is |  |  | 0
● | The POI Segment Length at Generic Resource LLC is |  |  | 0
● | Generic Resource LLC Part 1 Notes:
If needed, please use this "Notes" area to describe your Reactive Devices or to describe your Combined-Cycle Configurations.
● | Status of required integration engineering studies for Generic Resource LLC (Reactive Capability, Sub-synchronous Oscillation, and others as required by TSP and/or ERCOT).

## Controls S2
Commissioning Plan |  |  |  | Commissioning Plan |  |  |  | Commissioning Plan
|  | Resource Site Name: | Generic Resource LLC |  |  | Resource Site Name: | Generic Resource LLC |  |  | Resource Site Name: | Generic Resource LLC
Commissioning Plan Section 2 (Panel 1 of 3): Resource Site Controls |  |  |  | Commissioning Plan Section 2 (Panel 2 of 3): Resource Site Controls |  |  |  | Commissioning Plan Section 2 (Panel 3 of 3): Resource Site Controls
● | Site Control System |  |  | ● | Volatage Control from the Automatic Volatge Regulator (AVR) |  |  | ● | Power System Stabilizers (PSS)
| ○ | What is the in service date for the Site Control System at Generic Resource LLC? |  |  | ○ | What is the in service date for the AVR at Generic Resource LLC? |  |  | ○ | What is the in service date for the PSS at Generic Resource LLC?
Only Wind and Solar Resources are required to complete this box.
|  | Describe the Site Control System at Generic Resource LLC. |  |  | ○ | Describe what specific units will provide AVR capability at Generic Resource LLC? |  |  | ○ | Describe what specific units will provide PSS capability at Generic Resource LLC?
Only Wind and Solar Resources are required to complete this box.
| ○ | Describe the availability of Site Control System at Generic Resource LLC. Include limitations of the system from initial synchronization through final commercial operations. |  |  | ○ | Describe the availability of the AVR at Generic Resource LLC. Include limitations of the AVR from initial synchronization through final commercial operations. |  |  | ○ | Describe the PSS qualfication testing at Generic Resource LLC?
Only Wind and Solar Resources are required to complete this box.
● | Speed Contol or Primary Frequency Response (PFR) |  |  |  | ○ | Describe the AFR qualfication testing at Generic Resource LLC?
| ○ | What is the in service date for the PFR at Generic Resource LLC? | [5 empty] | ● | Generic Resource LLC Part 2 Notes:
| ○ | Describe what specific units will provide PFR capability at Generic Resource LLC?
[5 empty] | ○ | Describe the Reactive (Leading & Lagging) qualfication testing at Generic Resource LLC?
| ○ | Describe the PFR qualfication testing at Generic Resource LLC?

## Shut-down & Telemetry S3-S4
Commissioning Plan
|  | Resource Site Name: | Generic Resource LLC
|  | Resource Entity Name: | Generic Resource (RE)
|  | Resource QSE Name: | Generic Resource (QSE)
Commissioning Plan Section 3: Resource Site Shut-down Sequences
● | By completing and submitting to ERCOT this Commissioning Plan Generic Resource LLC and Generic Resource (QSE) acknowledge the requirement in the ERCOT Operating Guides, Section 2.2.10(4) that requires on-line Generation Resources to commence shutdown sequence within five minutes of receipt of a Dispatch Instruction from ERCOT.
If, during the commissioning of Generic Resource LLC, ERCOT provides an urgent Dispatch Instruction to reduce generation or remove the generator(s) from synchronization with ERCOT Transmission Grid, Generic Resource LLC will accelerate the shutdown sequence to comply with the time required in the Dispatch Instruction.
● | Orderly Shut-down at Generic Resource LLC will take place in |  |  | 0
● | Emergency Shut-down at Generic Resource LLC will take place in |  |  | 0
Commissioning Plan Section 4: Resource Site Telemetry Verification
● | Describe how the Generic Resource (QSE) and the Generic Resource (RE) will confirm telemetry quality during the entire Commissioning Plan through validation, monitoring performance, and troubleshooting.

## Milestones S5
Commissioning Plan | [6 empty] | Commissioning Plan
| Resource Site Name: |  |  | Generic Resource LLC |  |  |  | Resource Site Name: |  |  | Generic Resource LLC
Commissioning Plan Section 5 (Panel 1 of 2): Resource Site Commissioning Milestones | [6 empty] | Commissioning Plan Section 5 (Panel 2 of 2): Resource Site Commissioning Milestones
Commissioning Activity | Planned Dates | Unit A | Unit B | Unit C | Unit D | Unit E | Commissioning Activity | Planned Dates | Unit F | Unit G | Unit H | Unit I | Unit J
MW Value per Unit at Resource Site | [6 empty] | MW Value per Unit at Resource Site
Model Ready Date | [6 empty] | Model Ready Date
Site telemetry quality verification completed | [6 empty] | Site telemetry quality verification completed
Checklist Part 1 submitted | [6 empty] | Checklist Part 1 submitted
Planned Energization | [6 empty] | Planned Energization
Checklist Part 2 submitted | [6 empty] | Checklist Part 2 submitted
Planned Synchronization | [6 empty] | Planned Synchronization
PFR capability in service date for unit (_) | [6 empty] | PFR capability in service date for unit (_)
AVR/VSS capability in service date for unit (_) | [6 empty] | AVR/VSS capability in service date for unit (_)
PSS capability in service date for unit (_) | [6 empty] | PSS capability in service date for unit (_)
Reactive Device (_) with | [6 empty] | Reactive Device (_) with
(_ MVAR) in service date | [6 empty] | (_ MVAR) in service date
Plant Control System (MW & MVAr output controls) in service date | [6 empty] | Plant Control System (MW & MVAr output controls) in service date
Lead reactive capability testing for Part 3 requirements | [6 empty] | Lead reactive capability testing for Part 3 requirements
Lag reactive capability testing for Part 3 requirements | [6 empty] | Lag reactive capability testing for Part 3 requirements
AVR testing for Part 3 requirements | [6 empty] | AVR testing for Part 3 requirements
PFR testing for Part 3 requirements | [6 empty] | PFR testing for Part 3 requirements
Checklist Part 3 submitted | [6 empty] | Checklist Part 3 submitted
Planned Part 3 approval | [6 empty] | Planned Part 3 approval

## Schedule S6
Commissioning Plan | [11 empty] | Commissioning Plan
|  |  | Resource Site Name: |  |  |  |  | Generic Resource LLC | [6 empty] | Resource Site Name: |  |  |  |  | Generic Resource LLC
Commissioning Plan Section 6 (Panel 1 of 4): Resource Site Detailed Commissioning Schedule | [11 empty] | Commissioning Plan Section 6 (Panel 2 of 4): Resource Site Detailed Commissioning Schedule
Day | Date | # of Units | Connected Unit MW | Connected Unit MVA | PFR on AUTO | AVR on AUTO | Unit max. Leading MVAr under auto control | Unit max. Lagging MVAr under auto control | Cap Bank MVAr available | Reactor MVAr available | STATCOM/DVAR/SVC MVAr available on auto control | Day | Date | # of Units | Connected Unit MW | Connected Unit MVA | PFR on AUTO | AVR on AUTO | Unit max. Leading MVAr under auto control | Unit max. Lagging MVAr under auto control | Cap Bank MVAr available | Reactor MVAr available | STATCOM/DVAR/SVC MVAr available on auto control
[11 empty] | DVAR/SVC MVAr available on auto control | [11 empty] | DVAR/SVC MVAr available on auto control
Commissioning Plan | [11 empty] | Commissioning Plan
|  |  | Resource Site Name: |  |  |  |  | Generic Resource LLC | [6 empty] | Resource Site Name: |  |  |  |  | Generic Resource LLC
Commissioning Plan Section 6 (Panel 3 of 4): Resource Site Detailed Commissioning Schedule | [11 empty] | Commissioning Plan Section 6 (Panel 4 of 4): Resource Site Detailed Commissioning Schedule
Day | Date | # of Units | Connected Unit MW | Connected Unit MVA | PFR on AUTO | AVR on AUTO | Unit max. Leading MVAr under auto control | Unit max. Lagging MVAr under auto control | Cap Bank MVAr available | Reactor MVAr available | STATCOM/DVAR/SVC MVAr available on auto control | Day | Date | # of Units | Connected Unit MW | Connected Unit MVA | PFR on AUTO | AVR on AUTO | Unit max. Leading MVAr under auto control | Unit max. Lagging MVAr under auto control | Cap Bank MVAr available | Reactor MVAr available | STATCOM/DVAR/SVC MVAr available on auto control
[11 empty] | DVAR/SVC MVAr available on auto control | [11 empty] | DVAR/SVC MVAr available on auto control

## Capabilites S7
Commissioning Plan |  |  |  | Commissioning Plan
|  | Resource Site Name: | Generic Resource LLC |  |  | Resource Site Name: |  | Generic Resource LLC
[6 empty] | Resource QSE Name: |  | Generic Resource (QSE)
Commissioning Plan Section 7 (Panel 1 of 2): Resource Site Design Capabilities
Commissioning Plan Section 7 (Panel 2 of 2): Resource Site Design Capabilities
● | In accordance with Protocol Section 16.5(4), ERCOT reviews facility design capability. The current capabilities reviewed by ERCOT are listed in this section. ERCOT recommends that the Generic Resource LLC Commissioning Plan provides sufficient detail to help ERCOT evaluate fully the capabilities that will be available during the entire Commissioning Plan.
|  |  |  | ● | Confirm Generic Resource LLC has an AVR included in its design and that the AVR can be operated in voltage control mode.
[5 empty] | Comments: |  |  | Protocol Section 3.15.3 & 3.15(5)
Describe response times in accordance with ERCOT Nodal Operating Guides Section 2.2.10.
● | Confirm Generic Resource LLC will produce ±0.95 Power Factor Reactive at all MW levels between LSL and HSL.
| Comments: |  | Protocol Section 8.1.1.2.1.4 | ● | Confirm the reactive capability at Generic Resource LLC is based upon the ability to deliver to the High Side of the Step-Up transformer.
[5 empty] | Comments: |  |  | Protocol Section 3.15(3)
● | Confirm Generic Resource LLC has a Power System Stabilizer or equivalent included in its design.
| Comments: |  | Protocol Section 3.15.3(4)
|  |  |  | ● | Confirm Generic Resource LLC is able to receive controls signals from the Generic Resource (QSE) in an upward and downward direction. This is normally referred to as AGC.
[5 empty] | Comments: |  |  | Protocol Section 8.1.1.2.1.1 & 8.1.1.4.1(7-8)
● | Confirm Generic Resource LLC will provide Frequency Response.
| Comments: |  | Protocol Section 8.5.1.1 & 8.5.1.3
|  |  |  | ● | Confirm the under-frequncy relays installed at Generic Resource LLC meet the requirements in the ERCOT Operating Guides.
● | Confirm Generic Resource LLC will dynamically provide Voltage Regulation. |  |  |  | Comments: |  |  | Operating Guide Section 2.6.2
| Comments: |  | Protocol Section 3.15
● | Confirm the breaker interruption capability at Generic Resource LLC is suitable to fault duty. |  |  |  |  | Frequency Range | Delay to Trip
| Comments: |  |  |  |  | Above 59.4 Hz | No automatic tripping (Continuous operation)
[6 empty] | Above 58.4 Hz up to And including 59.4 Hz | Not less than 9 minutes
● | Confirm the transient volatage ride through at Generic Resource LLC. |  |  |  |  | Above 58.0 Hz up to And including 58.4 Hz | Not less than 30 seconds
| Comments: |  | Operating Guide Section 2.9
[6 empty] | Above 57.5 Hz up to And including 58.0 Hz | Not less than 2 seconds
[6 empty] | 57.5 Hz or below | No time delay required
● | Confirm Generic Resource LLC can respond to changes in the voltage profile.
| Comments: |  | Protocol Section 3.15

## Notes S8
Commissioning Plan
|  | Resource Site Name: | Generic Resource LLC
Commissioning Plan Section 8: Process Notes and Descriptions
● | Process notes and descriptions for the commissioning of Generic Resource LLC.

## Instructions
Instructions ● Please complete all 8 Parts to this commissioning plan before emailing it to your ERCOT Client Services Representative. Once your ERCOT Client Services Representative has received your completed plan, then an internal ERCOT meeting will be schedule to review (and possibly approve) your plan. ● Section 1: To complete most fields in Part 1, please use information directly from your RARF. RE should include "(RE)" at the end of the name. QSE should include "(QSE)" at the end of the name. ● Section 2: There are 3 panels/pages to complete on this tab. ● Section 3: None as of this draft. ● Section 4: None as of this draft. ● Section 5: There are 2 panels/pages to complete (if necessary) on this tab. Replace the unit names in row 2 on both panels/pages with the actual unit names at the Resource Site from your RARF. ● Section 6: There are 4 panels/pages to complete (if necessary) on this tab. The "Day" column should be used to number the event days (Example: 1 through 10). This will be used in case of delays during the plan to reference approximately how many days are left to complete the plan even though the dates in the next column may no longer apply. ● Section 7: There are 2 panels/pages to complete on this tab. ● Section 8: None as of this draft. ● Note: Many things on this form will be locked. If you need more room or choices on this form please consult with your ERCOT Client Services Representative.
Resource Categories
Biomass
Coal and Lignite
Combined Cycle
Diesel
Gas Steam
Hydro
Nuclear
Simple Cycle
Solar
Wind