|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report September 2014 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 236 active generation interconnection requests totaling over 64,700 MW. This includes over 25,800 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $393.6 Million. - Transmission Projects endorsed in 2014 total $754.4 Million. - All projects (in engineering, routing, licensing and construction) total approximately $4.98 Billion. - Transmission Projects energized in 2014 total about $438.2 Million. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

2.	Regional Planning Group Project Reviews	1

3.	Asynchronous Tie Interconnection	2

4.	Planning Model Activities	3

5.	Other Notable Activities	3

# 1.	Generation Interconnection

Generator interconnection information has been moved to the Generator Interconnection Status (GIS) Report, which is published monthly under the Grid Information / Resource Adequacy section of the ercot.com website.  Please  see the exact web link below.

http://www.ercot.com/gridinfo/resource/index

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

# Regional Planning Group Project Reviews

- Sharyland has submitted the Brady Area project. This is a Tier 2 project that is estimated to cost $18 million. This project is currently under ERCOT independent review.

- AEPSC has submitted the Brady Area Improvements project. This is a Tier 2 project that is estimated to cost $26.5 million. This project is currently under ERCOT independent review.

- Duke-American Transmission Company has submitted the Phoenix project. This is a Tier 2 project that is estimated to cost $39 million. This project is currently under ERCOT independent review.

- CPS Energy and LCRA Transmission Services Corporation (TSC) have jointly submitted the Transmission System Additions project to address the reliability needs in the northeast San Antonio area. This is a Tier 1 project that is estimated to cost $237.3 million. This project is currently under ERCOT independent review.

- CenterPoint Energy has submitted the Jones Creek project. This is a Tier 1 project that is estimated to cost $79.8 million. This project is currently under ERCOT independent review.

- Sharyland has submitted the North Loop Load Integration project. This is a Tier 2 project that is estimated to cost $11 million. This project is currently under ERCOT independent review.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

The short term calendar of major planning model events follows:

- Jul 23, 2014	Started 15DSB case build

- Oct 10, 2014	Post 15DSA updates and 15DSB Cases and MODTPIT

- Oct 29, 2014	Post Contingency Definitions and Planning Data Dictionary

- Dec 5, 2014	Complete Transmission Loss Factors

The following table shows updates since last month of interconnection projects that met Planning Guide section 6.9 (1) and were either modeled or not modeled based on submitted RARF data in accordance with Planning Guide section 6.9 (2).  A non-null value in the Project ID column signifies that the project was modeled and a null value means it was not modeled.  The Notes column may provide further explanation.

# Other Notable Activities

- ERCOT’s economic analysis of the 2014 Regional Transmission Plan (RTP) is underway. The initial N-1 SCOPF, G-1+N-1 and X-1+N-1 reliability analyses are complete.

- ERCOT's 2014 Long Term System Assessment (LTSA) study is in progress. ERCOT staff is currently working on reliability analysis for the “Current Trends” scenario of the LTSA.

- ERCOT is currently analyzing the reliability impact of the Frontera plant switching out of the ERCOT grid in 2015 and 2016.