## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
November 6, 2014

## Slide 2: 2014 Project Update – Agenda
  Project Portfolio Update p. 3-7
    Recent/Upcoming Project Highlights
    Planning Next Set of Project Bundles
    2014 Release Targets
    2015 Release Targets
    2014 Project Spending Update
  Appendix
    Project Portfolio Gantt Chart p. 9-18
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent/Upcoming Project Highlights
2014 Release 5 Off-Cycle Go-Live (October 2014) Complete
  Planning Site Transition to MIS
    10/16 go-live -- POI to be decommissioned on 11/20
    Includes:
      NPRR622 – Replace Planning and Operations Information Website References with MIS
      PGRR036 – Planning Market Data Transparency
  NPRR527 – Required Combined Cycle Telemetry for Operational Awareness and PDCWG Analysis
    11/1 go-live
2014 Release 6 Go-Lives (December 2014) In-Flight
  Settlement System Upgrade
  Electronic Crisis Communications Enhancements
  NPRR467 – Balancing Account Resettlement Due to DAM Resettlement
  NPRR619 – Minimum Quantity for DAM PTP Obligation Bids (O&M effort)
  NPRR580 – Establishment of a Rolling CRR Balancing Account Fund
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Planning Next Set of Project Bundles
CMM Start = July 2014
  NPRR559 - Revisions to MCE Calculation
  SCR778 - Credit Exposure Calculations for NOIE Options Linked to RTM PTP Obligations
  NPRR597 - Utilize Initial Estimated Liability (IEL) Only During Initial Market Activity
  NPRR601 - Inclusion of Incremental Exposure in Mass Transitions to Counter-Parties that are Registered as QSEs and LSEs and Provide POLR Service
CRR Start = July 2014
  SCR777 - Bilateral CRR Interface Enhancement
MMS / CDR / MIS Start = July 2014
  NPRR500 - Posting of Generation that is Off but Avail.
  NPRR543 - Message for Confirmed E-Tags
  SCR775 - Posting Results of Real-Time Data in a Display Format
Market input on this plan is greatly appreciated!
Initiated
Initiated
Initiated
Initiated
Pending further discussion
EMS Start = November 2014
  NPRR573 - Alignment of PRC Calculation
  NPRR581 - Add FRRS as a Subset of Regulation Svc
  NPRR524 - Resource Limits in Providing A/S
  NPRR272 - Definition and Participation of QSGRs
MMS Start = August 2014
  NPRR626 - Reliability Deployment Price Adder
    Includes NPRR665, NPRR644,
    and NPRR598
  Other release candidates still being assessed
    OFF10/OFF30 (remaining NPRR568 gray-box)
    OBD for Shadow Price Caps
      Revision to “Methodology for Setting the Constraint Shadow Price Cap for a Constraint that is Irresolvable in SCED”
    NPRR595, NPRR645 and SCR785 (all pending approval)
Registration Start = November 2014
  NPRR588 - Clarifications for PV Generation Resources
  NPRR615 - PVGR Forecasting
  NPRR519 - Collateral Exemption for ERS-Only QSEs
  SCR771 - Independent Master QSE for Split Generation
Pending further discussion

## Slide 5: 2014 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
None
January
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR425(b) – GREDP, EIS portions
NPRR589(a) – MMS portion
SCR756(b) – Remaining portions of SCR
SCR774(a) – All new fields except Comments
(a), (b), etc. indicates multiple phases
None
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
ü
ü
ü
Release Approach | Release 1 2/3 – 2/7 | Release 2 4/14 – 4/18 | Release 3 6/9 – 6/13 | Release 4 7/28 – 8/1 | Release 5 9/22–9/26 | Release 6 12/8–12/12 | 2014 TBD
On-Cycle | NPRR240 NPRR425(b) NOGRR105 NPRR509 | NPRR564 NPRR570 | NPRR532 NPRR555 | NPRR491 SCR769 SCR756(b) | NPRR485 NPRR571 NPRR586 SCR774(a) | NPRR467 NPRR580 NPRR619 | 
Off-Cycle | NPRR416 NPRR575 |  | NPRR568 NPRR589(a) |  | NPRR527 |  | 
Counts Total = 23 | 6 | 2 | 4 | 3 | 5 | 3 | 0
6/1
11/1
Retail: 2/22-2/23
Retail: 8/17
ü
ü
ü
2015
ü
ü
E
E
E
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
ü

## Slide 6: 2015 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portion of NPRR
NPRR589(b) – S&B portion
SCR774(b) – Addition of Comments field
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
Release 1 February | Release 2 April | Release 3 June | Release 4 August | Release 5 September | Release 6 December
NPRR519 NPRR543 NPRR556 NPRR559 NPRR597 NPRR601 SCR772 SCR775 SCR777 SCR778 SCR779 | NPRR256 NPRR493 NPRR500 NPRR524 NPRR573 NPRR581 SCR771 | NPRR210 NPRR272 NPRR487 NPRR495 NPRR588 NPRR615 | NPRR256 NPRR553 NPRR568 (remaining gray-box) NPRR626 OBD (Shadow Price Caps) | NPRR484(2) | NPRR419 NPRR439 NPRR556
 | NPRR589(b) | NPRR439 NPRR484(1b) | NOGRR084 SCR774(b) | NPRR327 | NPRR524 NPRR617 NPRR620
10 | 5 | 6 | 5 | 1 | 3
2014
2015 TBD Items (and month they became “TBD”)
June 2014
July 2014
Aug 2014
Oct 2014
NS
I
I
I
I
E
I
P
I
E
NS
P
NS
NS
NS
NS
NS
NS
P
NS
NS
NS
NS
NS
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
H
NS
NS
NS
NS
I
I
Nov 2014

## Slide 7: 2014 Cash Flow Projection – Approved Projects
2014 project budget increased to $26M in October 2014

## Slide 8: Business Integration Update – Appendix
  Appendix
    10/30/2014 Project Gantt
      In-flight items sorted by Project End Date
      “On Hold” projects listed separately
      “Not Started” items sorted by Project Start Date

## Slide 9
Project Portfolio Status – as of 10/30/2014

## Slide 10
Project Portfolio Status – as of 10/30/2014

## Slide 11
Project Portfolio Status – as of 10/30/2014

## Slide 12
Project Portfolio Status – as of 10/30/2014

## Slide 13
Project Portfolio Status – as of 10/30/2014

## Slide 14
Project Portfolio Status – as of 10/30/2014

## Slide 15
Project Portfolio Status – as of 10/30/2014

## Slide 16
Project Portfolio Status – as of 10/30/2014

## Slide 17
Project Portfolio Status – as of 10/30/2014

## Slide 18
Project Portfolio Status – as of 10/30/2014