## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
December 11, 2014

## Slide 2: 2014 Project Update – Agenda
  Project Portfolio Update p. 3-7
    Recent/Upcoming Project Highlights
    Planning Next Set of Project Bundles
    2014 Release Targets
    2015 Release Targets
    2014 Project Spending Update
  Appendix
    Project Portfolio Gantt Chart p. 9-16
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent/Upcoming Project Highlights
2014 Release 6 Go-Lives (December 2014) Complete
  Settlement System Upgrade
  Electronic Crisis Communications Enhancements
  NPRR467 – Balancing Account Resettlement Due to DAM Resettlement
  NPRR619 – Minimum Quantity for DAM PTP Obligation Bids (O&M effort)
  NPRR580 – Establishment of a Rolling CRR Balancing Account Fund
2015 Release Schedule
  Change in approach
    Release Management will no longer refer to releases by number (1, 2, 3, etc.)
    Instead, releases will be named by month (February, April, etc.)
    This reflects our approach to schedule releases as needed and in the most optimal timeslots
    Example: ORDC/Loads in SCED was delivered on 6/1/2014 (not the standard release date but met the timing commitment to the market)
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Planning Next Set of Project Bundles
CMM Start = July 2014
  NPRR559 - Revisions to MCE Calculation
  SCR778 - Credit Exposure Calculations for NOIE Options Linked to RTM PTP Obligations
  NPRR597 - Utilize Initial Estimated Liability (IEL) Only During Initial Market Activity
  NPRR601 - Inclusion of Incremental Exposure in Mass Transitions to Counter-Parties that are Registered as QSEs and LSEs and Provide POLR Service
  NPRR639 – Correction to
  Minimum Current Exposure
CRR Start = July 2014
  SCR777 - Bilateral CRR Interface Enhancement
MMS / CDR / MIS Start = July 2014
  NPRR500 - Posting of Generation that is Off but Avail.
  NPRR543 - Message for Confirmed E-Tags
  SCR775 - Posting Results of Real-Time Data in a Display Format
Market input on this plan is greatly appreciated!
Initiated
Initiated
Initiated
Initiated
Cancel
Defer
EMS Start = November 2014
  NPRR573 - Alignment of PRC Calculation
  NPRR581 - Add FRRS as a Subset of Regulation Svc
  NPRR524 - Resource Limits in Providing A/S
  NPRR272 - Definition and Participation of QSGRs
MMS Start = August 2014
  NPRR626 - Reliability Deployment Price Adder
    Includes NPRR665, NPRR644,
    and NPRR598
  Other release candidates still being assessed
    OFF10/OFF30 (remaining NPRR568 gray-box)
    OBD for Shadow Price Caps
      Revision to “Methodology for Setting the Constraint Shadow Price Cap for a Constraint that is Irresolvable in SCED”
    NPRR595, NPRR645 and SCR785 (all pending approval)
Registration Start = November 2014
  NPRR588 - Clarifications for PV Generation Resources
  NPRR615 - PVGR Forecasting
  NPRR519 - Collateral Exemption for ERS-Only QSEs
  SCR771 - Independent Master QSE for Split Generation
Initiated
Initiated
TBD
Start
Add

## Slide 5: 2014 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
None
January
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR425(b) – GREDP, EIS portions
NPRR589(a) – MMS portion
SCR756(b) – Remaining portions of SCR
SCR774(a) – All new fields except Comments
(a), (b), etc. indicates multiple phases
None
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
ü
ü
ü
Release Approach | Release 1 2/3 – 2/7 | Release 2 4/14 – 4/18 | Release 3 6/9 – 6/13 | Release 4 7/28 – 8/1 | Release 5 9/22–9/26 | Release 6 12/8–12/12 | 2014 TBD
On-Cycle | NPRR240 NPRR425(b) NOGRR105 NPRR509 | NPRR564 NPRR570 | NPRR532 NPRR555 | NPRR491 SCR769 SCR756(b) | NPRR485 NPRR571 NPRR586 SCR774(a) | NPRR467 NPRR580 NPRR619 | 
Off-Cycle | NPRR416 NPRR575 |  | NPRR568 NPRR589(a) |  | NPRR527 |  | 
Counts Total = 23 | 6 | 2 | 4 | 3 | 5 | 3 | 0
6/1
11/1
Retail: 2/22-2/23
Retail: 8/17
ü
ü
ü
2015
ü
ü
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
ü
ü

## Slide 6: 2015 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portion of NPRR
NPRR589(b) – S&B portion
SCR774(b) – Addition of Comments field
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
February | April | June | August | September | December
NPRR519 NPRR543 NPRR559 NPRR597 NPRR601 NPRR639 SCR772 SCR775 SCR777 SCR778 SCR779 | NPRR493 NPRR500 NPRR573 NPRR581 SCR771 SCR779 | NPRR210 NPRR272 NPRR487 NPRR495 NPRR588 NPRR615 SCR774(b) | NPRR256 NPRR553 NPRR568 (remaining gray-box) NPRR626 OBD (Shadow Price Caps) | NPRR484(2) | NPRR419 NPRR439 NPRR556
9 | 6 | 6 | 5 | 1 | 3
2014
2015 TBD Items (and month they became “TBD”)
NS
I
P
P
P
NS
E
I
P
P
E
NS
P
I
I
NS
E
NS
NS
NS
P
NS
NS
NS
NS
NS
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
NS
NS
NS
NS
I
I
E
June 2014 | July 2014 | Aug 2014 | Oct 2014 | Nov 2014 | Dec 2014
NPRR589(b) | NPRR484(1b) | NOGRR084 | NPRR327 H | NPRR524 | NPRR519
 |  | SCR774(b) |  | NPRR617 | NPRR272
 |  |  |  | NPRR620 | SCR777

## Slide 7: 2014 Cash Flow Projection – Approved Projects
2014 project budget increased to $26M in October 2014

## Slide 8: Business Integration Update – Appendix
  Appendix
    11/30/2014 Project Gantt
      In-flight items sorted by Project End Date
      “On Hold” projects listed separately
      “Not Started” items sorted by Project Start Date

## Slide 9
Project Portfolio Status – as of 11/30/2014

## Slide 10
Project Portfolio Status – as of 11/30/2014

## Slide 11
Project Portfolio Status – as of 11/30/2014

## Slide 12
Project Portfolio Status – as of 11/30/2014

## Slide 13
Project Portfolio Status – as of 11/30/2014

## Slide 14
Project Portfolio Status – as of 11/30/2014

## Slide 15
Project Portfolio Status – as of 11/30/2014

## Slide 16
Project Portfolio Status – as of 11/30/2014