## Change Request
CR Tracking Number | Priority ? | Ranking | Short Description | Requestor | Company | Date Requested | Associated Issue # | Disposition by AMWG | Disposition by RMS | Disposition by JDOA | Market Integration Affected? (Y/N) | Testing Required | Production Implementation date
2013 001 | No |  | Report for AMWG Data Monitoring – Data Completeness Measurements | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved for estimation | N | N | TBD - Needs Prioritization
2013 002 | No |  | Reports for AMWG Data Monitoring – Data Timeliness Measurements | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved | N | N | Q2 2014 Delivered
2013 003 | No |  | Reports for AMWG Data Monitoring – Measurement of Percentage of Actual Meter Reads | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved for estimation | N | N | TBD - Needs Prioritization
2013 004 | No |  | Reports for AMWG Data Monitoring – Measurement of Estimates | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved for estimation | N | N | TBD - Needs Prioritization
2013 005 | No |  | Reports for AMWG Data Monitoring – Number of SMT Help Desk Tickets Monthly by Ticket Type | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved | N | N | Q2 2014 Delivered
2013 006 | No |  | Reports for AMWG Data Monitoring – Availability of SMT API | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved | N | N | Q2 2014 Delivered
2013 007 | No |  | Reports for AMWG Data Monitoring – Availability of SMT FTPS | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved | N | N | Q2 2014 Delivered
2013 008 | No |  | Reports for AMWG Data Monitoring – Average Time to Deliver HAN Messages | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved for estimation | N | N | TBD - Needs Prioritization
2013 009 | No |  | Reports for AMWG Data Monitoring – Number of Accounts by Type | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved | N | N | Q2 2014 Delivered
2013 010 | No |  | Reports for AMWG Data Monitoring – Number of Reports Requested by GUI (Portal) and Number of FTPS Accesses | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved for estimation | N | N | TBD - Needs Prioritization
2013 011 | No |  | Average Time from HAN Provision Request to Meter Ready Status | Steve Brightman | Southwest Energy Smarts | 2013-06-10 | Business Question, Req 11, 12 | Submit to RMS for approval | Submit to JDOA for Approval | Approved for estimation | N | N | TBD - Needs Prioritization
2013 012 | No |  | Bypass redundant screen for Users with only one meter when accessing HAN device information | Steve Brightman | Southwest Energy Smarts | 2013-04-30 | 2013-002 | Submit to RMS for approval | Submit to JDOA for Approval | Approved | N | N | Q2 2014 Delivered
2013 013 | No |  | Timeout on SMT takes user to “incorrect login” screen | Steve Brightman | Southwest Energy Smarts | 2013-04-30 | 2013-003 | Submit to RMS for approval | Submit to JDOA for Approval | Approved | N | N | Q2 2014 Delivered
2013 014 | No |  | Allow SMT user to toggle between 15-Minute Reads and Daily Reads without having to reset the date range | John Schatz | TXU Energy | 2013-05-30 | ? | Submit to RMS for approval | Submit to JDOA for Approval | Approved | N | N | Q2 2014 Delivered
2013 015 | No |  | Expand Daily Usage Graph to show 35 days of daily usage on the SMT GUI | John Schatz | TXU Energy | 2013-05-30 | ? | Submit to RMS for approval | Submit to JDOA for Approval | Approved for estimation | N | N | TBD - Needs Prioritization
2013 016 | No |  | Capability for RORs to grant access to vendors on their behalf to the ROR’s customers via API (energy usage, HAN messaging , and HAN provisioning) and FTPS files | Kyle Mille | Big Data Energy | 2013-06-12 | ? | Submit to RMS for approval | Submit to JDOA for Approval | Approved | N | N | Q3 2014 Delivered
2013 017 | No |  | REP API for Energy Usage on SMT Backfill of Historical Usage Data for Existing Customers & Subscription for New Customer Historical Usage | Rob Bevill | Green Mountain Energy | 2013-07-02 | ? | Submit to RMS for approval | Submit to JDOA for Approval | Approved for estimation | N | N | Interim Delivered Q2 2014. Permanent Solution needs Prioritization TBD
2014-018 | No |  | Make generation data viewable on the SMT portal | Rob Bevill/John Schatz | NRG Retail and TXU Energy | 2014-08-26 | 2014-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved for estimation | N | N | Interim Delivered Q2 2014. Permanent Solution needs Prioritization TBD
2014-019 |  |  | Relocate various SMT user guides from the “authenticated” area of SMT to the “unauthenticated” area of SMT | John Schatz | TXU Energy | 2015-01-05 |  |  |  | Pending AMWG Review |  |  | TBD
2014-020 |  |  | Update the Service Address of the Customer Information section of the View/Edit Customer Agreement page | John Schatz | TXU Energy | 2015-01-05 |  |  |  | Pending AMWG Review |  |  | TBD
2014-021 |  |  | 3rd Party Access - Add Customer Type in the Customer Information section of the View/Edit Customer Agreement page | John Schatz | TXU Energy | 2015-01-05 |  |  |  | Pending AMWG Review |  |  | TBD
2014-022 |  |  | Keep selected REP of Record (ROR) visible during customer registration | John Schatz | TXU Energy | 2015-01-05 |  |  |  | Pending AMWG Review |  |  | TBD
2014-023 |  |  | Allow entry of multiple ESI IDs during customer registration process | John Schatz | TXU Energy | 2015-01-05 |  |  |  | Pending AMWG Review |  |  | TBD
2014-024 |  |  | 3rd Party Access - provide the ability within SMT to renew the Energy Data Agreement after the initial agreement duration | John Schatz | TXU Energy | 2015-01-05 |  |  |  | Pending AMWG Review |  |  | TBD
2014-025 |  |  | 3rd Party User Experience – Add identifying data fields in the Report Request Status page | John Schatz | TXU Energy | 2015-01-05 |  |  |  | Pending AMWG Review |  |  | TBD
2014-026 |  |  | Display portal message when report cannot be displayed in the SMT page. | John Schatz | TXU Energy | 2015-01-05 |  |  |  | Pending AMWG Review |  |  | TBD
2014-027 |  |  | Allow specific date entry on the Export Report screen | John Schatz | TXU Energy | 2015-01-05 |  |  |  | Pending AMWG Review |  |  | TBD
2014-028 |  |  | Allow ESIIDs to be copied and pasted into the ESIID box on the Usage page | John Schatz | TXU Energy | 2015-01-05 |  |  |  | Pending AMWG Review |  |  | TBD
2014-029 |  |  | Allow 3rd parties the ability to utilize an API for on-demand data requests/extracts | John Schatz | TXU Energy | 2015-01-05 |  |  |  | Pending AMWG Review |  |  | TBD

## Issues
Issue Tracking Number | Priority ? | Short Description | Requestor | Company | Date Requested | Disposition by AMWG | CR Required | Associated CR #
2014-001 | No | Make generation data viewable on the SMT portal | Rob Bevill/John Schatz | NRG Retail and TXU Energy | 8/18/02014 | Recommended for CR | Yes | 2014-018
2014-02 | ? | Provide another mechanism to send and accept Customer Agreements
2014-03 | ? | Improve TDSP Data / User functionality
2014-04 | ? | Improve Error Messages displayed in SMT Portal