## Slide 1
Project Update
Bundling Options for NPRR626 –
Reliability Deployment Price Adder
January 15, 2015

## Slide 2: Delivery Options for NPRR626
ERCOT evaluated the following delivery options for NPRR626 and other pending related system enhancements
  Option 1
    NPRR626 – Reliability Deployment Price Adder
    NPRR665 – As-Built Clarification of Reliability Deployment Price Adder *
    NPRR568 Phase 2 – Real-Time Reserve Price Adder Based on ORDC
    NPRR644 – Operating Reserve Demand Curve Phase 2 Revisions
    NPRR645 – Real-Time On-Line Capacity Revisions *
    NPRR598 – Clarify Inputs to PRC and ORDC
    OBD – Methodology for Setting Max Shadow Prices
  Option 2
    Option 1 plus:
      NPRR595 – RRS Load Resource Treatment In ORDC
  Option 3
    Multi-phase project
      Option 1 delivered as Phase 1
      NPRR595 delivered as Phase 2
* Pending Board approval in February 2015

## Slide 3: Delivery Options for NPRR626
Estimated delivery dates for each option
  Option 1 – 626/665/568ph2/644/645/598/OBD
    Late June – most likely 6/27-6/28
  Option 2 – 626/665/568ph2/644/645/598/OBD/595
    Early August – most likely 8/8-8/9
  Option 3 – Phased approach
    Phase 1 – 626/665/568ph2/644/645/598/OBD – Late June – most likely 6/27-6/28
    Phase 2 – NPRR595 – Mid-September – most likely 9/12-9/13

## Slide 4: Delivery Options for NPRR626
Why are the estimated delivery dates so close together?
  Only 626/665 require vendor work
  Much of the work on the remaining components can be performed by internal ERCOT staff in parallel with the vendor development
Why isn’t there an estimate for NPRR626 as a stand-alone effort?
  626/665 were originally estimated as a stand-alone option
  After considerable discussion, it was determined that the internal software development for the other components recommended as part of Option 1 could be accomplished without impacting the delivery date of NPRR626

## Slide 5: Delivery Options for NPRR626
Assumptions to meet estimated timelines
  NPRR665 and NPRR645 will be approved by the Board in February
  Market input can be obtained by 1/30
  The MMS/OS Tech Refresh project (scheduled for go-live on 3/26 with an 8 week stabilization period) will stay on schedule and allow the NPRR626 project to enter the integrated testing environment on 5/4
  EMS changes can be accomplished by early Q3 in order to avoid conflict with the in-flight EMS Upgrade project

## Slide 6: Delivery Options for NPRR626
Discussion points
  Which option is most efficient from a resource and funding perspective?
    Option 2 (single project produces maximum efficiencies)
  What are the costs of each option?
    The focus has been on schedule up to this point
    ERCOT will provide cost estimates for each option at PRS

## Slide 7: Delivery Options for NPRR626
Market input is needed in January in order to meet any of the target schedules outlined in this presentation
  Preferred option (1, 2, or 3)
  Any timing requests
    Example – Preferred day of week, time of year, etc.
What is happening while PRS and TAC consider these options?
  NPRR626 will gate to Execution on 1/14/2015
  Based on market input, scope will be added to the in-flight project
Questions?