## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
January 15, 2015

## Slide 2: 2014 Project Update – Agenda
  Project Portfolio Update p. 3-7
    Recent/Upcoming Project Highlights
    In-Flight Project Bundles
    2014 Releases
    2015 Release Targets
    2014 Project Spending Update
  Appendix
    Project Portfolio Gantt Chart p. 9-16
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent/Upcoming Project Highlights
2015 February Release In Flight
  NPRR500 – Posting of Generation that is Off but Available
    Targeted for delivery in February release window (2/2-2/6)
  SCR772 – New Extract for Five Minute Interval Settlement Data
    Targeted for delivery on 2/12
NPRR626 – Reliability Deployment Price Adder
  Upcoming discussion on delivery options
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: In-Flight Project Bundles
CMM Started in July 2014
  NPRR559 - Revisions to MCE Calculation
  SCR778 - Credit Exposure Calculations for NOIE Options Linked to RTM PTP Obligations
  NPRR597 - Utilize Initial Estimated Liability (IEL) Only During Initial Market Activity
  NPRR601 - Inclusion of Incremental Exposure in Mass Transitions to Counter-Parties that are Registered as QSEs and LSEs and Provide POLR Service
  NPRR639 – Correction to Minimum Current Exposure
CRR Started in July 2014
  SCR777 - Bilateral CRR Interface Enhancement
MMS / CDR / MIS Started in July 2014
  NPRR500 - Posting of Generation that is Off but Avail.
  NPRR543 - Message for Confirmed E-Tags
  SCR775 - Posting Results of Real-Time Data in a Display Format
Market input on this plan is greatly appreciated!
Planning
Planning / Execution
On Hold
EMS Started in November 2014
  NPRR573 - Alignment of PRC Calculation
  NPRR581 - Add FRRS as a Subset of Regulation Svc
  NPRR617 not able to be worked into
  this release
MMS Started in August 2014
  NPRR626 - Reliability Deployment Price Adder
    Includes NPRR665, NPRR644,
    and NPRR598
  Other release candidates still being assessed
    OFF10/OFF30 (remaining NPRR568 gray-box)
    OBD for Shadow Price Caps
      Revision to “Methodology for Setting the Constraint Shadow Price Cap for a Constraint that is Irresolvable in SCED”
    NPRR595 RRS Load Resource Treatment In ORDC
    NPRR645 Real-Time On-Line Capacity Revisions (pending approval)
Registration Started in November 2014
  NPRR588 - Clarifications for PV Generation Resources
  NPRR615 - PVGR Forecasting
  NPRR210 – Wind Forecasting to P50
Planning
Initiated
Initiated
Need Input
Feb
June
June
Update
Apr
Apr
Apr
Apr
June

## Slide 5: 2014 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
None
January
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR425(b) – GREDP, EIS portions
NPRR589(a) – MMS portion
SCR756(b) – Remaining portions of SCR
SCR774(a) – All new fields except Comments
(a), (b), etc. indicates multiple phases
None
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
ü
ü
ü
Release Approach | Release 1 2/3 – 2/7 | Release 2 4/14 – 4/18 | Release 3 6/9 – 6/13 | Release 4 7/28 – 8/1 | Release 5 9/22–9/26 | Release 6 12/8–12/12 | 2014 TBD
On-Cycle | NPRR240 NPRR425(b) NOGRR105 NPRR509 | NPRR564 NPRR570 | NPRR532 NPRR555 | NPRR491 SCR769 SCR756(b) | NPRR485 NPRR571 NPRR586 SCR774(a) | NPRR467 NPRR580 NPRR619 | 
Off-Cycle | NPRR416 NPRR575 |  | NPRR568 NPRR589(a) |  | NPRR527 |  | 
Counts Total = 23 | 6 | 2 | 4 | 3 | 5 | 3 | 0
6/1
11/1
Retail: 2/22-2/23
Retail: 8/17
ü
ü
ü
2015
ü
ü
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
ü
ü

## Slide 6: 2015 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portion of NPRR
NPRR589(b) – S&B portion
SCR774(b) – Addition of Comments field
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
February 2/2 – 2/6 | April 3/23 – 3/27 | June 6/8 – 6/12 | August 8/10 – 8/14 | Sept. / Oct. Dates TBD | December Dates TBD
NPRR500 NPRR543 NPRR559 NPRR597 NPRR601 NPRR639 SCR772 SCR775 SCR778 | NPRR493 NPRR500 NPRR559 NPRR573 NPRR581 NPRR597 NPRR601 SCR771 SCR778 SCR779 | NPRR210 NPRR487 NPRR495 NPRR543 NPRR588 NPRR589(b) NPRR615 NPRR639 SCR774(b) SCR775 | NPRR256 NPRR553 NPRR568 (remaining gray-box) NPRR626 OBD (Shadow Price Caps) | NPRR484(2) | NPRR419 NPRR439 NPRR553 NPRR556
2 | 9 | 10 | 4 | 1 | 4
2014
2015 TBD Items (and month they became “TBD”)
E
E
NS
P
I
I
P
P
I
P
E
NS
NS
P
NS
NS
NS
NS
NS
NS
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
NS
NS
NS
I
I
I
NS
E
I
I
June 2014 | July 2014 | Aug 2014 | Oct 2014 | Nov 2014 | Dec 2014
NPRR589(b) | NPRR484(1b) | NOGRR084 | NPRR327 H | NPRR524 | NPRR519
 |  |  |  | NPRR617 | NPRR272
 |  |  |  | NPRR620 | SCR777
NPRR626 may be moved based on PRS/TAC input

## Slide 7: 2014 Cash Flow Results – Approved Projects
2014 project budget increased to $26M in October 2014

## Slide 8: Business Integration Update – Appendix
  Appendix
    12/31/2014 Project Gantt
      In-flight items sorted by Project End Date
      “On Hold” projects listed separately
      “Not Started” items sorted by Project Start Date

## Slide 9
Project Portfolio Status – as of 12/31/2014

## Slide 10
Project Portfolio Status – as of 12/31/2014

## Slide 11
Project Portfolio Status – as of 12/31/2014

## Slide 12
Project Portfolio Status – as of 12/31/2014

## Slide 13
Project Portfolio Status – as of 12/31/2014

## Slide 14
Project Portfolio Status – as of 12/31/2014

## Slide 15
Project Portfolio Status – as of 12/31/2014

## Slide 16
Project Portfolio Status – as of 12/31/2014