## Sheet1
TX SET Meeting Notes / Action Items
December 16th - 17th 2014
Agenda Item: | Decision / Resolution | Action Items :
November 2014 Meeting Notes | No changes were made to the notes. | The Texas SET Chair will have these posted to the November 16th meeting page.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
ERCOT Market Testing--Update • Script Review--Finalize updates to Script pack • Verify 2015 Day 1 Sim Date--01/12/2015 • Continue TMTP Review | • Texas SET reviewed the Scripts and made adjustments where needed in order to finalize the document. • All TDSPs agreed to January 12th 2015 as the Day 1 SIM Date. | • ERCOT sent the finalized scripts to the Texas SET Chair and will post to the ERCOT Market Testing webpage. • The Texas SET Chair will send the finalized document to the list serve.
668NPRR-01 Updates to Texas SET Implementation Guide Process--RMS update | • Texas SET reviewed and modified the language in the NPRR. • Texas SET also reviewed and updated the Texas SET Working Group Procedures to further support NPRR668. o Sections 8, 9 and 10 were removed and placed in the Texas SET Implementation Guides Revision Process document. o The revision process document was renamed to Texas SET Implementation Guides Change Control Process. | • The Texas SET Chair will send the NPRR668 Texas SET comments to ERCOT to post to the market. • The Texas SET Chair will send the changes to the Texas SET Working Group Procedures and the Texas SET Implementation Guides Revision Process to the list serve. o Texas SET will review and finalize these changes at the January meeting.
CBCI File validations—RMGRR126 RMS Update | The Texas SET Chair updated the group on the RMS vote to table the IA for one month to allow ERCOT time to modify the IA.
Flight 1014 Testing Update | ERCOT presented the final Flight 1014 update and reviewed the schedule for Flight 0215.
Issue 2014-I139: Would like to discuss how Critical Care (CC) status re-establishes itself for a customer after an IAG has occurred--Review RMG Changes | Texas SET reviewed the draft RMGRR submitted by NRG / Reliant and recommended that the changes be submitted to RMS for approval. | • The Texas SET Chair will submit the draft RMGRR to ERCOT Market Rules for review and updates. • The chair will subsequently submit the RMGRR to the Revision Request group for a number; then have the RMGRR submitted and posted for the January 6th RMS meeting.
• Tariff Project 41121--RMG Section 7 Market Processes updates related to TDSP tariff changes effective Jan 2015 • Safety Net timelines—add to matrix • Other items—TXU RMG Comments for potential discussion and changes review | • Texas SET reviewed and made final changes to the Timeline matrix. • Texas SET reviewed the TXU comments placed in Section 7 Market Process of the Retail Market Guide. • It was noted that changes to the Safety Net timelines will be delayed until Texas SET can seek RMS direction regarding §25.487. Obligations Related to Move-In Transactions of the PUCT Customer Protection Rules. o The rule provides explicit language regarding Safety Net submission timelines. | The Texas SET Chair will send the changes made to Section 7 Market Process of the Retail Market Guide to the list serve for review and request direction from RMS regarding the Safety Net timelines at the January 6th RMS meeting.
Other Business
Texas SET 2015 Meeting Date Schedule | The Texas SET Chair presented the 2015 meeting dates. | The Texas SET Chair will send the schedule to the list serve.
Texas SET Release Discussion | Texas SET agreed that there are approved change controls that have not been implemented in a new Texas SET Release. The group agreed that the subject will be presented to the February RMS meeting at the same time as the Texas SET 2014 Accomplishments / 2015 Goals. | The Texas SET Chair will begin creating the 2014 Accomplishments and 2015 Goals for the group to review at the Janaury meeting.
Texas SET Procedures Document | Texas SET agreed that the Texas SET Procedures document will need to be reviewed for further changes in the near future in order to incorporate the RMS assignments generated from the Sharyland Transition Task Force Lessons Learned.
REP Certification Matrix—Long-term solution | On hold
• RMS assignments--On Hold
• New Entrant Documentation—Procedures and Documentation Location o Method used to create ESI IDs o Method used to create 867_03 data for unmetered services o Difference between methods to update Premise Type and POLR Class in ERCOT system o Cycle assignments for unmetered services o Data updates required to align with loaded read dates at ERCOT o Use of TDSP supplemental address field | Discussion is delayed until next month
• Add STTF Transition Documents (Lessons Learned) to key documents | Discussion is delayed until next month
• Add Master Customer List (MCL) guide back to the Texas SET Guides | Discussion is delayed until next month
Next Meeting | January 21st - 22nd Rm 168 ERCOT Met Center
Attendees
Kathryn Thurman ERCOT | Becky Taylor CNP | George Esparza ONCOR
Ed Echols ONCOR | Carolyn Reed CNP | Kathy Scott CNP
Paul Yockey ERCOT | Greg Huckabee ONCOR | Diana Rehfeldt TNMP
Kaci Jacobs TXU | Kyle Patrick NRG / Reliant
WebEx:
Amy Raferty ESG | Norm Levine Direct Energy | Roger Tenebown Aurea
Gricelda Calzada AEP | Dave Louder NEC | Sandra Tindall ERCOT
Ivan Velasquez ONCOR | Paula Shadle NEC | Suzy Clifton ERCOT
Mike Woolsey ONCOR