## Slide 1
Project Update
Bundling Options for NPRR626 –
Reliability Deployment Price Adder
January 29, 2015

## Slide 2: ERCOT evaluated the following delivery options for NPRR626 and other pending related system enhancements:
Bundling Option | Timing | Cost Est.
Option 1 NPRR626 – Reliability Deployment Price Adder NPRR665 – As-Built Clarification of Reliability Deployment Price Adder * NPRR568 Phase 2 – Real-Time Reserve Price Adder Based on ORDC NPRR644 – Operating Reserve Demand Curve Phase 2 Revisions NPRR645 – Real-Time On-Line Capacity Revisions * NPRR598 – Clarify Inputs to PRC and ORDC OBD – Methodology for Setting Max Shadow Prices | Late June 2015 Likely Date 6/27 – 6/28 | $1.0M
Option 2 Option 1 plus: NPRR595 – RRS Load Resource Treatment In ORDC | Early August 8/8 – 8/9 | $1.1M
Option 3 Multi-phase project Option 1 delivered as Phase 1 NPRR595 delivered as Phase 2 | Ph1 – 6/27-6/28 Ph2 – 9/12-9/13 | $1.2M
* Pending Board approval in February 2015
ü
ß PRS Recommendation

## Slide 3: Delivery Options for NPRR626
Market input is needed in January in order to meet any of the target schedules outlined in this presentation
  Preferred option (1, 2, or 3)
  Any timing requests
    Example – Preferred day of week, time of year, etc.
On 1/15/2015, PRS unanimously voted to recommend Option 3 (multi-phase project)
What is happening while PRS and TAC consider these options?
  NPRR626 gated to Execution on 1/16/2015
  Based on market input, scope will be added to the in-flight project
Questions?

## Slide 4: Delivery Options for NPRR626
Appendix

## Slide 5: Delivery Options for NPRR626
Why are the estimated delivery dates so close together?
  Only 626/665 require vendor work
  Much of the work on the remaining components can be performed by internal ERCOT staff in parallel with the vendor development
Why isn’t there an estimate for NPRR626 as a stand-alone effort?
  626/665 were originally estimated as a stand-alone option
  After considerable discussion, it was determined that the internal software development for the other components recommended as part of Option 1 could be accomplished without impacting the delivery date of NPRR626

## Slide 6: Delivery Options for NPRR626
Assumptions to meet estimated timelines
  NPRR665 and NPRR645 will be approved by the Board in February
  Market input can be obtained by 1/30
  The MMS/OS Tech Refresh project (scheduled for go-live on 3/26 with an 8 week stabilization period) will stay on schedule and allow the NPRR626 project to enter the integrated testing environment on 5/4
  EMS changes can be accomplished by early Q3 in order to avoid conflict with the in-flight EMS Upgrade project