## Slide 1: Overview of ERCOT Outage Coordination
Woody Rickerson
Director Grid Coordination
January 2015

## Slide 2
ERCOT processes approximately 115,000 outages annually
15 dedicated Outage Coordination ftes
Two peak outage seasons
Two off seasons
Peak for 2014 on Nov. 11 – 3481 outages on system
March through May
Oct. through Mid – Dec.

## Slide 3
Some outages are analyzed multiple times
Late arriving outages may only be studied once before being handed off to Real-Time

## Slide 4: Outage Submission Timelines
App
Approval
Target Day
To Start
Outage
TD +45
TD + 30
A
TD+9
TD+4
TD+3
TD+1
Approval
TD + 90
TD + 75
90-day
A
4-day
9-day
45-day
3-d
Resource Outages automatically accepted
Resource Outages Require Approval
Transmission Outages
Resource Outages

## Slide 9: Outage Coordination Timelines
Real Time
12 months in advance, rolling annual outage plan to be submitted
90-120 days in advance NOMCRs due for Operations Model (NOMCRs)
90-day timeline
45-day timeline (Resource)
time
4-day
3-day
9-day timeline
CRR Snapshot
Interim Update NOMCRs
Transmission Outages
Operational Model Changes
CRR Models
Tri-annual Planning Model Updates
Resource Outages

## Slide 10: Outage Coordination Study Process
No Reliability Problems
Reliability Problems
CIM-derived EMS case containing
Date specific Topology
Load Forecast
Starting Gen. Pattern
Contingency file
Wind Scenarios
Previously Approved or Accepted
Resource and Transmission Outages
Outages Awaiting ERCOT Approval
Reject
Approve
Order of Receipt
Coordinate Outages
Modify Gen Pattern

## Slide 11: When Reliability meets Economics
Approximately 75 “High Cost” Outages were identified during the Outage Approval Process in 2014
Questionnaire:
A statement of why the work is required.
Is there a switching solution to reduce market impact?
A statement of what has been done to reduce the length of Outage.
Are you working extended hours? If not, can you submit it daily?
Is this outage scheduled during a reduced load season? If not, please explain the reason.
Can the outage be scheduled during a resource outage that would reduce market impact.

## Slide 12: High Cost Outages
High Cost Outages are subjectively determined by the amount of generation that has changed from an optimal dispatch to resolve reliability violations.
Including 10 in the Rio Grande Valley area (Ajo to Rio Hondo, Lon Hill to North Edinburg, etc.) and 14 in the Houston Import area (Singleton to Tomball, etc.)

## Slide 13: High Cost Outages