|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report December 2014 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 239 active generation interconnection requests totaling over 62,000 MW. This includes over 23,900 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $451.1 Million. - Transmission Projects endorsed in 2014 total $857.3 Million. - All projects (in engineering, routing, licensing and construction) total approximately $5.54 Billion. - Transmission Projects energized in 2014 total about $693.7 Million. - ERCOT installed wind capacity, as reported through the registration process, currently totals 12,470 MW (10,789 MW Non-Coastal and 1,680 MW Coastal). |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

2.	Regional Planning Group Project Reviews	1

3.	Asynchronous Tie Interconnection	2

4.	Planning Model Activities	2

5.	Other Notable Activities	3

# 1.	Generation Interconnection

Generator interconnection information has been moved to the Generator Interconnection Status (GIS) Report, which is published monthly under the Grid Information / Resource Adequacy section of the ercot.com website.  Please  see the exact web link below.

http://www.ercot.com/gridinfo/resource/index

# Regional Planning Group Project Reviews

- Duke-American Transmission Company has submitted the Phoenix project. This is a Tier 2 project that is estimated to cost $39 million. This project is currently under ERCOT independent review.

- CPS Energy and LCRA Transmission Services Corporation (TSC) have jointly submitted the Transmission System Additions project to address the reliability needs in the northeast San Antonio area. This is a Tier 1 project that is estimated to cost $237.3 million. This project is currently under ERCOT independent review.

- CenterPoint Energy has submitted the Jones Creek project. This is a Tier 1 project that is estimated to cost $79.8 million. ERCOT has issued the independent review report on Nov. 13th. ERCOT will present the project to TAC and the Board of Directors for their endorsement.

- Sharyland submitted the North Loop Load Integration project. This is a Tier 2 project that is estimated to cost $11 million. This project has completed the RPG review and ERCOT will send the RPG acceptance letter.

- TNMP submitted the SCLP-Brazoria Line Rebuild Conversion Project. This is a Tier 3 project that is estimated to cost $27 million. This project has completed the RPG review and ERCOT will send the RPG acceptance letter.

- LCRA has submitted the Goldthwaite-Lampasas Line Upgrades Project. This is a Tier 1 project that is estimated to cost $71 million. This project is currently under ERCOT independent review.

- Garland Power & Light (GPL) submitted the Wylie Switch-Firewheel 138 kV line upgrade project. This project has completed the RPG review and ERCOT will send the RPG acceptance letter.

- ONCOR has submitted the Spraberry - Garden City East 138 kV project. This is a Tier 3 project that is estimated to cost $24 million. This project has been submitted for RPG comments.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

The short term calendar of major planning model events follows:

- Dec 30, 2014	NMMS Snapshot for 2015 Update Cycle 1 (update 15DSA and 15DSB)

- Feb 24, 2015	Post 2015 Update Cycle 1 updated cases and MODTPIT

- Mar 13, 2015	Post 2015 Update Cycle 1 Contingency Files and Planning Data Dictionary

The following table shows updates since last month of interconnection projects that met Planning Guide section 6.9 (1) and were either modeled or not modeled based on submitted RARF data in accordance with Planning Guide section 6.9 (2).  A non-null value in the Project ID column signifies that the project was modeled and a null value means it was not modeled.  The Notes column may provide further explanation.

# Other Notable Activities

- The System Protection Working Group has begun building the 2015 Current Year case with a proposed completion date of Mar 27, 2015.

- The 2014 Regional Transmission Plan and the Long Term System Assessment reports are complete. Both study results are posted on the MIS Secure. Public versions of the reports are also available on ERCOT.com

- The 2014 Constraints and Needs report is complete and available on ERCOT.com.

- ERCOT has commenced work on the 2015 Regional Transmission Plan; ERCOT is currently working on preparing the start cases for the reliability analysis phase.