## Cover Sheet
"NERC Standards Watch List" Disclaimer
This NERC Standards Watch List is intended for informational purposes only.
It is simply a tool for use in ERCOT's NERC Reliability Working Group (NRWG).
All of the information contained herein is available publically.
Although it is correct to the best of my knowledge, I cannot guarantee the accuracy of its contents.
If something seems incorrect to you, verify it.
If you know of any errors, please let me know so I can make any necessary corrections.
Lisa Martin
512-322-6457
lisa.martin@austinenergy.com

## Pending Regulatory Approval
NERC Standards Watch List |  |  |  | LEGEND: | Phase Complete
Updated: 2/13/15 |  |  |  |  | New Info
STANDARDS PENDING REGULATORY APPROVAL This list excludes standards that were not approved by FERC in Order 693. Refer to NERC's "pending regulatory approval standards" list.
Project | Standard | Title | Applicable Entities | SAR / Interpretation Request | Industry Stakeholder Process | NERC BOT Approval | NERC Petition for Approval | FERC NOPR | FERC Order | Implementation Plan Summary | Comment
2009-19 | BAL-002-1a | Disturbance Control Performance | BA, Reserve Sharing Groups, RRO | 2009-09-02 | 2012-10-08 | 2012-11-07 | 2013-02-12 | NOPR proposing remand: 5/16/2013 |  |  | Interpretation of R4 & R5; RM13-6
2012-05 | MOD-001-2 | Available Transmission System Capability | TO, TSP (entities operating in ERCOT are exempt) | 2013-09-25 | 2013-12-20 | 2014-02-06 | 2014-02-10 | 2014-06-19 |  |  | MOD A; includes ERCOT exemption; RM14-7-000
2010-04 | MOD-031-1 | Demand Data | PC, TP, BA, RP, LSE, DP | 2013-07-18 | 2014-05-05 | 2014-05-07 | 2014-05-13 | 2014-09-18 |  |  | MOD C; retires MOD-016-1.1, MOD-017-0.1, MOD-018-0, MOD-019-0.1, and MOD-21-1; RM14-12-000
2006-06 | COM-001-2 | Communications | BA, DP, GOP, TOP, RC | 2007-05-01 | 2012-09-17 | 2012-11-07 | 2014-05-14 | 2014-09-18 |  |  | Reliability Coordination; RM14-13-000
2007-02 | COM-002-4 | Operating Personnel Communications Protocols | BA, DP, RC, TOP, GOP | 2007-06-08 | 2014-04-07 | 2014-05-07 | 2014-05-14 | 2014-09-18 |  |  | RM14-13-000
2010-14.1 | BAL-001-2 | Phase 1 Balancing Authority Reliability-Based Controls | BA, Regulation Reserve Sharing Group | originally part of Project 2007-05 & 2007-13 | 2013-07-25 | 2013-08-15 | 2014-04-02 | 2014-11-20 |  |  | RM14-10-000
2010-05.1 | PRC-004-3 | Protection System (Misoperations) | DP, GO, TO | 2011-06-09 | 2014-08-07 | 2014-08-14 | 2014-09-15 |  |  |  | RD14-14-000
2008-02 | PRC-006-2 | Underfrequency Load Shedding | PC, UFLS entities (DP, TO) | 2013-05-23 | 2014-10-31 | 2014-11-13 | 2014-12-15 |  |  |  | Retires PRC-006-1
2007-11 | PRC-002-2 | Disturbance Monitoring | GO, PC, RC, TO | 2013-04-15 | 2014-11-06 | 2014-11-13 | 2014-12-15 |  |  |  | Retires PRC-002-1, PRC-018-1
2007-17.3 | PRC-005-4 | Protection System Maintenance and Testing - Phase 3 (Sudden Pressure Relays) | DP, GO, TO | 2014-02-12 | 2014-10-29 | 2014-11-13 | 2014-12-18 |  |  |  | Retires PRC-005-3
2009-03 | EOP-011-1 | Emergency Operations | BA, RC, TOP | 2013-10-17 | 2014-11-06 | 2014-11-13 | 2014-12-29 |  |  |  | RM15-7; Consolidates and retires EOP-001-2.1b, EOP-002-3.1, EOP-003-2
2010-13.3 | PRC-026-1 | Relay Performance During Stable Power Swings | GO, TO, PC | 2010-08-12 | 2014-12-16 | 2014-12-17 | 2014-12-31 |  |  |  | RM15-8
2013-03 | TPL-007-1 | Transmission System Planned Performance for Geomagnetic Disturbance Failure | GO, PC, TO, TP | 2013-06-21 | 2014-12-16 | 2014-12-17 | 2015-01-21 |  |  |  | RM15-11
2010-05.2 | RAS definition | Special Protection Systems - Phase 2 |  | 2014-02-12 | 2014-11-06 | 2014-11-13 | 2015-02-03 |  |  |  | Petition for approval includes updates in the stds listed in the cell comment
2008-02 | PRC-010-1 | Undervoltage Load Shedding | PC, TP, UVLS entities (DP, TO) | 2013-05-23 | 2014-09-18 | 2014-11-13 | 2015-02-06 |  |  |  | Consolidates and retires PRC-010-0, PRC-020-1, PRC-021-1, PRC-022-1
2014-01 | PRC-004-2.1(i)a | Analysis and Mitigation of Transmission and Generation Protection System Misoperations | DP, GO, TO | 2013-10-01 | 2014-11-06 | 2014-11-13 | 2015-02-06 |  |  |  | Applicability for Dispersed Generation Resources; retires PRC-004-2.1a; RM15-3
2014-01 | PRC-004-4 | Protection System Misoperation Identification and Correction | DP, GO, TO | 2013-10-01 | 2014-11-06 | 2014-11-13 | 2015-02-06 |  |  |  | Applicability for Dispersed Generation Resources; retires PRC-004-3; RM15-3
2014-01 | PRC-005-2(i) | Protection System Maintenance | DP, GO, TO | 2013-10-01 | 2014-09-05 | 2014-11-13 | 2015-02-06 |  |  |  | Applicability for Dispersed Generation Resources; retires PRC-005-2; RM15-3
2014-01 | PRC-005-3(i) | Protection System and Automatic Reclosing Maintenance | DP, GO, TO | 2013-10-01 | 2014-09-05 | 2014-11-13 | 2015-02-06 |  |  |  | Applicability for Dispersed Generation Resources; retires PRC-005-3; RM15-3
2014-01 | VAR-002-4 | Generator Operation for Maintaining Network Voltage Schedules | GO, GOP | 2013-10-01 | 2014-11-06 | 2014-11-13 | 2015-02-06 |  |  |  | Applicability for Dispersed Generation Resources; retires VAR-002-3; RM15-3
2009-22 | COM-002-2a | Communications and Coordination | BA, GOP, TOP, RC | 2009-10-02 | 2011-12-23 | 2012-02-09 |  |  |  |  | Interp re "directives" for emergencies or normal ops
2012-INT-05 | CIP-002-3b | Critical Cyber Asset Identification | All | 2011-02-24 | 2013-01-23 | 2013-02-07 |  |  |  |  | Interp re applicability of R1.2.5 to AMI systems
2012-INT-04 | CIP-007-3b | Interpretation of CIP-007-3 for ITC |  | 2011-12-28 | 2013-09-20 | 2013-11-07
2012-INT-06 | CIP-003-3a | Interpretation of CIP-003-3 for Consumers Energy |  | 2011-06-09 | 2013-09-20 | 2013-11-07
2014-03 | TOP-002-4 | Operations Planning | BA, TOP | 2014-02-12 | 2014-10-22 | 2014-11-13 |  |  |  |  | Revisions to TOP/IRO Standards; retires 19 TOP/IRO stds including PER-001-0.2
2014-03 | TOP-003-3 | Operational Reliability Data | BA, DP, GO, GOP, LSE, TO, TOP | 2014-02-12 | 2014-10-22 | 2014-11-13 |  |  |  |  | Revisions to TOP/IRO Standards; retires 19 TOP/IRO stds including PER-001-0.2
2014-03 | IRO-001-4 | Reliability Coordination – Responsibilities | BA, DP, GO, RC, TOP | 2014-02-12 | 2014-10-20 | 2014-11-13 |  |  |  |  | Revisions to TOP/IRO Standards; retires 19 TOP/IRO stds including PER-001-0.2
2014-03 | IRO-002-4 | Reliability Coordination – Monitoring and Analysis | RC | 2014-02-12 | 2014-10-20 | 2014-11-13 |  |  |  |  | Revisions to TOP/IRO Standards; retires 19 TOP/IRO stds including PER-001-0.2
2014-03 | IRO-008-2 | Reliability Coordinator Operational Analyses and Real-time Assessments | RC | 2014-02-12 | 2014-10-22 | 2014-11-13 |  |  |  |  | Revisions to TOP/IRO Standards; retires 19 TOP/IRO stds including PER-001-0.2
2014-03 | IRO-010-2 | Reliability Coordinator Data Specification and Collection | BA, DP, GO, GOP, LSE, RC, TO, TOP | 2014-02-12 | 2014-10-20 | 2014-11-13 |  |  |  |  | Revisions to TOP/IRO Standards; retires 19 TOP/IRO stds including PER-001-0.2
2014-03 | IRO-014-3 | Coordination Among Reliability Coordinators | RC | 2014-02-12 | 2014-10-22 | 2014-11-13 |  |  |  |  | Revisions to TOP/IRO Standards; retires 19 TOP/IRO stds including PER-001-0.2
2014-03 | IRO-017-1 | Outage Coordination | BA, PC, RC, TO, TOP | 2014-02-12 | 2014-10-22 | 2014-11-13 |  |  |  |  | Revisions to TOP/IRO Standards; retires 19 TOP/IRO stds including PER-001-0.2
2014-02 | CIP-003-6 | Cyber Security – Security Management Controls | All | 2014-03-17 | 2014-11-06 | 2015-02-12 |  |  |  |  | CIP v5 Revisions; retires CIP-003-5
2014-02 | CIP-004-6 | Cyber Security – Personnel & Training | All | 2014-03-17 | 2014-11-06 | 2015-02-12 |  |  |  |  | CIP v5 Revisions; retires CIP-004-5.1
2014-02 | CIP-006-6 | Cyber Security – Physical Security of BES Cyber Systems | All | 2014-03-17 | 2014-11-06 | 2014-11-13 |  |  |  |  | CIP v5 Revisions; retires CIP-006-5
2014-02 | CIP-007-6 | Cyber Security – Systems Security Management | All | 2014-03-17 | 2014-11-06 | 2015-02-12 |  |  |  |  | CIP v5 Revisions; retires CIP-007-5
2014-02 | CIP-009-6 | Cyber Security – Recovery Plans for BES Cyber Systems | All | 2014-03-17 | 2014-11-06 | 2014-11-13 |  |  |  |  | CIP v5 Revisions; retires CIP-009-5
2014-02 | CIP-010-2 | Cyber Security – Configuration Change Management and Vulnerability Assessments | All | 2014-03-17 | 2014-11-06 | 2015-02-12 |  |  |  |  | CIP v5 Revisions; retires CIP-010-1
2014-02 | CIP-011-2 | Cyber Security – Information Protection | All | 2014-03-17 | 2014-11-06 | 2015-02-12 |  |  |  |  | CIP v5 Revisions; retires CIP-011-1
2014-03 | TOP-001-3 | Transmission Operations | BA, DP, GOP, TOP | 2014-02-12 | 2015-01-07 | 2015-02-12 |  |  |  |  | Revisions to TOP/IRO Standards; retires 19 TOP/IRO stds including PER-001-0.2
2014-01 | PRC-001-1.1(ii) | System Protection Coordination |  | 2013-10-01 | 2015-01-22 | 2015-02-12 |  |  |  |  | Applicability for Dispersed Generation Resources; retires PRC-001-1.1
2014-01 | PRC-019-2 | Coordination of Generating Unit or Plant Capabilities, Voltage Regulating Controls, and Protection |  | 2013-10-01 | 2015-01-22 | 2015-02-12 |  |  |  |  | Applicability for Dispersed Generation Resources; retires PRC-019-1
2014-01 | PRC-024-2 | Generator Frequency and Voltage Protective Relay Settings |  | 2013-10-01 | 2015-01-22 | 2015-02-12 |  |  |  |  | Applicability for Dispersed Generation Resources; retires PRC-024-2
Note on G37: Lisa Martin: The initial version, originally approved by NERC BOT on 11/13/2014, was withdrawn and replaced with the current version and approved by the NERC BOT on 2/12/2015; see agenda package for details
Note on G38: Lisa Martin: The initial version, originally approved by NERC BOT on 11/13/2014, was withdrawn and replaced with the current version and approved by the NERC BOT on 2/12/2015; see agenda package for details
Note on G40: Lisa Martin: The initial version, originally approved by NERC BOT on 11/13/2014, was withdrawn and replaced with the current version and approved by the NERC BOT on 2/12/2015; see agenda package for details
Note on G42: Lisa Martin: The initial version, originally approved by NERC BOT on 11/13/2014, was withdrawn and replaced with the current version and approved by the NERC BOT on 2/12/2015; see agenda package for details
Note on G43: Lisa Martin: The initial version, originally approved by NERC BOT on 11/13/2014, was withdrawn and replaced with the current version and approved by the NERC BOT on 2/12/2015; see agenda package for details
Note on L18: Lisa Martin: Petition for approval includes updates in the following stds: EOP-004-3 FAC-010-3 FAC-011-3 MOD-030-3 MOD-029-2a PRC-001-1.1(i) PRC-005-2(ii) PRC-005-3(ii) PRC-012-1 PRC-013-1 PRC-014-1 PRC-015-1 PRC-016-1 PRC-017-1 PRC-023-4 TPL-001-0.1(i) TPL-002-0(i)b TPL-003-0(i)b TPL-004-0(i)a

## Future Enforcement
NERC Standards Watch List |  |  |  |  | LEGEND: | Phase Complete
Updated: 2/13/15 | [5 empty] | New Info
STANDARDS SUBJECT TO FUTURE ENFORCEMENT This list includes standards that have achieved FERC approval
Project | Standard | Title | Enforcement Date | Applicable Entities | SAR | Industry Stakeholder Process | NERC BOT Approval | NERC Petition for Approval | FERC NOPR | FERC Order | Implementation Plan Summary | Comment
2007-17 | PRC-005-2 | Protection System Maintenance | R1, R2 & R5: 4/1/2015 R3 & R4: staggered implementation ranging from 10/1/2015 to 4/1/2027 | DP, GO, TO | 1st SAR 5/7/2007 2nd SAR 8/4/2011 | 2012-10-24 | 2012-11-07 | 2013-02-26 | 2013-07-18 | Issued 12/19/2013 Fed Reg 12/24/2013 Effective 2/24/2014 | R1, R2 & R5: 1st day of 1st cal qtr 12 mo after FERC approval R3 & R4: Staggered as stated in the Implementation Plan | Combines PRC-008, -011, -017 with PRC-005; RM13-7; Order No. 793
2007-12 | BAL-003-1 | Frequency Response | R2, R3 & R4: 4/1/2015 R1: 4/1/2016 | BA | 2007-06-30 | 2012-12-21 | 2013-02-07 | 2013-03-29 | 2013-07-18 | Issued 1/16/2014 Fed Reg 1/23/2014 Effective 3/24/2014 | R2, R3 & R4: 1st day of 1st cal qtr 12 mo after FERC approval R1: 1st day of 1st cal qtr 24 mo after FERC approval | Frequency Response; RM13-11; Order No. 794; Note: R2-R4 are not applicable in the ERCOT Region
n/a | BAL-001-TRE-1 | Primary Frequency Response in the ERCOT Region | Std effective date: 4/1/2014 IMPLEMENTATION PLAN: R1 & R8: 4/1/2015 R2 - R5: 10/1/2015 R6 & R7: 50% compliant by 4/1/2015, 100% compliant by 10/1/2015 R9 & R10: 50% compliant by 4/1/2016, 100% compliant by 10/1/2016 | BA, GO, GOP | n/a | TRE BOT approval: 4/23/2013 | 2013-08-15 | 2013-09-18 | n/a | Issued/Effective: 1/16/2014 | R1 & R8: 1st day of 1st cal qtr 12 mo after FERC approval R2 - R5: 1st day of 1st cal qtr 18 mo after FERC approval R6 & R7: 50% compliant by 1st day of 1st cal qtr 12 mo after FERC approval, 100% compliant by 1st day of 1st cal qtr 18 mo after FERC approval R9 & R10: 50% compliant by 1st day of 1st cal qtr 24 mo after FERC approval, 100% compliant by 1st day of 1st cal qtr 30 mo after FERC approval | RD13-12-000
2013-03 | EOP-010-1 | Geomagnetic Disturbance Mitigation | R1 & R3: 4/1/2015 R2: TBD | RC, TOPs w/ a TOP Area incl pwr xfmr w/ a high side wye-grounded winding w/ terminal voltage >200kV | No date on SAR | 2013-11-04 | 2013-11-07 | 2013-11-14 | 2014-01-16 | Issued 6/19/2014 Fed Reg 6/25/2014 Effective 8/25/2014 | R1 & R3: 1st day of 1st cal qtr 6 mo after FERC approval R2: 1st day following retirement of IRO-005-3.1a | Phase 1 of GMD; RM14-1-000
2010-13.2 | PRC-023-3 | Phase 2 Relay Loadability: Generation | Std effective date: 10/1/2014 IMPLEMENTATION PLAN: R1, R2, R3 (except ckts IDed by PC per R6): 10/1/2014 R1, R2 R3 (for ckts IDed by PC per R6): see Imp Plan R4: 4/1/2015 R5, R6: 10/1/2014 | TO, GO & DP, all with load-responsive phase protection systems described in Attach. A (for DP, the ckts have to have bi-directional flow capabilities) and PC | 2012-11-30 | 2013-09-13 | 2013-11-07 | 2013-12-17 | 2014-03-20 | Issued 7/17/2014 Fed Reg 7/23/2014 Effective 9/22/2014 | Std effective: 1st day of 1st cal qtr after FERC approval Implementation Plan provides a table with specific dates for and within each requirement R1, R2, R3 (except ckts IDed by PC per R6): 1st day of 1st cal qtr after FERC approval R1, R2 R3 (for ckts IDed by PC per R6): see Imp Plan R4: 1st day of 1st cal qtr 6 mo after FERC approval R5, R6: 1st day of 1st cal qtr after FERC approval | Filed as a supplement to the 9/30/2013 PRC-025-1 petition; RM13-19-000 and RM14-3-000; Order No. 799; Retires PRC-023-2 except for Criterion 6 of R1 which remains in effect until the enforcement date of PRC-025-1; Any implementation dates/ milestones established under PRC-023-2 remain in place | http://www.nerc.com/pa/Stand/PRC0233RD/PRC_023_3_Implementation_Plan_CLEAN_2013_08_27.pdf
2010-03 | MOD-032-1 | Modeling Data | R1: 7/1/2015 R2-R4: 7/1/2016 | BA, GO, LSE, PC, RP, TO, TP, TSP | 2012-12-12 | 2013-12-16 | 2014-02-06 | 2014-02-25 | n/a | Issued/Effective: 5/1/2014 | R1: 1st day of 1st cal qtr 12 mo after FERC approval R2-R4: 1st day of 1st cal qtr 24 mo after FERC approval | MOD B; RD14-5-000
2014-04 | CIP-014-1 | Physical Security | 2015-10-01 | TO, TOP | 2014-03-12 | 2014-05-05 | 2014-05-13 | 2014-05-23 | 2014-07-17 | Issued 11/20/2014 Fed Reg 11/25/2014 Effective 1/26/2015 | 1st day of the 1st cal qtr 6 mo after FERC approval | RM14-15
2012-13 | NUC-001-3 | Nuclear Plant Interface Coordination | 2016-01-01 | Nuc Plant GOPs, Transmission Entities (can include BA, DP, GO, GOP, LSE, PC, RC, TO, TOP, TP, TSP) | 2013-10-01 | 2014-07-03 | 2014-08-14 | 2014-09-15 | n/a | Issued/Effective: 11/4/2014 | 1st day of 1st cal qtr 1 year after FERC approval | RD14-13-000; retires NUC-001-2.1
2010-02 | FAC-001-2 | Connecting New Facilities to the Grid | 2016-01-01 | TO, GO (with fully executed Agreement to conduct a reliability impact study ...) | 2014-03-31 | 2014-06-23 | 2014-08-14 | 2014-08-22 | n/a | Issued/Effective: 11/6/2014 | 1st day of 1st cal qtr 1 year after FERC approval | RD14-12-000; retires FAC-001-1
2010-02 | FAC-002-2 | Connecting New Facilities to the Grid | 2016-01-01 | DP, GO, LSE, PC, TO, TP | 2014-03-31 | 2014-06-23 | 2014-08-14 | 2014-08-22 | n/a | Issued/Effective: 11/6/2014 | 1st day of 1st cal qtr 1 year after FERC approval | RD14-12-000; retires FAC-002-1
2010-07 | FAC-003-3 | Transmission Vegetation Management | TOs: 7/1/2014 Applicable GOs: R3: 1/1/2015 R1, R2, R4-R7: 1/1/2016 | Applicable TOs, Applicable GOs | 2010-11-30 | 2012-05-03 | 2012-05-09 | 2012-07-30 | 2013-04-18 | Issued 9/19/2013 Fed Reg 9/24/2013 Effective 11/25/2013 | For TOs: the date FAC-003-2 was scheduled to become effective For applicable GOs: R3: 1st day of the 1st cal qtr 1 yr after FERC approval R1, R2, R4-R7: 1st day of the 1st cal qtr 2 yrs after FERC approval | Generator Req'mts at the Trans Interface
2010-11 | TPL-001-4 | TPL Table 1, Footnote B | R1 & R7: 1/1/2015 R2-R6 & R8: 1/1/2016 | PC, TP | 2010-04-14 | 2013-01-31 | 2013-02-07 | 2013-02-28 | 2013-05-16 | Issued 10/17/2013 Fed Reg 10/23/2013 Effective 12/23/2013 | R1 & R7: 1st day of 1st cal qtr 12 mo after FERC approval R2-R6 & R8: 1st day of 1st cal qtr 24 mo after FERC approval See Implementation Plan for add'l details | Related to FERC Order 762; approved by NERC BOT as TPL-001-3 but discrepancy IDed and corrected; retires TPL-001-0.1, TPL-002-0b, TPL-003-0a, and TPL-004-0; Docket Nos. RM12-1, RM13-9; Order 786
2008-06 | CIP-002-5 through CIP-011-1 | Cyber Security | High & Med Impact BES Cyber Systems: 4/1/2016 Low Impact BES Cyber Systems: 4/1/2017 | All | 2008 | 2012-11-05 | 2012-11-26 | 2013-01-31 | 2013-04-18 | Issued 11/21/2013 Fed Reg 12/20/2013 Effective 2/3/2014 | Later of: July 1, 2015 -OR- 1st day of 9th cal qtr after FERC approval | CIP v5; RM13-5
n/a | CIP v5 | Revisions to CIP v5 VRFs and VSLs | see enforcement date of each standard | All | n/a | n/a | 2014-05-07 | 2014-05-15 | n/a | Issued/Effective: 7/9/2014 | n/a | responds to directives in Order 791; RD13-5-000
2007-17.2 | PRC-005-3 | Protection System Maintenance and Testing - Phase 2 (Reclosing Relays) | R1, R2 & R5: 4/1/2016 R3 & R4: staggered implementation | DP, GO, TO | 2013-01-17 | 2013-10-25 | 2013-11-07 | 2014-02-14 | 2014-07-17 | Issued 1/22/2014 Fed Reg 1/27/2014 Effective 3/30/2015 | R1, R2 & R5 (for Automatic Reclosing Components): 1st day of 1st cal qtr 12 mo after FERC approval R3 & R4: Staggered as stated in the Implementation Plan | RM14-8; Order No. 803; retires PRC-005-2, PRC-005-1b, PRC-008-0, PRC-011-0, PRC-017-0
2007-09 | MOD-025-2 | Verification and Data Reporting of Generator Real and Reactive Power Capability and Synchronous Condenser Reactive Power Capability | 7/1/2016 (40%) 7/1/2017 (60%) 7/1/2018 (80%) 7/1/2019 (100%) | GO, TOs w/ sync condenser(s) | 2007-06-14 | 2012-12-21 | 2013-02-07 | 2013-05-30 | 2013-09-19 | Issued 3/20/2014 Fed Reg 3/27/2014 Effective 5/27/2014 | 1st day of 1st cal qtr x cal years after FERC approval (y% verification of applicable facilities) if x = 2, y = 40% if x = 3, y = 60% if x = 4, y = 80% if x = 5, y = 100% | Generator Verification; RM-13-16-000; Order 796
2007-09 | PRC-019-1 | Coordination of Generating Unit or Plant Capabilities, Voltage Regulating Controls, and Protection | 7/1/2016 (40%) 7/1/2017 (60%) 7/1/2018 (80%) 7/1/2019 (100%) | GO, TOs w/ sync condenser(s) | 2007-06-14 | 2012-12-21 | 2013-02-07 | 2013-05-30 | 2013-09-19 | Issued 3/20/2014 Fed Reg 3/27/2014 Effective 5/27/2014 | 1st day of 1st cal qtr x cal years after FERC approval (y% verification of applicable facilities) if x = 2, y = 40% if x = 3, y = 60% if x = 4, y = 80% if x = 5, y = 100% | Generator Verification; RM-13-16-000; Order 796
2007-09 | PRC-024-1 | Generator Frequency and Voltage Protective Relay Settings | 7/1/2016 (40%) 7/1/2017 (60%) 7/1/2018 (80%) 7/1/2019 (100%) | GO | 2007-06-14 | 2013-03-27 | 2013-05-09 | 2013-05-30 | 2013-09-19 | Issued 3/20/2014 Fed Reg 3/27/2014 Effective 5/27/2014 | 1st day of 1st cal qtr x cal years after FERC approval (y% verification of applicable facilities) if x = 2, y = 40% if x = 3, y = 60% if x = 4, y = 80% if x = 5, y = 100% | Generator Verification; RM-13-16-000; Order 796
2010-01 | PER-005-2 | Operations Personnel Training | 2016-07-01 | BA, RC, TOP, TO (if applicable), GOP (if applicable) | 2008-12-01 | 2014-02-05 | 2014-02-06 | 2014-03-07 | n/a | Issued/Effective: 6/19/2014 | 1st day of 1st cal qtr 24 mo after FERC approval | Coordinate Interchange Standards; RD14-7-000; replaces PER-005-1; includes revisions to def of "System Operator" and adds a def for "Operations Support Personnel"
2010-03 | MOD-033-1 | Model Verification | 2017-07-01 | PC, RC, TOP | 2012-12-12 | 2014-02-05 | 2014-02-06 | 2014-02-25 | n/a | Issued/Effective: 5/1/2014 | 1st day of 1st cal qtr 36 mo after FERC approval | MOD B; RD14-5-000
2007-09 | MOD-026-1 | Verification of Models and Data for Generator Excitation Control System or Plant Volt/Var Control Functions | R1 & R3-R6: 7/1/2014 R2: 7/1/2018 (30%) 7/1/2020 (50%) 7/1/2024 (100%) | GO, TP | 2007-06-14 | 2012-12-21 | 2013-02-07 | 2013-05-30 | 2013-09-19 | Issued 3/20/2014 Fed Reg 3/27/2014 Effective 5/27/2014 | R1 & R3-R6: 1st day of 1st cal qtr after FERC approval R2: 1st day of 1st cal qtr x years after FERC approval (y% of its applicable unit gross MVA per Interconnection are compliant) if x = 4, y = 30% if x = 6, y = 50% if x = 10, y = 100% | Generator Verification; RM-13-16-000; Order 796
2007-09 | MOD-027-1 | Verification of Models and Data for Turbine/Governor and Load Control or Active Power/Frequency Control Functions | R1 & R3-R5: 7/1/2014 R2: 7/1/2018 (30%) 7/1/2020 (50%) 7/1/2024 (100%) | GO, TP | 2007-06-14 | 2012-12-21 | 2013-02-07 | 2013-05-30 | 2013-09-19 | Issued 3/20/2014 Fed Reg 3/27/2014 Effective 5/27/2014 | R1 & R3-R5: 1st day of 1st cal qtr after FERC approval R2: 1st day of 1st cal qtr x years after FERC approval (y% of its applicable unit gross MVA per Interconnection are compliant) if x = 4, y = 30% if x = 6, y = 50% if x = 10, y = 100% | Generator Verification; RM-13-16-000; Order 796
2010-13.2 | PRC-025-1 | Phase 2 Relay Loadability: Generation | Std effective date: 10/1/2014 IMPLEMENTATION PLAN: R1 (where replacement or removal IS NOT necessary): 10/1/2019 R1 (where replacement or removal IS necessary): 10/1/2021 | GO, TO & DP, all that apply load-responsive protective relays at the terminals of Elements listed in 3.2 | 2010-11-01 | 2013-08-12 | 2013-08-15 | 2013-09-30 | 2014-03-20 | Issued 7/17/2014 Fed Reg 7/23/2014 Effective 9/22/2014 | Std effective: 1st day of 1st cal qtr after FERC approval Implementation Plan provides a table with specific dates R1 (where replacement or removal IS NOT necessary): 1st day of 1st cal qtr 60 mo after FERC approval R1 (where replacement or removal IS necessary): 1st day of 1st cal qtr 84 mo after FERC approval | RM13-19-000 and RM14-3-000; Order No. 799; retires PRC-023-2, R1 Criterion 6 | http://www.nerc.com/pa/Stand/PRC0251RD/PRC_025_1_Implementation_Plan_2013_06_20_Draft_4_(Clean).pdf
Note on K17: LMartin: originally published in the Federal Registry on 12/3/2013; corrected version published on 12/20/2013; no impact to Effective Date of FERC approval

## Archive
NERC Standards Watch List - ARCHIVE |  |  |  |  | LEGEND: | Phase Complete
Updated: 2/13/15 | [5 empty] | New Info
ARCHIVE INFORMATION - This tab contains standards that were removed from the other tabs for any reason (e.g., currently enforced, removed from process)
Project | Standard | Title | Enforcement Date | Applicable Entities | SAR | Industry Stakeholder Process | NERC BOT Approval | NERC Petition for Approval | FERC NOPR | FERC Order | Implementation Plan Summary | Comment
2010-10 | FAC-013-2 | Assessment of Transfer Capability for the Near-Term Transmission Planning Horizon | 2013-04-01 | PC | 2010-04-29 | 2011-01-23 | 2011-01-24 | 2011-01-28 | n/a | Issued 11/17/2011 Fed Reg 11/22/2011 Effective 1/23/2012 | LATER OF 1st day of 1st cal qtr 12 mo after FERC approval -OR- 1st day of 1st cal qtr 6 mo after MOD-001-1, MOD-028-1, MOD-029-1, MOD-030-2 become effective | retires FAC-012-1 and FAC-013-1
2006-01 | PER-005-1 R1, R2 & subs | System Personnel Training | 2013-04-01 | BA, RC, TOP | 2006-04-12 | 2008-12-22 | 2009-02-10 | 2009-09-30 | 2010-06-17 | Issued 11/18/2010 Fed Reg 11/26/2010 Effective 1/25/2011 | 1st day of 1st cal qtr 24 mo after FERC approval | RM09-25-000; Order 742
2007-17 | Definition Revision | Protection System | 2013-04-01 | n/a | 2010 directive from Standards Committee | 2010-11-11 | 2010-11-19 | 2011-03-30 | n/a | 2012-02-03 | 1st day of 1st cal qtr 12 mo after FERC approval | RD11-13-000
2006-06 | IRO-001-2 | Reliability Coordination — Responsibilities and Authorities |  | BA, GOP, LSE, PSE, TOP, TSP, RC, RRO | 2007-05-01 | 2011-07-25 | 2011-08-04 | n/a | n/a | n/a | n/a | Removes IRO-001-1.1 R7 (coordinates with IRO-014-2); subsequently replaced with IRO-001-3; believe it goes to inactive list; never enforceable
2012-INT-02 | TPL-003-0b and TPL-004-0a | System Performance Following Loss of Two or More BES Elements (Category C) System Performance Following Extreme Events Resulting in the Loss of Two or More BES Elements (Category D) | 2013-06-20 | PA, TP | 2011-12-12 | 2013-01-31 | 2013-02-07 | 2013-04-12 | n/a | Issued/Effective 6/20/2013 | effective upon FERC approval | Interpretation related to FERC Order 754; coordinated with petition for approval of TPL-001-4; RD13-8
2006-03 | EOP-001-2.1b | Emergency Operations Planning | 2013-07-01 | BA, TOP | 2006-10-26 | 2009-05-18 | 2009-08-05 | 2009-12-31 | 2010-11-17 | Issued 3/17/2011 Fed Reg 3/23/2011 Effective 5/23/2011 | 1st day of 1st cal qtr 24 mo after FERC approval | Order 749 & Letter Order for errata
2006-03 | EOP-005-2 | System Restoration from Blackstart Resources | 2013-07-01 | GOP, TOP & DP,TO IDed in a TOP restoration plan | 2006-10-26 | 2009-05-18 | 2009-08-05 | 2009-12-31 | 2010-11-17 | Issued 3/17/2011 Fed Reg 3/23/2011 Effective 5/23/2011 | 1st day of 1st cal qtr 24 mo after FERC approval | Order 749
2006-03 | EOP-006-2 | System Restoration Coordination | 2013-07-01 | RC | 2006-10-26 | 2009-05-18 | 2009-08-05 | 2009-12-31 | 2010-11-17 | Issued 3/17/2011 Fed Reg 3/23/2011 Effective 5/23/2011 | 1st day of 1st cal qtr 24 mo after FERC approval | Order 749
2006-04 | EOP-008-1 | Loss of Control Center Functionality | 2013-07-01 | BA, RC, TOP | 2006-10-26 | 2010-07-26 | 2010-08-05 | 2011-02-11 | n/a | Issued 4/21/2011 Fed Reg 4/28/2011 Effective 6/27/2011 | 1st day of 1st cal qtr 24 mo after FERC approval | RD11-4-000
2011-INT-02 | VAR-002-2b | Generator Operation for Maintaining Network Voltage Schedules | 2013-07-01 | GO, GOP | 2011-01-28 | 2012-07-27 | 2012-08-16 | 2012-11-21 | n/a | Issued/Effective 4/16/2013 | 1st day of the 1st cal qtr following the date of this order | RapidRev re AVR notification during start up/shut down; RD13-2-000
2010-13 | PRC-023-2 R1 (For criterion 10.1 … see cell comment) | Transmission Relay Loadability | 2013-07-01 | TO, GO, DP | 2010-08-12 | 2011-03-07 | 2011-03-10 | 2011-03-18 | 2011-09-15 | Issued 3/15/2012 Fed Reg 3/21/2012 Effective 5/7/2012 | 1st day of 1st cal qtr 12 mo after FERC approval | RM11-16-000; Order No. 759
2012-08.1 Phase 1 | Definition revision | “Bulk-Power System,” “Reliability Standard” and “Reliable Operation” | 2013-07-09 | n/a | 2012-05-10 | 2013-04-29 | 2013-05-09 | 2013-05-10 | n/a | Issued/Effective 7/9/2013 | Effective upon FERC approval | Statutory definitions to NERC Glossary of Terms; RD13-10-000
2011-INT-01 | MOD-028-2 | Area Interchange Methodology | 2013-10-01 | TOPs & TSPs that use Area Interchange Methodology to calc TTC & ATC, respectively | 2011-08-30 | 2011-12-22 | 2012-02-09 | 2012-08-24 | 2013-03-21 | Issued 7/18/2013 Fed Reg 7/29/2013 Effective 9/27/2013 | 1st day of 1st cal qtr after FERC approval | RapidRev re timing/freq of TTC calcs for ATC calc; RM12-19-000
2007-01 | EOP-003-2 | Load Shedding Plans | 2013-10-01 | BA, TOP | 2007-03-28 | 2010-10-28 | 2010-11-04 | 3/31/2011 amended 5/17/2011 | 2011-10-20 | Issued 5/7/2012 Fed Reg 5/11/2012 Effective 7/10/2012 | 1 year following the 1st day of the 1st cal qtr after FERC approval | RM11-20-000; Order No. 763 retires PRC-007-0, PRC-009-0, EOP-003-1, and PRC-006-0 (never enforceable)
2007-01 | PRC-006-1 | Automatic Underfrequency Load Shedding | 2013-10-01 | PC, UFLS entities (DP, TO) | 2007-03-28 | 2010-10-28 | 2010-11-04 | 3/31/2011 amended 5/17/2011 | 2011-10-20 | Issued 5/7/2012 Fed Reg 5/11/2012 Effective 7/10/2012 | 1st day of 1st cal qtr 1 year after FERC approval (except for R4.1 - R4.6) R4.1-R4.6: one year following the receipt of gen data as required in PRC-024-1, but no sooner than effective date for rest of the std | RM11-20-000; Order No. 763 retires PRC-007-0, PRC-009-0, EOP-003-1, and PRC-006-0 (never enforceable)
2010-13 | PRC-023-2 R1 (For switch-on-to-fault schemes as described in Attachment A, Section 1.3) | Transmission Relay Loadability | 2013-10-01 | TO, GO, DP | 2010-08-12 | 2011-03-07 | 2011-03-10 | 2011-03-18 | 2011-09-15 | Issued 3/15/2012 Fed Reg 3/21/2012 Effective 5/7/2012 | Later of: 1st day of 1st cal qtr after FERC approval of PRC-023-2 (7/1/2012) -OR- 1st day of 1st cal qtr 39 mo after FERC approval of PRC-023-1 (10/1/2013) | RM11-16-000; Order No. 759
2007-07 | FAC-003-2 | Transmission Vegetation Management | 2014-07-01 | TO | 2007-04-02 | 2011-10-13 | 2011-11-03 | 2011-12-21 | 2012-10-18 | Issued 3/21/2013 Fed Reg 3/28/2013 Effective 5/27/2013 | 1st day of 1st cal qtr 1 yr after FERC approval | Superseded by FAC-003-3 as of 11/25/2013; never enforceable
2006-02 | TPL-001-2 | Transmission System Planning Performance Requirements |  | PC, TP | 2006-04-30 | 2011-07-22 | 2011-08-04 | 2011-10-19 | NOPR proposing remand: 4/19/2012 supplemental NOPR: 5/16/2013 (see TPL-001-4 below) |  |  | Superseded by TPL-001-4
2008-06 | CIP-002-4 CIP-003-4 CIP-004-4a CIP-005-4a CIP-006-4c CIP-007-4 CIP-008-4 CIP-009-4 | Cyber Security — Critical Cyber Asset Identification | 10/1/2014 4/1/2014 | All | 2008-07-10 | 2010-12-30 | 2011-01-24 | 2011-02-10 | 2011-09-15 | Issued 4/19/2012 Fed Reg 4/25/2012 Effective 6/25/2012 ORDER GRANTING EXTENSION OF TIME 8/12/2013 | Existing CAs: 1st day of 8th cal qtr after FERC approval; Newly IDed CAs: see implementation plan | RM11-11-000 Order 761; Superseded by CIP v5 per Order 791 paragraph 171
2010-07 | FAC-001-1 | Facility Connection Requirements | TOs: 11/25/2013 Applicable GOs: 1/1/2015 | TO, Applicable GOs | 2010-11-30 | 2011-12-23 | 2012-02-09 | 2012-07-30 | 2013-04-18 | Issued 9/19/2013 Fed Reg 9/24/2013 Effective 11/25/2013 | For TOs: upon FERC approval For applicable GOs: 1st day of the 1st cal qtr 1 yr after FERC approval | Generator Req'mts at the Trans Interface; RM12-16-000
2010-07 | PRC-004-2.1a | Analysis and Mitigation of Transmission and Generation Protection System Misoperations | 2013-11-25 | GO, TO, DPs that own trans Protection Sys | 2010-11-30 | 2011-12-23 | 2012-02-09 | 2012-07-30 | 2013-04-18 | Issued 9/19/2013 Fed Reg 9/24/2013 Effective 11/25/2013 | Upon FERC approval | Generator Req'mts at the Trans Interface
2010-07 | PRC-005-1.1b | Transmission and Generation Protection System Maintenance and Testing | 2013-11-25 | GO, TO, DPs that own trans Protection Sys | 2010-11-30 | 2012-05-03 | 2012-05-09 | 2012-07-30 | 2013-04-18 | Issued 9/19/2013 Fed Reg 9/24/2013 Effective 11/25/2013 | Upon FERC approval | Generator Req'mts at the Trans Interface
2008-06 | CIP-002-5.1 | Cyber Security — BES Cyber System Categorization |  | All | n/a | n/a | Standards Committee approval: 9/27/2013 | 2013-09-30 | integrated into CIP v5 package | n/a |  | Errata approved by Standards Committee on 9/27/2013; Revises defs for Electronic Access Control or Monitoring Systems (EACMS) and Interactive Remote Access to use the term “Intermediate Systems” instead of “Intermediate Device”; CIP-002 uses the term EACMS
2008-06 | CIP-004-5.1 | Cyber Security — Personnel & Training |  | All | n/a | n/a | Standards Committee approval: 9/27/2013 | 2013-09-30 | integrated into CIP v5 package | n/a |  | Errata approved by Standards Committee on 9/27/2013; Revises the VSL for R4 Part 4.2 which had an identical VSL for Moderate and High
2010-13 | PRC-023-2 R6 | Transmission Relay Loadability | 2014-01-01 | PC | 2010-08-12 | 2011-03-07 | 2011-03-10 | 2011-03-18 | 2011-09-15 | Issued 3/15/2012 Fed Reg 3/21/2012 Effective 5/7/2012 | 1st day of 1st cal qtr 18 mo after FERC approval | RM11-16-000; Order No. 759
2009-01 | EOP-004-2 | Event Reporting | 2014-01-01 | BA, DP, GO, GOP, TO, TOP, RC | 2009-04-15 | 2012-11-05 | 2012-11-07 | 12/31/2012 amended: 1/4/2013 | n/a | Issued/Effective 6/20/2013 | 1st day of 1st cal qtr 6 mo after FERC approval | Combines CIP-001-1 and EOP-004-1; RD13-3-000
n/a | VAR-001-3 | Voltage and Reactive Control | 2014-01-01 | LSE, PSE, TOP and GOPs in Western Interconnect | WECC Regional Process | 2011-12-05 | 2012-05-09 | 2013-02-25 | n/a | Issued/Effective 6/20/2013 | 1st day of 1st cal qtr 6 mo after FERC approval | WECC Regional Variance; RD13-6-000
2013-02 | Paragraph 81 | Paragraph 81 | 1/21/2014 Note: Standards will not be updated or upversioned but requirements will be officially retired | various | 2012-09-12 | 2013-01-17 | 2013-02-07 | 2013-02-28 | 2013-06-20 | Issued 11/21/2013 Fed Reg 12/6/2013 Effective 1/21/2014 | immediately upon FERC approval | Removes 34 requirements from 19 standards; RM13-8; Order 788
2006-01 | PER-005-1 R3.1 | System Personnel Training | 2014-04-01 | BA, RC, TOP | 2006-04-12 | 2008-12-22 | 2009-02-10 | 2009-09-30 | 2010-06-17 | Issued 11/18/2010 Fed Reg 11/26/2010 Effective 1/25/2011 | 1st day of 1st cal qtr 36 mo after FERC approval | RM09-25-000; Order 742
n/a | BAL-001-1 | Real Power Balancing Control Performance | 2014-04-01 | BA | n/a | n/a | 2012-12-19 | 2013-08-20 | n/a | Issued/Effective 10/16/2013 | 1st day of 2nd cal qtr after FERC approval | WECC Regional Variance; Joint filing with WECC for BAL-004-WECC-02; RD13-11-000
2010-17 Phase 1 | Definition Revision | Bulk Electric System (BES) | 2014-07-01 | n/a | 2010-12-17 | 2011-11-21 | 2012-01-18 | 2012-01-25 | 2012-06-22 | Issued 12/20/2012 Fed Reg 1/4/2013 Effective 3/5/2013 Issued 4/18/2013 ORDER GRANTING EXTENSION OF TIME Issued 6/13/2013 | 1st day of the 2nd cal qtr after FERC approval | Order 773 and Order 773-A; RM12-6-001; RM12-7-001; subsequently replaced with phase 2 definition
2006-06 | COM-002-3 | Communication and Coordination | n/a | BA, DP, GOP, TOP, RC | 2007-05-01 | 2012-07-06 | 2012-11-07 | n/a | n/a | n/a | n/a | Reliability Coordination; subsequently combined with COM-003-1 to become COM-002-4; goes to inactive list; never enforceable
2007-17 | PRC-001-1.1 | System Protection Coordination | 2013-04-01 | BA, GOP, TOP | n/a | n/a | Standards Committee approval: 4/11/2012 | informational filing: 9/9/2013 | n/a | n/a | effective immediately | RD11-13-000; errata change capitalizes all instances of "Protection System"; NERC website now shows an enforcement date equal to the date the new definition of Protection System went into effect
2007-17 | NUC-001-2.1 | Nuclear Plant Interface Coordination | 2013-04-01 | Nuclear Plant GOP, Transmission Entities | n/a | n/a | Standards Committee approval: 4/11/2012 | informational filing: 9/9/2013 | n/a | n/a | effective immediately | RD11-13-000; errata change capitalizes all instances of "Protection System"; NERC website now shows an enforcement date equal to the date the new definition of Protection System went into effect
2010-17 | Definition Revision | Proposed Definition of Bulk Electric System (Phase 2) | 2014-07-01 | All | 2011-12-02 | 2013-11-18 | 2013-11-21 | 2013-12-13 | n/a | Issued/Effective: 3/20/2014 | 1st day of 2nd cal qtr after FERC approval | RD 14-2-000
2010-17 Exception | BES | Rules of Procedure changes | 2014-07-01 | n/a | 2010-12-17 | 10/27/2011 (comments only) | 2012-01-18 | 2012-01-25 | 2012-06-22 | Issued 12/20/2012 Fed Reg 1/4/2013 Effective 3/5/2013 Issued 4/18/2013 ORDER GRANTING EXTENSION OF TIME Issued 6/13/2013 | 1st day of 2nd cal qtr after FERC approval | Exception Process; Order 773 and Order 773-A; RM12-6-001; RM12-7-001
2010-07 | FAC-003-3 | Transmission Vegetation Management | TOs: 7/1/2014 Applicable GOs: R3: 1/1/2015 R1, R2, R4-R7: 1/1/2016 | Applicable TOs, Applicable GOs | 2010-11-30 | 2012-05-03 | 2012-05-09 | 2012-07-30 | 2013-04-18 | Issued 9/19/2013 Fed Reg 9/24/2013 Effective 11/25/2013 | For TOs: the date FAC-003-2 was scheduled to become effective For applicable GOs: R3: 1st day of the 1st cal qtr 1 yr after FERC approval R1, R2, R4-R7: 1st day of the 1st cal qtr 2 yrs after FERC approval | Generator Req'mts at the Trans Interface
2010-13 | PRC-023-2 R1 (For supervisory elements, see Attachment A, Section 1.6) | Transmission Relay Loadability | 2014-07-01 | TO, GO, DP | 2010-08-12 | 2011-03-07 | 2011-03-10 | 2011-03-18 | 2011-09-15 | Issued 3/15/2012 Fed Reg 3/21/2012 Effective 5/7/2012 | 1st day of 1st cal qtr 24 mo after FERC approval | RM11-16-000; Order No. 759
2007-09 | MOD-026-1 | Verification of Models and Data for Generator Excitation Control System or Plant Volt/Var Control Functions | R1 & R3-R6: 7/1/2014 R2: 7/1/2018 (30%) 7/1/2020 (50%) 7/1/2024 (100%) | GO, TP | 2007-06-14 | 2012-12-21 | 2013-02-07 | 2013-05-30 | 2013-09-19 | Issued 3/20/2014 Fed Reg 3/27/2014 Effective 5/27/2014 | R1 & R3-R6: 1st day of 1st cal qtr after FERC approval R2: 1st day of 1st cal qtr x years after FERC approval (y% of its applicable unit gross MVA per Interconnection are compliant) if x = 4, y = 30% if x = 6, y = 50% if x = 10, y = 100% | Generator Verification; RM-13-16-000; Order 796
2007-09 | MOD-027-1 | Verification of Models and Data for Turbine/Governor and Load Control or Active Power/Frequency Control Functions | R1 & R3-R5: 7/1/2014 R2: 7/1/2018 (30%) 7/1/2020 (50%) 7/1/2024 (100%) | GO, TP | 2007-06-14 | 2012-12-21 | 2013-02-07 | 2013-05-30 | 2013-09-19 | Issued 3/20/2014 Fed Reg 3/27/2014 Effective 5/27/2014 | R1 & R3-R5: 1st day of 1st cal qtr after FERC approval R2: 1st day of 1st cal qtr x years after FERC approval (y% of its applicable unit gross MVA per Interconnection are compliant) if x = 4, y = 30% if x = 6, y = 50% if x = 10, y = 100% | Generator Verification; RM-13-16-000; Order 796
2008-12 | INT-004-3 | Dynamic Transfers | 2014-10-01 | BA, PSE | 2008-12-01 | 2014-02-05 | 2014-02-06 | 2014-02-27 | n/a | Issued/Effective: 6/30/2014 | 1st day of 2nd cal qtr after FERC approval | Coordinate Interchange Standards; RD14-4-000
2008-12 | INT-006-4 | Evaluation of Interchange Transactions | 2014-10-01 | BA, TSP | 2008-12-01 | 2013-12-20 | 2014-02-06 | 2014-02-27 | n/a | Issued/Effective: 6/30/2014 | 1st day of 2nd cal qtr after FERC approval | Coordinate Interchange Standards; RD14-4-000
2008-12 | INT-009-2 | Implementation of Interchange | 2014-10-01 | BA | 2008-12-01 | 2013-12-20 | 2014-02-06 | 2014-02-27 | n/a | Issued/Effective: 6/30/2014 | 1st day of 2nd cal qtr after FERC approval | Coordinate Interchange Standards; RD14-4-000
2008-12 | INT-010-2 | Interchange Initiation and Modification for Reliability | 2014-10-01 | BA | 2008-12-01 | 2014-02-05 | 2014-02-06 | 2014-02-27 | n/a | Issued/Effective: 6/30/2014 | 1st day of 2nd cal qtr after FERC approval | Coordinate Interchange Standards; RD14-4-000
2008-12 | INT-011-1 | Intra-Balancing Authority Transaction Identification | 2014-10-01 | LSE | 2008-12-01 | 2013-12-20 | 2014-02-06 | 2014-02-27 | n/a | Issued/Effective: 6/30/2014 | 1st day of 2nd cal qtr after FERC approval | Coordinate Interchange Standards; RD14-4-000
2013-04 | VAR-001-4 | Voltage and Reactive Control | 2014-10-01 | TOP, GOPs within WECC | 2013-07-18 | 2013-12-23 | 2014-02-06 | 2014-06-09 | n/a | Issued/Effective: 8/1/2014 | 1st day of 1st cal qtr after FERC approval | Voltage and Reactive Control; RD14-11-000; retires VAR-001-3
2013-04 | VAR-002-3 | Generator Operation for Maintaining Network Voltage Schedules | 2014-10-01 | GOP, GO | 2013-07-18 | 2014-05-05 | 2014-05-07 | 2014-06-09 | n/a | Issued/Effective: 8/1/2014 | 1st day of 1st cal qtr after FERC approval | Voltage and Reactive Control; RD14-11-000; retires VAR-002-2b
2010-INT-01 | TOP-006-3 | Monitoring System Conditions |  | BA, GOP, TOP, RC | 2010-01-20 | 2012-09-21 | 2012-11-07 | 2013-04-04 | NOPR proposing approval: 11/21/2013 | n/a | n/a | RapidRev re reporting and tech info responsibilities; RM13-12; replaced with TOP/IRO Revisions project 2014-03
2006-06 | IRO-001-3 | Reliability Coordination – Responsibilities and Authorities |  | BA, DP, GOP, TOP, RC | 2007-05-01 | 2012-07-06 | 2012-08-16 | 2013-04-16 | NOPR proposing remand: 11/21/2013 | n/a | n/a | Reliability Coordination; includes retirement of IRO-001-1.1, IRO-002-2; IRO-005-3a, IRO-014-1, IRO-015-1 and IRO-016-1; requests simultaneous approval with TOP stds; RM13-15; replaced with TOP/IRO Revisions project 2014-03
2006-06 | IRO-002-3 | Reliability Coordination — Analysis Tools |  | RC | 2007-05-01 | 2011-07-25 | 2011-08-04 | 2013-04-16 | NOPR proposing remand: 11/21/2013 | n/a | n/a | see IRO-001-3 (above)
2006-06 | IRO-005-4 | Reliability Coordination — Current Day Operations |  | RC | 2007-05-01 | 2011-07-25 | 2011-08-04 | 2013-04-16 | NOPR proposing remand: 11/21/2013 | n/a | n/a | see IRO-001-3 (above)
2006-06 | IRO-014-2 | Coordination Among Reliability Coordinators |  | RC | 2007-05-01 | 2011-07-25 | 2011-08-04 | 2013-04-16 | NOPR proposing remand: 11/21/2013 | n/a | n/a | see IRO-001-3 (above)
2007-03 | TOP-001-2 | Transmission Operations |  | BA, DP, GOP, LSE, TOP | 2007-08-06 | 2012-05-06 | 2012-05-09 | 2013-04-16 | NOPR proposing remand: 11/21/2013 | n/a | n/a | RT Transmission Ops; includes retirement of TOP-001-1a, TOP-002-2.1b, TOP-003-1, TOP-004-2, TOP-005-2a, TOP-006-2, TOP-007-0, TOP-008-1, PER-001-0.2; requests simultaneous approval with IRO stds; RM13-14; replaced with TOP/IRO Revisions project 2014-03
2007-03 | TOP-002-3 | Operations Planning |  | TOP | 2007-08-06 | 2012-05-06 | 2012-05-09 | 2013-04-16 | NOPR proposing remand: 11/21/2013 | n/a | n/a | see TOP-001-2 (above)
2007-03 | TOP-003-2 | Operational Reliability Data |  | BA, DP, GO, GOP, IA, LSE, TO, TOP | 2007-08-06 | 2012-05-06 | 2012-05-09 | 2013-04-16 | NOPR proposing remand: 11/21/2013 | n/a | n/a | see TOP-001-2 (above)
2007-03 | PRC-001-2 | System Protection Coordination |  | BA, GOP, TOP | 2007-08-06 | 2012-05-06 | 2012-05-09 | 2013-04-16 | NOPR proposing remand: 11/21/2013 | n/a | n/a | see TOP-001-2 (above)
2010-07 | FAC-001-1 | Facility Connection Requirements | TOs: 11/25/2013 Applicable GOs: 1/1/2015 | TO, Applicable GOs | 2010-11-30 | 2011-12-23 | 2012-02-09 | 2012-07-30 | 2013-04-18 | Issued 9/19/2013 Fed Reg 9/24/2013 Effective 11/25/2013 | For TOs: upon FERC approval For applicable GOs: 1st day of the 1st cal qtr 1 yr after FERC approval | Generator Req'mts at the Trans Interface; RM12-16-000
2008-10 | CIP-006-3d or -4d | Cyber Security — Physical Security of Critical Cyber Assets |  | All | 2008-04-02 | 2011-12-19 | 2012-02-09 | 2012-05-23 | n/a | Remanded: 3/21/2013 |  | Interp re ESP wiring external to a PSP; RD12-3-000; now showing on NERC's inactive page
2010-INT-05 | CIP-002-3a or -4a | Cyber Security — Critical Cyber Asset Identification |  | All | 2010-07-27 | 2012-04-30 | 2012-05-09 | 2012-08-01 | n/a | Remanded: 3/21/2013 |  | Interp re "essential to the op of a CA"; RD12-5-000; now showing on NERC's inactive page
2010-13 | PRC-023-2 R1, R2, R3 (For circuits identified by the PC pursuant to R6) | Transmission Relay Loadability | Later of: X/1/XX -OR- 1/1/XX | TO, GO, DP | 2010-08-12 | 2011-03-07 | 2011-03-10 | 2011-03-18 | 2011-09-15 | Issued 3/15/2012 Fed Reg 3/21/2012 Effective 5/7/2012 | Later of: 1st day of 1st cal qtr 39 mo after notification by PC of a circuit’s inclusion -OR- 1st day of 1st cal year in which any criterion in Attachment B applies, unless the PC removes the circuit from the list before the applicable effective date | RM11-16-000; Order No. 759; replaced by PRC-023-3 and, in part, by PRC-025-1
Note on B15: For R1, criterion 10.1, to set transformer fault protection relays on transmission lines terminated only with a transformer such that the protection settings do not expose the transformer to fault level and duration that exceeds its mechanical withstand capability
Note on D64: Martin, Lisa: See ERCOT Operations Notice W-B052914-01 dated 5/29/2014 as one example of notification
Note on L47: Martin, Lisa: The standard Effective Date language does not match the language of the Implementation Plan. The NERC website says "The filing to FERC indicated that the standards were to be effective consistent with the implementation plan" and gives an Enforcement Date of 10/1/2014; NERC issued an information filling with FERC on 7/30/14 to resolve this issue
Note on L48: Martin, Lisa: The standard Effective Date language does not match the language of the Implementation Plan. The NERC website says "The filing to FERC indicated that the standards were to be effective consistent with the implementation plan" and gives an Enforcement Date of 10/1/2014; NERC issued an information filling with FERC on 7/30/14 to resolve this issue
Note on L49: Martin, Lisa: The standard Effective Date language does not match the language of the Implementation Plan. The NERC website says "The filing to FERC indicated that the standards were to be effective consistent with the implementation plan" and gives an Enforcement Date of 10/1/2014; NERC issued an information filling with FERC on 7/30/14 to resolve this issue