## Slide 1: SMT Update To AMWG
February 20, 2015

## Slide 2: SMT Events Update

## Slide 3: Event - SMT Website Portal Missing Data Files in Late December 2014
On December 24, 27, 28 and 29, 2014 Some TDSP 15 Minute Interval LSE Files Were Not Loaded into the SMT Database for Website Portal Access
Awareness of an issue was initiated through calls to the SMT Helpdesk concerning missing data on December 24 and December 27
Investigation found the following:
  All TDSP 15 minute interval LSE files were successfully received by SMT and loaded to the SMT FTPS folders for pick up by RORs
  A failure to load all 15 minute interval LSE files occurred between the SMT staging table and the SMT website portal database on the two reported dates in December
  The file loading portion of the SMT solution had intermittent failures under the increased workload due to the ramp up of REP Enrollment functionality, REP Historical Backfill requests, and increasing TDSP LSE file volume
  Actions taken were the following:
    The missing files were requested from the TDSPs for December 24 and December 27 and those files were loaded to the SMT database for website portal access
    An analysis of files successfully loaded to the SMT website portal database was conducted and identified the two additional dates of December 28 and December 29 that had missing data and required reload from the TDSPs to SMT
The following remediation's were implemented
  Additional monitoring was instituted to verify all TDSP files are successfully loaded from the SMT staging table to the SMT website portal database
  Scheduling of TDSP LSE files, REP Historical Backfill and REP Enrollment jobs was tuned for less volume per hour
  The new SMT infrastructure will accommodate increased volume capacity per hour

## Slide 4: Event - SMT Solution Services Outage Sunday February 8, 2015
On Sunday February 8, 2015 from 10:00 AM until 1:00 PM SMT Experienced a Services Outage
Awareness of an issue was initiated through the SMT solution automated monitoring alarms
Investigation found the following:
  The SMT database log had become full and locked the SMT database
  The SMT database locking caused the SMT servers to fail and bring down the SMT solution
  The SMT database log automated monitoring mechanism had failed to report the issue
  Actions taken were the following:
    The SMT database logs were cleared
    The SMT servers, applications and services were restarted
The following remediation's were implemented
  The database log automated monitoring mechanism has been reprogrammed to prompt a warning at a lower percentage utilization to allow time for action to take place prior to an outage
  The SMT database log manual monitoring processes have been modified to initiate additional check points
  The new SMT infrastructure will provide upgraded versions of database software that accommodate larger logs and even greater enhancements to automated monitoring

## Slide 5: SMT Infrastructure Refresh Update

## Slide 6: SMT Infrastructure Refresh Project Schedule
Hardware Acquisition, Rack Stack, Build, Install OS – Development, Test, Stage, Production and DR Environments
1st Quarter
2nd Quarter
2014
3rd Quarter
4th Quarter
2015
Network and Security – Development, Test, Stage, Production and DR Environments
Planning
UAT Test
Legend
Completed
In Process
Future Task
January
February
March
April
3/28/15
Go Live
2 - 4 Day Outage
Required
Configuration, SMT Solution Build, and TDSP Integration
SIT Test
Stage
All Five Environments
Production
Disaster Recovery
UAT Test
Configuration, SMT Solution Build, and TDSP Integration
SIT Test
UAT Test
Configuration, SMT Solution Build, and TDSP Integration
SIT Test
2/24/15 – 2/26/15
HAN and ODR
2 Day
Intermittent
Outage
Required
3/1015 – 3/12/15
HAN and ODR
2 Day
Intermittent
Outage
Required
Note: Outage Dates are not yet Hardened

## Slide 7: Status Update of AMWG Change Requests

## Slide 8: Status of AMWG Change Requests
Summary: 39 Total AMWG Change Requests Including 9 Delivered, 1 Ready for Delivery in the Next Release, 19 RMS Approved and 10 AMWG Drafts in Review 2/20/15
9 AMWG Change Requests Delivered 2014
  SMT Reporting AMWG CR 2013 002, AMWG CR 2013 005, AMWG CR 2013 006, AMWG CR 2013 007, and AMWG CR 2013 009 – Delivered Q2 2014
  ROR Historical Backfill and ROR New Customer Enrollment (Interim Solution) AMWG CR 2013 017 – Delivered Q2 2014
  ROR Vendor on Behalf AMWG CR 2013 016 – Delivered Q3 2014
  Usability Bypass redundant screen for Users with only one meter when accessing HAN device information AMWG CR 2013 012 – Delivered Q4 2014
  Usability Timeout on SMT takes user to “incorrect login” screen AMWG CR 2013 013 – Delivered Q4 2014

## Slide 9: Status of AMWG Change Requests
1 AMWG Change Request Awaiting Next Release to Implement in 2015
  AMWG CR 2013 014 Allow SMT user to toggle between 15-Minute Reads and Daily Reads without having to reset the date range
8 AMWG Change Requests Completed JDOA Estimation
  AMWG CR 2013 001, AMWG CR 2013 003, AMWG CR 2013 004, AMWG CR 2013 008, AMWG CR 2013 010, AMWG CR 2013 011, AMWG CR 2013 015, AMWG CR 2014 018
11 AMWG Change Requests Approved by RMS In Process for JDOA Estimation
  AMWG CR 2015 019 through AMWG CR 2015 029
10 AMWG Draft Change Requests in Review February 20, 2015
  AMWG CR 2015 030 through AMWG CR 2015 039

## Slide 10: Rough Order Of Magnitude (ROM) Estimate of Effort Classification
These are rough order of magnitudes and do not include project ramp-up and testing effort (SIT & UAT) and only assumes unit testing.
Actual estimates could vary significantly depending on requirements.
Ramp-up and testing would be 20 to 40% of the overall effort
Overall project cost will vary based on efficiency gains from packaging like functionality
Change Type | ROM
MINOR | 0 – 20 K
SMALL | 20 – 40 K
MEDUIM | 40 – 60 K
HIGH | 60 – 120 K
VERY HIGH | Over 120 K

## Slide 11
AMWG Change Request | AMWG CR Document | Status | Estimated Delivery Date | Estimated Cost
AMWG CR 2013 001 – Report for AMWG Data Monitoring – Data Completeness Measurements |  | JDOA Estimate Complete | Awaiting Prioritization | Small
AMWG CR 2013 002 – Reports for AMWG Data Monitoring – Data Timeliness Measurements |  | Complete | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 003 – Reports for AMWG Data Monitoring – Measurement of Percentage of Actual Meter Reads |  | JDOA Estimate Complete | Awaiting Prioritization | Small
AMWG CR 2013 004 – Reports for AMWG Data Monitoring – Measurement of Estimates |  | JDOA Estimate Completed | Awaiting Prioritization | Medium
AMWG CR 2013 005 – Reports for AMWG Data Monitoring – Number of SMT Help Desk Tickets Monthly by Ticket Type |  | Complete | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 006 – Reports for AMWG Data Monitoring – Availability of SMT API |  | Complete | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 007 – Reports for AMWG Data Monitoring – Availability of SMT FTPS |  | Complete | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 008 – Reports for AMWG Data Monitoring – Average Time to Deliver HAN Messages |  | JDOA Estimate Completed | Awaiting Prioritization | Small
AMWG CR 2013 009 – Reports for AMWG Data Monitoring – Number of Accounts by Type |  | Complete | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 010 – Reports for AMWG Data Monitoring – Number of Reports Requested by GUI (Portal) and Number of FTPS Accesses |  | JDOA Estimate Complete | Awaiting Prioritization | Medium
AMWG Change Requests

## Slide 12
AMWG Change Request | AMWG CR Document | Status | Estimated Delivery Date | Estimated Cost
AMWG CR 2013 011 – Average Time from HAN Provision Request to Meter Ready Status |  | JDOA Estimate Completed | Awaiting Prioritization | Small
AMWG CR 2013 012 – Bypass redundant screen for Users with only one meter when accessing HAN device information |  | Complete | Q4 2014 Delivered | Included in Third-Party
AMWG CR 2013 013 – Timeout on SMT takes user to “incorrect login” screen |  | Complete | Q4 2014 Delivered | Included in Third-Party
AMWG CR 2013 014 – Allow SMT user to toggle between 15-Minute Reads and Daily Reads without having to reset the date range |  | Designed | 2015 Next Release | Included in Usability
AMWG CR 2013 015 – Expand Daily Usage Graph to show 35 days of daily usage on the SMT GUI |  | JDOA Estimate Completed | Awaiting Prioritization | Medium
AMWG CR 2013 016 – Capability for RORs to grant access to vendors on their behalf to the ROR’s customers via API (energy usage, HAN messaging , and HAN provisioning) and FTPS files |  | Complete | Q3 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Backfill of Historical Usage Data for Existing Customers- “Interim”) | See Below CR 2013 017 Permanent | Completed Interim | Q4 2013 Delivered | Included in SMT Work In Process
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Subscription for New Customer Historical Usage – “Interim”) | See Below CR 2013 017 Permanent | Completed Interim | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT – Permanent Solution to Replace Interim Solution |  | JDOA Estimate To Begin After Q1 2015 | Awaiting Prioritization | Will Be Estimated After New Infrastructure Implemented in Q1 2015
AMWG CR 2014 018 – Add Generation Data to the SMT Portal View |  | JDOA Estimate Completed | Awaiting Prioritization | Medium
AMWG Change Requests (Cont.)

## Slide 13
AMWG Change Request | AMWG CR Document | Status | Estimated Delivery Date | Estimated Cost
AMWG CR 2015 019 – Relocate Various SMT User Guides from the Authenticated Site to the Unauthenticated Site |  | RMS Approved | Awaiting Prioritization | In Process for 3/25/15
AMWG CR 2015 020 – Add Customer Type in the Customer Information Section in the View / Edit Agreement Page |  | RMS Approved | Awaiting Prioritization | In Process for 3/25/15
AMWG CR 2015 021 – Improve REP of Record Search Criteria During the Customer Registration Process |  | RMS Approved | Awaiting Prioritization | In Process for 3/25/15
AMWG CR 2015 022 – Keep Selected ROR Visible During Customer Registration |  | RMS Approved | Awaiting Prioritization | In Process for 3/25/15
AMWG CR 2015 023 – Allow Entry of Multiple ESIIDs During Customer Registration Process |  | RMS Approved | Awaiting Prioritization | In Process for 3/25/15
AMWG CR 2015 024 – Third Party Access Renew Energy Data Agreement After One Year |  | RMS Approved | Awaiting Prioritization | In Process for 3/25/15
AMWG CR 2015 025 – Third Party User Experience Add Identifying Data Fields in the Report Request Status Page |  | RMS Approved | Awaiting Prioritization | In Process for 3/25/15
AMWG CR 2015 026 – SMT Functionality Display Portal Message when Report Can Not be Displayed in the SMT Portal Page |  | RMS Approved | Awaiting Prioritization | In Process for 3/25/15
AMWG CR 2015 027 – SMT Functionality Allow Specific Date Entry on the Export Report Screen |  | RMS Approved | Awaiting Prioritization | In Process for 3/25/15
AMWG CR 2015 028 – SMT Functionality Allow ESIIDs to be Copied and Pasted into the ESIID Box on the Usage Page |  | RMS Approved | Awaiting Prioritization | In Process for 3/25/15
AMWG CR 2015 029 – This Party Allow Third Parties to Utilize an API for On Demand Data Requests |  | RMS Approved | Awaiting Prioritization | In Process for 3/25/15
AMWG Change Requests (Cont.)

## Slide 14
AMWG Change Request | AMWG CR Document | Status | Estimated Delivery Date | Estimated Cost
AMWG CR 2015 030 – Support multiple RORs during CSV file meter upload | Draft in AMWG Review 2/20/15 |  |  | 
AMWG CR 2015 031 – Allow only current ROR for account registration validation and meter add validation | Draft in AMWG Review 2/20/15 |  |  | 
AMWG CR 2015 032 – Support SFTPS protocol for SMT integration | Draft in AMWG Review 2/20/15 |  |  | 
AMWG CR 2015 033 – Provide user id and password rules up front on UI registration page | Draft in AMWG Review 2/20/15 |  |  | 
AMWG CR 2015 034 – Display the day of the week in addition to the date on usage reports | Draft in AMWG Review 2/20/15 |  |  | 
AMWG CR 2015 035 - Provide a customer-selected option to receive a monthly usage report via email | Draft in AMWG Review 2/20/15 |  |  | 
AMWG CR 2015 036 – Rename Overview tab to Home | Draft in AMWG Review 2/20/15 |  |  | 
AMWG CR 2015 037 – Remove SMT Demo from Private Site for REPs, TDSPs, and Third Parties | Draft in AMWG Review 2/20/15 |  |  | 
AMWG CR 2015 038 – Provide a “Hold” capability on Third Party accounts to reactivate usage until the Third Party has integrated with FTPS and API | Draft in AMWG Review 2/20/15 |  |  | 
AMWG CR 2015 039 – Provide more detail for Third Party Agreement Invitation Error Messages | Draft in AMWG Review 2/20/15 |  |  | 
AMWG Change Requests (Cont.)

## Slide 15: Prioritization of SMT AMWG CRs

## Slide 16: Q&A Monthly SMT Reports to AMWG Data Through January 2015