|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report February 2015 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 245 active generation interconnection requests totaling over 63,000 MW. This includes over 25,300 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $421.3 Million. - Transmission Projects endorsed in 2015 total $103.8 Million. - All projects (in engineering, routing, licensing and construction) total approximately $6.15 Billion. - Transmission Projects energized in 2015 total about $32.8 Million. - ERCOT installed wind capacity, as reported through the registration process, currently totaling 12,575 MW (10,895 MW Non-Coastal and 1,680 MW Coastal). |  |  |  |  |  |  |  |

Table of Contents

1.	Regional Planning Group Project Reviews	1

2.	Asynchronous Tie Interconnection	2

3.	Planning Model Activities	2

4.	Other Notable Activities	3

# Regional Planning Group Project Reviews

- Duke-American Transmission Company has submitted the Phoenix project. This is a Tier 2 project that is estimated to cost $39 million. This project is currently under ERCOT independent review.

- CPS Energy and LCRA Transmission Services Corporation (TSC) have jointly submitted the Transmission System Additions project to address the reliability needs in the northeast San Antonio area. This is a Tier 1 project that is estimated to cost $237.3 million. This project is currently under ERCOT independent review.

- CenterPoint Energy has submitted the Jones Creek project. This is a Tier 1 project that is estimated to cost $79.8 million. ERCOT has issued the independent review report on Nov. 13th. The project was endorsed by the Board of Directors on Feb. 10, 2015.

- LCRA has submitted the Goldthwaite-Lampasas Line Upgrades Project. This is a Tier 1 project that is estimated to cost $71 million. This project is currently under ERCOT independent review.

- TNMP has submitted the Flat Top 138 kV Interconnection project. This is a Tier 2 project that is estimated to cost $29 million. This project is currently under ERCOT independent review.

- Garland Power & Light has submitted the Greenville 138 kV tie project. This is a Tier 2 project that is estimated to cost $27 million. This project is currently under ERCOT independent review.

- LCRA has submitted the Luling–Nixon 69 kV overhaul project. This is a Tier 3 project that is estimated to cost $18 million. This project has been submitted for RPG comments.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In-Progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

The short term calendar of major planning model events follows:

- Feb 25, 2015	Posted 2015 Update Cycle 1 updated cases and MODTPIT

- Mar 4, 2015	NMMS Snapshot for 2015 Update Cycle 2 (Build 16DSA and 16DSB) – ERCOT and SSWG will possibly change name from “Update Cycle” and also change the 16DSA and 16DSB naming convention to denote the year the cases were built and remove “DSA” and “DSB” designations

- Mar 13, 2015	Post 2015 Update Cycle 1 Contingency Files and Planning Data Dictionary

- Mar 25, 2015	Update MOD with NMMS snapshot

- Mar 30, 2015	Begin building all cases currently known as “DSA” and “DSB”

- Jun 19, 2015	Post all cases currently known as “DSA” and “DSB”

The following table shows updates since last month of interconnection projects that met Planning Guide section 6.9 (1) and were either modeled or not modeled based on submitted RARF data in accordance with Planning Guide section 6.9 (2).  A non-null value in the Project ID column signifies that the project was modeled and a null value means it was not modeled.  The Notes column may provide further explanation.

# Other Notable Activities

- The System Protection Working Group has begun building the 2015 Current Year case with a proposed completion date of Mar 27, 2015.

- ERCOT has commenced work on the 2015 Regional Transmission Plan; ERCOT is currently working on preparing the start cases for the reliability analysis phase.

- ERCOT has completed a review of all suspect model data that was identified by the consultant for the Small Signal Stability study by cross-checking the most recent RARF submissions with the ERCOT Dynamics Working Group data sets.  The appropriate resource owners have been notified of any model data issues and have been requested to submit model updates in the RARF as necessary.