## Sheet1
TX SET Meeting Notes / Action Items
February 18-19, 2015
Agenda Item: | Decision / Resolution | Action Items :
January 2015 Meeting Notes | No changes were made to the notes. | The Chair will have the notes posted to the Janauary 21st meeting page key documents.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
668NPRR-01 Updates to Texas SET Implementation Guide Process--ERCOT Comments and PRS Review | ERCOT explained the ERCOT comments and noted that the changes allowed ERCOT to show the Impact Analysis with a zero dollar amount. Without the ERCOT comments, ERCOT would be required to remove links from the webpages that Texas SET never intended to have happen.
Texas Standard Electronic Transaction Implementation Guides Change Control Process Review | The Texas SET Working Group completed a final review and updated the document where necessary. | The Chair will send the document to ERCOT Market Rules for review and submission to RMS for a vote.
RMGRR126, Additional ERCOT Validations for Customer Billing Contact Information File—RMS update; ERCOT IA to be revised and returned to RMS in March | The Texas SET Chair gave an update to the group on the status of the RMGRR.
Flight 0215 Testing Update | ERCOT presented an update on the current Market Test Type
RMGRR128,Reinstate Critical Care Status After Resolution of an Inadvertent Gain (Issue 139)--RMS Update—RMS approved | The Texas SET Chair gave an update to the group on the status of the RMGRR. The RMS Chair noted that the Impact Analysis for this RMGRR would also be returned to RMS for a vote in March.
• Tariff Project 41121--RMG Section 7 Market Processes updates related to TDSP tariff changes effective Jan 2015 • Action items— TDSPs to verify each TDSP specific information • DNP meter seal color • TNMP to verify the tariff language for Self-Selected Switch charges •Safety Net timelines—On Hold | The Texas SET Working Group completed a final review and updated the document where necessary. After meeting was ajourned, the chair noticed that the RMGRR contained a note that stated the name of the timing matrix would be changed. The RMS Chair and TX SET Chair modified the file name of the timing matrix and updated the RMGRR with that name (Appendix D3 TDSP’s Discretionary Services for Metered and Un-Metered Premises Matrix). | The Chair will put the RMGRR draft into the revision form and send the document to ERCOT Market Rules for review and submission to RMS for a vote. The Chair will also send the Appendix D3 TDSP’s Discretionary Services for Metered and Un-Metered Premises Matrix to ERCOT Market Rules as a part of the RMGRR.
Texas Market Test Plan Review | No review was conducted this month.
Texas SET Procedures Document Review | The Texas SET Working Group completed a final review and updated the document where necessary. | The Chair will send the document to ERCOT Market Rules for review and submission to RMS for a vote.
• RMS assignments--Discuss Approach and Requirements
• New Entrant Documentation—Procedures and Documentation Location o Method used to create ESI IDs o Method used to create 867_03 data for unmetered services o Difference between methods to update Premise Type and POLR Class in ERCOT system o Cycle assignments for unmetered services o Data updates required to align with loaded read dates at ERCOT o Use of TDSP supplemental address field | The Texas SET Working Group reviewed the action items and began discussions as how to approach the task. The Texas SET Working Group prepared an initial outline that will be used in determining an approach at future meetings. The discussions will be held on the second meeting day in the future.
• Add STTF Transition Documents (Lessons Learned) to key documents | This was included in the New Entrant discussions and will be included in those discussions.
• Add Master Customer List (MCL) guide back to the Texas SET Guides | The Texas SET Working Group reviewed the guide as a part of the New Entrant discussions and updated the document as needed. | The Chair will send the modified document to the Texas SET Working Group email distribution list.
Other Business
Issue 140--Requesting review of MVOs and how they interact with CSAs—CSA relationship cancelled prior to MVO to CSA completion--NRG update | NRG considered the Issue closed with no further action. The Texas SET Working Group Chair updated the Issue. | The Chair will send the updated issue to ERCOT for final posting to the website.
2015 Goals updated | The Texas SET Working Group Chair reviewed the modifications that RMS made to the goals.
Texas SET Release Discussion--on hold
REP Certification Matrix—Long-term solution--On hold
Next Meeting | March 9 Rm 168 - 10 Rm 168 ERCOT Met Center | It was requested that we move the March 9th meeting time to 11 AM instead of 10 AM. The Texas SET Working Group Chair will send the request to ERCOT Stakeholder Services to update the time on the meeting webpage.
Attendees
Diana Rehfeldt TNMP | Kathryn Thurman ERCOT | Paul Yockey ERCOT
Carolyn Reed CNP | Becky Taylor CNP | Kaci Jacobs TXU
Jim Lee AEP | Kyle Patrick NRG / Reliant | Chris Rowley ONCOR
Kathy Scott CNP
WebEx
Barbara Goubeaud EC Infosystems | Lindsay Butterfield ERCOT | Customized Energy Solutions
Pam Shaw SU | Amy Rafferty ESG | Mary Sithihao Stream Energy
Carla Marquez CES | Teresa Rodriquez Stream Energy