## Slide 1: SMT Update To AMWG
March 25, 2015

## Slide 2: SMT Outage Overview

## Slide 3: SMT Outage Overview
One of the redundant servers managing the SMT SAN (storage for the data warehouse) failed at 6 AM Saturday March 21, 2015. During the process of restoring that server the second redundant server failed later Saturday evening causing corruption on several application instances on SMT.
Faced with needing an additional few days continuation of the current outage to restore the legacy environment followed by a 3 day outage for the cutover, the decision was made to be more efficient and reduce the total number of outage days by moving directly into the cut over to the new legacy environment
The new legacy environment provides a greater redundancy model with 4 redundant servers in critical areas such as SAN management.

## Slide 4: SMT Infrastructure Refresh Update

## Slide 5: SMT Infrastructure Refresh Project Schedule
Hardware Acquisition, Rack Stack, Build, Install OS – Development, Test, Stage, Production and DR Environments
1st Quarter
2nd Quarter
2014
3rd Quarter
4th Quarter
2015
Network and Security – Development, Test, Stage, Production and DR Environments
Planning
UAT Test
Legend
Completed
In Process
Future Task
January
February
March
April
Go Live
3/25/15 9:00 PM – 3/27/15 7:00 AM
2.5 Day Outage Required
Configuration, SMT Solution Build, and TDSP Integration
SIT Test
Stage
All Five Environments
Production
Disaster Recovery
UAT Test
Configuration, SMT Solution Build, and TDSP Integration
SIT Test
UAT Test
Configuration, SMT Solution Build, and TDSP Integration
SIT Test
2/24/15 – 2/26/15
HAN and ODR
2 Day
Intermittent
Outage
Required
Legacy SMT DR Environment Available
Until New Infrastructure is Hardened

## Slide 6: Status Update of AMWG Change Requests

## Slide 7: Status of AMWG Change Requests
Summary: 39 Total AMWG Change Requests Including 9 Delivered, 1 Ready for Delivery in the Next Release, 19 RMS Approved and 10 AMWG Drafts in Review 2/20/15
9 AMWG Change Requests Delivered 2014
  SMT Reporting AMWG CR 2013 002, AMWG CR 2013 005, AMWG CR 2013 006, AMWG CR 2013 007, and AMWG CR 2013 009 – Delivered Q2 2014
  ROR Historical Backfill and ROR New Customer Enrollment (Interim Solution) AMWG CR 2013 017 – Delivered Q2 2014
  ROR Vendor on Behalf AMWG CR 2013 016 – Delivered Q3 2014
  Usability Bypass redundant screen for Users with only one meter when accessing HAN device information AMWG CR 2013 012 – Delivered Q4 2014
  Usability Timeout on SMT takes user to “incorrect login” screen AMWG CR 2013 013 – Delivered Q4 2014
1 AMWG Change Request Awaiting Next Release to Implement in 2015
  AMWG CR 2013 014 Allow SMT user to toggle between 15-Minute Reads and Daily Reads without having to reset the date range

## Slide 8: Status of AMWG Change Requests
6 AMWG Change Requests Completed JDOA Estimation, Approved by RMS and Awaiting Prioritization
  AMWG CR 2013 001, AMWG CR 2013 003, AMWG CR 2013 004, AMWG CR 2013 008, AMWG CR 2013 011, and AMWG CR 2013 015
1 AMWG Change Request Completed JDOA Estimation Awaiting RMS Review in April
  AMWG CR 2013 010
2 AMWG Change Request Disapproved by RMS
  AMWG CR 2014 018 and AMWG CR 2015 035
11 AMWG Change Requests Completed JDOA Estimation Awaiting AMWG Review 3/25/15
  AMWG CR 2015 019 through AMWG CR 2015 029
9 AMWG Change Requests Approved by AMWG 2/20/15 in Process of JDOA Estimation
  AMWG CR 2015 030 through AMWG CR 2015 039 (Except 2015 035 Disapproved by RMS listed above)

## Slide 9: Rough Order Of Magnitude (ROM) Estimate of Effort Classification
These are rough order of magnitudes and do not include project ramp-up and testing effort (SIT & UAT) and only assumes unit testing.
Actual estimates could vary significantly depending on requirements.
Ramp-up and testing would be 20 to 40% of the overall effort
Overall project cost will vary based on efficiency gains from packaging like functionality
Change Type | ROM
MINOR | 0 – 20 K
SMALL | 20 – 40 K
MEDUIM | 40 – 60 K
HIGH | 60 – 120 K
VERY HIGH | Over 120 K

## Slide 10
AMWG Change Request | AMWG CR Document | Status | Estimated Delivery Date | Estimated Cost
AMWG CR 2013 001 – Report for AMWG Data Monitoring – Data Completeness Measurements |  | Estimate Complete & RMS Approved 3/3/15 | Awaiting Prioritization | Small
AMWG CR 2013 002 – Reports for AMWG Data Monitoring – Data Timeliness Measurements |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 003 – Reports for AMWG Data Monitoring – Measurement of Percentage of Actual Meter Reads |  | Estimate Complete & RMS Approved 3/3/15 | Awaiting Prioritization | Small
AMWG CR 2013 004 – Reports for AMWG Data Monitoring – Measurement of Estimates |  | Estimate Complete & RMS Approved 3/3/15 | Awaiting Prioritization | Medium
AMWG CR 2013 005 – Reports for AMWG Data Monitoring – Number of SMT Help Desk Tickets Monthly by Ticket Type |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 006 – Reports for AMWG Data Monitoring – Availability of SMT API |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 007 – Reports for AMWG Data Monitoring – Availability of SMT FTPS |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 008 – Reports for AMWG Data Monitoring – Average Time to Deliver HAN Messages |  | Estimate Complete & RMS Approved 3/3/15 | Awaiting Prioritization | Small
AMWG CR 2013 009 – Reports for AMWG Data Monitoring – Number of Accounts by Type |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 010 – Reports for AMWG Data Monitoring – Number of Reports Requested by GUI (Portal) and Number of FTPS Accesses |  | JDOA Estimate Complete | Awaiting RMS Approval in April | Medium
AMWG Change Requests

## Slide 11
AMWG Change Request | AMWG CR Document | Status | Estimated Delivery Date | Estimated Cost
AMWG CR 2013 011 – Average Time from HAN Provision Request to Meter Ready Status |  | Estimate Complete & RMS Approved 3/3/15 | Awaiting Prioritization | Small
AMWG CR 2013 012 – Bypass redundant screen for Users with only one meter when accessing HAN device information |  | Implemented | Q4 2014 Delivered | Included in Third-Party
AMWG CR 2013 013 – Timeout on SMT takes user to “incorrect login” screen |  | Implemented | Q4 2014 Delivered | Included in Third-Party
AMWG CR 2013 014 – Allow SMT user to toggle between 15-Minute Reads and Daily Reads without having to reset the date range |  | Implemented | 2015 Next Release | Included in Usability
AMWG CR 2013 015 – Expand Daily Usage Graph to show 35 days of daily usage on the SMT GUI |  | Estimate Complete & RMS Approved 3/3/15 | Awaiting Prioritization | Medium
AMWG CR 2013 016 – Capability for RORs to grant access to vendors on their behalf to the ROR’s customers via API (energy usage, HAN messaging , and HAN provisioning) and FTPS files |  | Complete | Q3 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Backfill of Historical Usage Data for Existing Customers- “Interim”) | See Below CR 2013 017 Permanent | Implemented Interim | Q4 2013 Delivered | Included in SMT Work In Process
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Subscription for New Customer Historical Usage – “Interim”) | See Below CR 2013 017 Permanent | Implemented Interim | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT – Permanent Solution to Replace Interim Solution |  | JDOA Estimate To Begin After Q1 2015 | Awaiting JDOA Estimate | Will Be Estimated After New Infrastructure Implemented in Q1 2015
AMWG CR 2014 018 – Add Generation Data to the SMT Portal View |  | JDOA Estimate Completed | RMS Disapproved 3/3/15 | Medium
AMWG Change Requests (Cont.)

## Slide 12
AMWG Change Request | AMWG CR Document | Status | Estimated Delivery Date | Estimated Cost
AMWG CR 2015 019 – Relocate Various SMT User Guides from the Authenticated Site to the Unauthenticated Site |  | JDOA Estimate Completed | Awaiting AMWG Review 3/25/15 | Small
AMWG CR 2015 020 – Add Customer Type in the Customer Information Section in the View / Edit Agreement Page |  | JDOA Estimate Completed | Awaiting AMWG Review 3/25/15 | Medium
AMWG CR 2015 021 – Improve REP of Record Search Criteria During the Customer Registration Process |  | JDOA Estimate Completed | Awaiting AMWG Review 3/25/15 | Medium,
AMWG CR 2015 022 – Keep Selected ROR Visible During Customer Registration |  | JDOA Estimate Completed | Awaiting AMWG Review 3/25/15 | Small
AMWG CR 2015 023 – Allow Entry of Multiple ESIIDs During Customer Registration Process |  | JDOA Estimate Completed | Awaiting AMWG Review 3/25/15 | High
AMWG CR 2015 024 – Third Party Access Renew Energy Data Agreement After One Year |  | JDOA Estimate Completed | Awaiting AMWG Review 3/25/15 | Medium
AMWG CR 2015 025 – Third Party User Experience Add Identifying Data Fields in the Report Request Status Page |  | JDOA Estimate Completed | Awaiting AMWG Review 3/25/15 | High
AMWG CR 2015 026 – SMT Functionality Display Portal Message when Report Can Not be Displayed in the SMT Portal Page |  | JDOA Estimate Completed | Awaiting AMWG Review 3/25/15 | Minor
AMWG CR 2015 027 – SMT Functionality Allow Specific Date Entry on the Export Report Screen |  | JDOA Estimate Completed | Awaiting AMWG Review 3/25/15 | Small
AMWG CR 2015 028 – SMT Functionality Allow ESIIDs to be Copied and Pasted into the ESIID Box on the Usage Page |  | JDOA Estimate Completed | Awaiting AMWG Review 3/25/15 | Minor
AMWG CR 2015 029 – This Party Allow Third Parties to Utilize an API for On Demand Data Requests |  | JDOA Estimate Completed | Awaiting AMWG Review 3/25/15 | High
AMWG Change Requests (Cont.)

## Slide 13
AMWG Change Request | AMWG CR Document | Status | Estimated Delivery Date | Estimated Cost
AMWG CR 2015 030 – Support multiple RORs during CSV file meter upload |  | JDOA Estimate In Process |  | 
AMWG CR 2015 031 – Allow only current ROR for account registration validation and meter add validation |  | JDOA Estimate In Process |  | 
AMWG CR 2015 032 – Support SFTPS protocol for SMT integration |  | JDOA Estimate In Process |  | 
AMWG CR 2015 033 – Provide user id and password rules up front on UI registration page |  | JDOA Estimate In Process |  | 
AMWG CR 2015 034 – Display the day of the week in addition to the date on usage reports |  | JDOA Estimate In Process |  | 
AMWG CR 2015 035 - Provide a customer-selected option to receive a monthly usage report via email |  | JDOA Estimate on Hold | Disapproved by RMS 3/3/15 | 
AMWG CR 2015 036 – Rename Overview tab to Home |  | JDOA Estimate In Process |  | 
AMWG CR 2015 037 – Remove SMT Demo from Private Site for REPs, TDSPs, and Third Parties |  | JDOA Estimate In Process |  | 
AMWG CR 2015 038 – Provide a “Hold” capability on Third Party accounts to reactivate usage until the Third Party has integrated with FTPS and API |  | JDOA Estimate In Process |  | 
AMWG CR 2015 039 – Provide more detail for Third Party Agreement Invitation Error Messages |  | JDOA Estimate In Process |  | 
AMWG Change Requests (Cont.)

## Slide 14: AMWG CR 2015 019 through 029 Story Boards with Estimates Review

## Slide 15: Categorization of SMT RMS Approved AMWG CRs

## Slide 16: Q&A Monthly SMT Reports to AMWG Data Through February 2015