## Slide 1
Flight Testing Update
Paul Yockey
Flight Administrator
Retail Market Subcommittee
04/07/15

## Slide 2
Retail Market Subcommittee
04/07/15
Flight 0215
Flight 0215 Summary
Flight 0215 is 100% complete as of 04/06/15.
3 New CRs tested (Including 2 additional DUNS)
Existing CRs: 1 CR tested for Change of Service Provider, and 1 CR added new territories (1 CR withdrew from testing).
642 tasks were scheduled including connectivity (approximately a 42% decrease in tasks and approximately a 70% decrease in actual test days using the newly implemented Flight testing script pack)
Adhoc Period Testing: 4 Existing CRs are testing, 1 for Change of Service Provider, 2 for Bank Change, and 1 for additional DUNS.
Adhoc Period had 369 total task scheduled including connectivity.
Adhoc Testing is 89.02% complete as of 04/06/15.

## Slide 3
Retail Market Subcommittee
04/07/15
Flight 0215
Schedule
Flight 0215 signup began 01/07/15
Flight 0215 signup deadline was 01/14/15 (Adhoc, 03/27/15 for Current MPs Only, subject to Flight Administrator and TDSPs’ Approval)*
Connectivity kick-off conference call was 01/20/15
Flight kick-off conference call was 02/13/15
Day 1 transactions began 02/16/15
Flight 0215 concluded on 02/27/15 (Contingency/Adhoc Period until 04/17/15)

## Slide 4
Retail Market Subcommittee
04/07/15
Flight 0615
Schedule
Flight 0615 signup begins 05/13/15
Flight 0615 signup deadline is 05/20/15 (Adhoc, 07/17/15 for Current MPs Only, subject to Flight Administrator and TDSPs’ Approval)*
Connectivity kick-off conference call is 05/26/15
Flight kick-off conference call is 06/12/15
Day 1 transactions begin 06/15/15
Flight 0615 concludes on 06/26/15 (Contingency/Adhoc Period until 08/07/15)

## Slide 5
Retail Market Subcommittee
04/07/15
Questions?