## Change Request
CR Tracking Number | Value (H,M,L) | Cost/Effort $, $$, $$$) | Ranking (1,2…) | Short Description | Requestor | Company | Date Requested | Associated Issue # | Disposition by AMWG for CR | Disposition by RMS for CR | Disposition by AMWG for Estimate | Disposition by RMS for Estimate | Prioritization | Market Integration Affected? (Y/N) | Market Testing Required | Production Implementation date
2013 001 | TBD | TBD | TBD | Report for AMWG Data Monitoring – Data Completeness Measurements | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved - Submit to RMS for Approval | Estimate Approved at RMS 3/3/2015 |  | N | N | TBD - Needs Prioritization after estimation review
2013 002 | N/A | N/A | N/A | Reports for AMWG Data Monitoring – Data Timeliness Measurements | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved - Submit to RMS for Approval | Approved |  | N | N | Q2 2014 Delivered
2013 003 | TBD | TBD | TBD | Reports for AMWG Data Monitoring – Measurement of Percentage of Actual Meter Reads | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved - Submit to RMS for Approval | Estimate Approved at RMS 3/3/2015 |  | N | N | TBD - Needs Prioritization after estimation review
2013 004 | TBD | TBD | TBD | Reports for AMWG Data Monitoring – Measurement of Estimates | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved - Submit to RMS for Approval | Estimate Approved at RMS 3/3/2015 |  | N | N | TBD - Needs Prioritization after estimation review
2013 005 | N/A | N/A | N/A | Reports for AMWG Data Monitoring – Number of SMT Help Desk Tickets Monthly by Ticket Type | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved - Submit to RMS for Approval | Approved |  | N | N | Q2 2014 Delivered
2013 006 | N/A | N/A | N/A | Reports for AMWG Data Monitoring – Availability of SMT API | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved - Submit to RMS for Approval | Approved |  | N | N | Q2 2014 Delivered
2013 007 | N/A | N/A | N/A | Reports for AMWG Data Monitoring – Availability of SMT FTPS | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved - Submit to RMS for Approval | Approved |  | N | N | Q2 2014 Delivered
2013 008 | TBD | TBD | TBD | Reports for AMWG Data Monitoring – Average Time to Deliver HAN Messages | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Approval | Approved - Submit to RMS for Approval | Approved at RMS 3/3/2015 |  | N | N | TBD - Needs Prioritization after estimation review
2013 009 | N/A | N/A | N/A | Reports for AMWG Data Monitoring – Number of Accounts by Type | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved |  | N | N | Q2 2014 Delivered
2013 010 | TBD | TBD | TBD | Reports for AMWG Data Monitoring – Number of Reports Requested by GUI (Portal) and Number of FTPS Accesses | Jennifer Frederick | Direct Energy | 2013-05-23 | 2013-001 | Submit to RMS for approval | Submit to JDOA for Estimate | Approved - Submit to RMS for Approval | Estimate is Pending RMS approval to be added to RMS April agenda |  | N | N | TBD - Needs Prioritization after estimation review
2013 011 | TBD | TBD | TBD | Average Time from HAN Provision Request to Meter Ready Status | Steve Brightman | Southwest Energy Smarts | 2013-06-10 | Business Question, Req 11, 12 | Submit to RMS for approval | Submit to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved at RMS 3/3/2015 |  | N | N | TBD - Needs Prioritization after estimation review
2013 012 | N/A | N/A | N/A | Bypass redundant screen for Users with only one meter when accessing HAN device information | Steve Brightman | Southwest Energy Smarts | 2013-04-30 | 2013-002 | Submit to RMS for approval | Submit to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved |  | N | N | Q2 2014 Delivered
2013 013 | N/A | N/A | N/A | Timeout on SMT takes user to “incorrect login” screen | Steve Brightman | Southwest Energy Smarts | 2013-04-30 | 2013-003 | Submit to RMS for approval | Submit to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved |  | N | N | Q2 2014 Delivered
2013 014 | N/A | N/A | N/A | Allow SMT user to toggle between 15-Minute Reads and Daily Reads without having to reset the date range | John Schatz | TXU Energy | 2013-05-30 | N/A | Submit to RMS for approval | Submit to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved |  | N | N | Q2 2014 Delivered
2013 015 | TBD | TBD | TBD | Expand Daily Usage Graph to show 35 days of daily usage on the SMT GUI | John Schatz | TXU Energy | 2013-05-30 | N/A | Submit to RMS for approval | Submit to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved at RMS 3/3/2015 |  | N | N | TBD - Needs Prioritization after estimation review
2013 016 | N/A | N/A | N/A | Capability for RORs to grant access to vendors on their behalf to the ROR’s customers via API (energy usage, HAN messaging , and HAN provisioning) and FTPS files | Kyle Mille | Big Data Energy | 2013-06-12 | N/A | Submit to RMS for approval | Submit to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved |  | N | N | Q3 2014 Delivered
2013 017 | N/A | N/A | N/A | REP API for Energy Usage on SMT Backfill of Historical Usage Data for Existing Customers & Subscription for New Customer Historical Usage | Rob Bevill | Green Mountain Energy | 2013-07-02 | N/A | Submit to RMS for approval | Submit to JDOA for Estimate | Pending Estimate for Permanent Soluction | Pending Estimate |  | N | N | Interim Delivered Q2 2014. Permanent Solution needs Prioritization TBD
2014-018 | N/A | N/A | N/A | Make generation data viewable on the SMT portal | Rob Bevill/John Schatz | NRG Retail and TXU Energy | 2014-08-26 | 2014-001 | Approved ?? to be Submitted to RMS for approval | Submit to JDOA for Estimate | Approved - Submit to RMS for Approval | Estimate rejected at RMS 3/3/2015 Needs further review by AMWG. |  | N | N | Interim Delivered Q2 2014. Permanent Solution needs Prioritization TBD
2015-019 | TBD | TBD | TBD | Relocate various SMT user guides from the “authenticated” area of SMT to the “unauthenticated” area of SMT | John Schatz on behalf of AMWG | TXU Energy | 2015-01-05 | N/A | Approved 1/20 - Submitted to RMS for approval | Approved 2/3 - Submitted to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved at RMS 4/7/2015 |  | N | N | TBD
2015-020 | TBD | TBD | TBD | Update the Service Address of the Customer Information section of the View/Edit Customer Agreement page | John Schatz on behalf of AMWG | TXU Energy | 2015-01-05 | N/A | Approved 1/20 - Submitted to RMS for approval | Approved 2/3 - Submitted to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved at RMS 4/7/2015 |  | N | N | TBD
2015-021 | TBD | TBD | TBD | 3rd Party Access - Add Customer Type in the Customer Information section of the View/Edit Customer Agreement page | John Schatz on behalf of AMWG | TXU Energy | 2015-01-05 | N/A | Approved 1/20 - Submitted to RMS for approval | Approved 2/3 - Submitted to JDOA for Estimate | Estimate rejected - Need review by IBM | Pending Review |  | N | N | TBD
2015-022 | TBD | TBD | TBD | Keep selected REP of Record (ROR) visible during customer registration | John Schatz on behalf of AMWG | TXU Energy | 2015-01-05 | N/A | Approved 1/20 - Submitted to RMS for approval | Approved 2/3 - Submitted to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved at RMS 4/7/2015 |  | N | N | TBD
2015-023 | TBD | TBD | TBD | Allow entry of multiple ESI IDs during customer registration process | John Schatz on behalf of AMWG | TXU Energy | 2015-01-05 | N/A | Approved 1/20 - Submitted to RMS for approval | Approved 2/3 - Submitted to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved at RMS 4/7/2015 |  | N | N | TBD
2015-024 | TBD | TBD | TBD | 3rd Party Access - provide the ability within SMT to renew the Energy Data Agreement after the initial agreement duration | John Schatz on behalf of AMWG | TXU Energy | 2015-01-05 | N/A | Approved 1/20 - Submitted to RMS for approval | Approved 2/3 - Submitted to JDOA for Estimate | Approved - Submit to RMS for Approval | Rejected at RMS 4/7/2015 - Estimate should be 0 |  | N | N | TBD
2015-025 | TBD | TBD | TBD | 3rd Party User Experience – Add identifying data fields in the Report Request Status page | John Schatz on behalf of AMWG | TXU Energy | 2015-01-05 | N/A | Approved 1/20 - Submitted to RMS for approval | Approved 2/3 - Submitted to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved at RMS 4/7/2015 |  | N | N | TBD
2015-026 | TBD | TBD | TBD | Display portal message when report cannot be displayed in the SMT page. | John Schatz on behalf of AMWG | TXU Energy | 2015-01-05 | N/A | Approved 1/20 - Submitted to RMS for approval | Approved 2/3 - Submitted to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved at RMS 4/7/2015 |  | N | N | TBD
2015-027 | TBD | TBD | TBD | Allow specific date entry on the Export Report screen | John Schatz on behalf of AMWG | TXU Energy | 2015-01-05 | N/A | Approved 1/20 - Submitted to RMS for approval | Approved 2/3 - Submitted to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved at RMS 4/7/2015 |  | N | N | TBD
2015-028 | TBD | TBD | TBD | Allow ESIIDs to be copied and pasted into the ESIID box on the Usage page | John Schatz on behalf of AMWG | TXU Energy | 2015-01-05 | N/A | Approved 1/20 - Submitted to RMS for approval | Approved 2/3 - Submitted to JDOA for Estimate | Approved - Submit to RMS for Approval | Approved at RMS 4/7/2015 |  | N | N | TBD
2015-029 | TBD | TBD | TBD | Allow 3rd parties the ability to utilize an API for on-demand data requests/extracts | John Schatz on behalf of AMWG | TXU Energy | 2015-01-05 | N/A | Approved 1/20 - Submitted to RMS for approval | Approved 2/3 - Submitted to JDOA for Estimate | Reject at march meeting - Need further Review scheduled for April Meeting | Pending Review |  | Y | Y | TBD
2015-030 | TBD | TBD | TBD | Add meter functionality using CSV file with a ROR association does not work when the file contains meters of multiple RORs | John Schatz on behalf of AMWG | TXU Energy | 2015-02-11 | N/A | Approved 2/20 - Submitted to RMS for approval | Approved 3/3 - Submitted to JDOA for Estimate | Pending Estimate | Pending Estimate |  | N | N | TBD
2015-031 | TBD | TBD | TBD | Users are able to Add Meter on SMT Portal with Old RORs, should be allowed to add with Current ROR only | John Schatz on behalf of AMWG | TXU Energy | 2015-02-11 | N/A | Approved 2/20 - Submitted to RMS for approval | Approved 3/3 - Submitted to JDOA for Estimate | Pending Estimate | Pending Estimate |  | N | N | TBD
2015-032 | TBD | TBD | TBD | Request to provide support for SFTP protocol for FTP | John Schatz on behalf of AMWG | TXU Energy | 2015-02-11 | N/A | Approved 2/20 - Submitted to RMS for approval | Approved 3/3 - Submitted to JDOA for Estimate | Pending Estimate | Pending Estimate |  | N | N | TBD
2015-033 | TBD | TBD | TBD | Provide more intuitive or upfront information about user name and password requirements while registering | John Schatz on behalf of AMWG | TXU Energy | 2015-02-11 | N/A | Approved 2/20 - Submitted to RMS for approval | Approved 3/3 - Submitted to JDOA for Estimate | Pending Estimate | Pending Estimate |  | N | N | TBD
2015-034 | TBD | TBD | TBD | Show day of week (Monday, Tuesday … ) along with usage date on the portal and in reports | John Schatz on behalf of AMWG | TXU Energy | 2015-02-11 | N/A | Approved 2/20 - Submitted to RMS for approval | Approved 3/3 - Submitted to JDOA for Estimate | Pending Estimate | Pending Estimate |  | N | N | TBD
2015-035 | TBD | TBD | TBD | Option to have residential customers receive a usage data report delivered monthly via e-mail | John Schatz on behalf of AMWG | TXU Energy | 2015-02-11 | N/A | Approved 2/20 - Submitted to RMS for approval | Approved 4/7 - Submitted to JDOA for Estimate | Pending Estimate | Pending Estimate |  | N | N | TBD
2015-036 | TBD | TBD | TBD | Change ‘Overview’ tab to read ‘Home’ | John Schatz on behalf of AMWG | TXU Energy | 2015-02-11 | N/A | Approved 2/20 - Submitted to RMS for approval | Approved 3/3 - Submitted to JDOA for Estimate | Pending Estimate | Pending Estimate |  | N | N | TBD
2015-037 | TBD | TBD | TBD | Remove SMT demo video from private site | John Schatz on behalf of AMWG | TXU Energy | 2015-02-11 | N/A | Approved 2/20 - Submitted to RMS for approval | Approved 3/3 - Submitted to JDOA for Estimate | Pending Estimate | Pending Estimate |  | N | N | TBD
2015-039 | TBD | TBD | TBD | Improve Error Messages displayed in SMT Portal | John Schatz on behalf of AMWG | TXU Energy | TBD | 2015-04 | Approved 2/20 - Submitted to RMS for approval | Approved 3/3 - Submitted to JDOA for Estimate | Pending Estimate | Pending Estimate |  | N | N | TBD
2015-038 | TBD | TBD | TBD | Ability to hold a Third Party account for 60 days | John Schatz on behalf of AMWG | TXU Energy | 2015-02-11 | 2015-05 | Approved 2/20 - Submitted to RMS for approval | Approved 3/3 - Submitted to JDOA for Estimate | Pending Estimate | Pending Estimate |  | N | N | TBD

## Issues
Issue Tracking Number | Short Description | Requestor | Company | Date Requested | Disposition by AMWG | CR Required | Associated CR #
2014-001 | Make generation data viewable on the SMT portal | Rob Bevill/John Schatz | NRG Retail and TXU Energy | 8/18/02014 | Recommended for CR | Yes | 2014-018
2014-002 | Provide another mechanism to send and accept Customer Agreements / Federation | 3rd Party Market Tester | Presented by Andrea O’Flaherty-Brown | 2014-12-10 | Hold for future discussion | TBD | TBD
2014-003 | Improve TDSP Data / User functionality | 3rd Party Market Tester | Presented by Andrea O’Flaherty-Brown | 2014-12-11 | Hold for TDSP Review and discussion | TBD | TBD
2014-004 | Improve Error Messages displayed in SMT Portal | 3rd Party Market Tester | Presented by Andrea O’Flaherty-Brown | 2014-12-12 | Recommended for CR | Yes | TBD
2014-005 | Ability to hold a Third Party account for 60 days | 3rd Party Market Tester | Presented by Andrea O’Flaherty-Brown | 2014-12-13 | Recommended for CR | Yes | TBD
2014-006 | Add Customized Usage Data Buttons | 3rd Party Market Tester | Presented by Andrea O’Flaherty-Brown | 2014-12-14 | Not recommended for CR | N/A | N/A
2014-007 | Improve TDSP Data / User Functionality - Ability to view all the versions of a Day’s Reads with the date loaded | Ed Echols | Presented by Andrea O’Flaherty-Brown | 2014-12-15 | Hold for future discussion | TBD | TBD
2015-008 | Offer data usage reading in KVA and display Power Factor number | SMT Sharefeedback | Presented by Andrea O’Flaherty-Brown | 2015-01-20 | TDSP to contact Customer no CR to be created | N/A | N/A
2015-009 | Ability to view interval data for the entire billing period | SMT Sharefeedback | Presented by Andrea O’Flaherty-Brown | 2015-01-21 | SMT to Contact customer for clarification | TBD | TBD