## Sheet1
Report Discontinuance Tracking
NPRR, NOGRR, LPGRR | Title | Initial Posting Date | Current Status | Next Steps | Impact Following Approval | History
NPRR654 | Discontinue Ancillary Service Requirement Methodology Assessment Report | 2014-09-24 | Approved at Board 4/14/15 | Approved | Effective upon system implemetation | Previoulsy endorsed at WMS, ROS, PRS, and TAC
NPRR655 | Discontinue Contingency List Changes Due to Weather Report | 2014-09-24 | Approved at Board 4/14/15 | Approved | Effective upon system implemetation | Previously endorsed at WMS, ROS, PRS, and TAC
NPRR656 | Discontinue the Long-Term Weekly Peak Demand Forecast, 36 Month Resource Capacity Report, and Projected Transmission Constraints for Medium Term PASA Reports | 2014-09-24 | Withdrawn by MISUG 10/30/14 | N/A | N/A | After additional discussion with ERCOT Staff, the three reports recommended for discontinuance in NPRR656 are needed for compliance with subsection (d)(1) of P.U.C. Sub. R. 25.505, Resource Adequacy in the Electric Reliability Council of Texas Power Region.
NPRR657 | Discontinue Backup Control Plan Submittal Results, Dispatch Instructions Compliance Metrics, and Backup Control Plan Test Dates and Results Summary Reports | 2014-09-24 | Approved at Board 4/14/15 | Approved | Effective upon system implemetation | Previously endorsed at OWG, WMS, ROS, PRS, and TAC
NOGRR138 | Delete Grey Box for Reporting of Back-up Control Plan Submittal | 2014-09-24 | Tabled at TAC | TAC Consideration on 5/28/15 | Can take effect upon implementation of NPRR657, per NOGRR138 Impact Analysis | Initially tabled at OWG to hear back from Black Start Working Group; now endorsed by OWG and ROS
NPRR658 | Changes to Annual Reporting Requirements for RUC Payments Made to Resources with PPAs | 2014-09-24 | Approved by Board 2/10/15 | Approved | Effective March 1, 2015 | Previously endorsed at WMS, ROS, PRS and TAC
NPRR659 | Discontinue RMR Cost Data Deviation Requests/Responses Report | 2014-09-24 | Approved by Board 2/10/15 | Approved | Effective upon system implementation. --> Effective 1-2 months after Board approval, and a Market Notice will be sent out at least 30 days in advance before implementation, per NPRR659 Impact Analysis | Previously endorsed at WMS, ROS, PRS and TAC
NPRR661 | Discontinue Posting Profile Data Evaluation Report | 2014-09-24 | Approved at Board 4/14/15 | Approved | Effective upon upon implementation of LPGRR054 | Previously endorsed at ROS, PWG, WMS, PRS and TAC
LPGRR054 | Alignment with NPRR661, Discontinue Posting Profile Data Evaluation Report | 2014-09-24 | Approved at TAC 3/26/15 | Approved | Effective upon system implemetation | Previously endorsed at PWG and COPS