## Slide 1
Project Prioritization Review
May 14, 2015

## Slide 2: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR484 (ph 1b) – Revisions to CRR Credit Calculations and Payments | May 2015 | 2016-R1 | $300k-$400k | Luminant
NPRR484 (ph 2) – Revisions to CRR Credit Calculations and Payments | May 2015 | 2016-R1 | $100k-$120k | Luminant
NPRR210 – Wind Forecasting Change to P50, Synchronization with PRR841 | July 2015 | TBD | $45k-$55k | Morgan Stanley
NPRR219 – TSPs Must Submit Outages for Resource Owned Equipment and Clarification of Changes in Status of Transmission Element Postings | July 2015 | 2016-R3 | $300k-$400k | ERCOT
NPRR256 – Sync w/PRR787, Add Non-Compliance Language to QSE Perf. Standards | July 2015 | TBD | $120k-$135k | Luminant
NPRR419 – Revise Real-Time Energy Imbalance and RMR Adjustment Charge | July 2015 | 2015-R6 | $25k-$30k | ERCOT
NPRR495 – Changes to Ancillary Services Capacity Monitor | July 2015 | 2015-R6 | $105k-$125k | MIS User Group
NPRR556 – Resource Adequacy During Transmission Equipment Outage | July 2015 | 2015-R6 | $65k-$95k | Tenaska
RRGRR003 – Modifications to Improve Wind Forecasting | July 2015 | 2015-R6 | $35k-$50k | ERCOT
SCR783 – Outage Scheduler Enhancements | July 2015 | 2016-R3 | $600k-$800k | ERCOT
NPRR515 – Day-Ahead Market Self-Commitment of Generation Resources | Aug 2015 | 2016-R2 | $260k-$285k | ERCOT
NPRR617 – Energy Offer Flexibility | Aug 2015 | 2016-R1 | $60k-$80k | Calpine
NPRR620 – Collateral Requirements for Counter-Parties with No Load or Generation | Nov 2015 | 2016-R2 | $80k-$100k | ERCOT
    See Next Slides for More Detailed Questions and Comments
      Aging Revision Requests where importance/relevance input is requested

## Slide 3: Aging Revision Requests – ERCOT Comments and Requests for Market Input
Item | Description | Board Approval Date | Submitter | Target PPL Start Date | Comments / Questions | ERCOT Opinion
NOGRR084 | Daily Grid Operations Summary Report | 5/15/2012 | MISUG | Oct-2015 | Pending NOGRR to revise NOGRR084 language. ERCOT is the author so an Impact Analysis is in progress. | Do not start - pending revisions
NPRR181 | FIP Definition Revision | n/a | Luminant | TBD | TAC tabled the IA in 2011 pending FERC clarification of alignment of gas and electricity days. WMS reviewed the NPRR in 2014 and voted to continue tabling. To our knowledge this has not been addressed by FERC. | Should this continue to be tabled at TAC or should the language be removed? Any future FERC decision could be addressed with a new NPRR.
NPRR210 | Wind Forecasting Change to P50, Sync with PRR841 | 6/15/2010 | Morgan Stanley | Jul-2015 | Language issue, ERCOT can't implement as written. The P80 forecast required in the NPRR is not available in MMS, which was assumed in the IA. However it is available in EMS. If the market wishes to pursue we will ask for an updated IA. | Do not start – market input requested
NPRR256 | Sync with PRR787, Add Non-Compliance Language to QSE Performance Standards | 11/16/2010 | Luminant | Jul-2015 | 2 gray boxes still in Protocols: - 8.1.1.4.1 (6) ( c ) - 8.1.1.4.1 (7) | Is this still needed? Market input requested.
NPRR272 | Definition and Participation of Quick Start Generation Resources | 11/16/2010 | ERCOT | Jan-2016 | 6 gray boxes still in Protocols: - 3.8.3 (1) - 3.8.3 (2) - 3.8.3 (3) - 3.8.3 (7) - 3.9.1 (5)(b)(i)( C ) - 3.9.1 (5)(b)(i)(N) | ERCOT opinion is TBD
NPRR285 | Generation Resource Base Point Deviation Charge Corrections | 11/16/2010 | WMS | TBD | Section 6.5.7.4 (e) was inadvertently un-gray-boxed when the first phase of this NPRR was implemented. This caused it to be missed as part of the second (and final) phase. The submitter has agreed it is not urgent but would like to see it implemented in 2016. | Original NPRR was $30k-$40k. ERCOT is investigating to determine the cost of the remaining deliverable. No market action requested at this time.

## Slide 4: Aging Revision Requests – ERCOT Comments and Requests for Market Input
Item | Description | Board Approval Date | Submitter | Target PPL Start Date | Comments / Questions | ERCOT Opinion
NPRR327 | State Estimator Data Redaction Methodology | 4/17/2012 | ERCOT | Oct-2012 | This NPRR has been “On Hold” for an extended period. ERCOT has assessed the effort required to deliver and maintain this reporting and wishes to discuss the value proposition with the market. | Request market input on value proposition
NPRR455 | CRR Shift Factors Report | 7/17/2012 | MISUG | TBD | High cost item - market has asked that ERCOT not proceed until cost can be reduced considerably | Do not start - pending efficiencies with other efforts
NPRR484 | Revisions to Congestion Revenue Rights Credit Calculations and Payments - Phase 1b / 2 | 3/19/2013 | Luminant | May-2015 | Only Phases 1b and 2 remain - ERCOT would like to work with the market to provide clarifications to the NPRR language. | Do not start - market input requested
NPRR493 | Half-Hour RUC Clawback | 3/19/2013 | GDF Suez | TBD | Not sure if still needed given other market changes that have been implemented | Do not start - market input requested
NPRR515 | Day-Ahead Market Self-Commitment of Generation Resources | 7/16/2013 | ERCOT | Aug-2015 | Consider pushing to 2016 | Request market input on value given 2015 budget constraints
NPRR664 | Index Fuel Price | 12/9/2014 | RCWG | TBD | TAC asked that ERCOT not proceed until further notice | Do not start
OS-14 | Outage Scheduler Reporting Change | N/A | N/A | TBD | Add to reporting autotransformers with high side or low side breakers and open and single-ended transmission lines. | Due to estimated cost, ERCOT requests the market submit an SCR if this is still needed