## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity
May 14, 2015

## Slide 2: 2015 Project Update – Agenda
  Project Portfolio Update p. 3-5
    Recent/Upcoming Project Highlights
    2015 Release Targets
    2015 Project Spending Update
  Appendix
    Project Portfolio Gantt Chart p. 7-15
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent / Upcoming Project Highlights
2015 May Release In Flight
  SCR779 – Increase to the CRR Auction Transaction Limit
    Targeting end of May go-live – watch for market notices
2015 June Release – 6/13/2015 In Flight
  CMM Release
    NPRR559, NPRR597, NPRR601, NPRR639
2015 June Release – Week of 6/22/2015 In Flight
  2015 Market System Enhancements
    NPRR626, NPRR665, NPRR645, NPRR598, Max Shadow Price OBD
  NPRR543 – Message for Confirmed E-Tags
  NPRR589(b) – Ancillary Service Offers in the Supplemental Ancillary Services Market
  SCR774(b) – Enhancement to Outage Scheduler and Reports
  SCR775 – Posting Results of Real-Time Data in a Display Format
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2015 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR589(b) – S&B portion
SCR774(b) – Addition of Comments field
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
February 2/2 – 2/12 | March 3/23 – 3/27 | June |  | August 8/10 – 8/14 | September 9/21 – 9/25 | December 12/7 – 12/11
NPRR500 SCR772 | SCR778 SCR779 | NPRR559 NPRR597 NPRR601 NPRR639 | NPRR543 NPRR589(b) NPRR598 NPRR626 NPRR645 NPRR665 SCR774(b) SCR775 SCR779 OBD (Shadow Price Caps) | NPRR573 SCR771 | NPRR553 NPRR573 NPRR588 NPRR595 NPRR615 | NPRR419 NPRR495 NPRR556 RMGRR126 RRGRR003
2 | 2 | 13 |  | 1 | 5 | 5
2015 TBD Items (and month they became “TBD”)
E
E
E
E
I
P
NS
P
NS
NS
NS
NS
NS
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
E
E
E
E
Aug 2014 | Oct 2014 | Dec 2014 | Jan 2015 | Feb 2015 | Mar 2015 | Apr 2015
NOGRR084 | NPRR327 H | NPRR272, SCR777 H | NPRR210, NPRR664 | NPRR493 | NPRR256 | NPRR568-ph2, NPRR644
E
E
E
E
E
E
E
E
E
Late May
6/13 (CMM)
6/22 – 6/26

## Slide 5: 2015 Project Spending Update
2015 project budget = $21.65M
Reason: Minor Capital, Program Control and Common Infrastructure projects were re-allocated to departments that use those funds

## Slide 6: Business Integration Update – Appendix
  Appendix
    4/30/2015 Project Gantt
      In-flight items sorted by Project End Date
      “On Hold” projects listed separately
      “Not Started” items sorted by Project Start Date

## Slide 7
Project Portfolio Status – as of 4/30/2015

## Slide 8
Project Portfolio Status – as of 4/30/2015

## Slide 9
Project Portfolio Status – as of 4/30/2015

## Slide 10
Project Portfolio Status – as of 4/30/2015

## Slide 11
Project Portfolio Status – as of 4/30/2015

## Slide 12
Project Portfolio Status – as of 4/30/2015

## Slide 13
Project Portfolio Status – as of 4/30/2015

## Slide 14
Project Portfolio Status – as of 4/30/2015

## Slide 15
ERCOT Public