## Slide 1: SMT Update To AMWG
June 16, 2015

## Slide 2: Status Update of AMWG Change Requests

## Slide 3: Status of AMWG Change Requests
Summary: 42 Total AMWG Change Requests
9 AMWG Change Requests Delivered 2014
1 AMWG Change Request CR 2013-014 Toggle Between 15 Min Reads and Daily Reads Designed and Awaiting Next Release to Implement in 2015
1 RMS Tabled CR 2014-018 Add Generation Data to the SMT Portal View
1 AMWG Pushed Back as Defect CR 2015-022 Keep ROR Visible During Customer Registration
1 AMWG Change Request CR 2015-024 Renew Energy Data Agreement After One Year is In Queue for Release in 2015 at No Cost
1 AMWG Change Request CR 2015-041 CR Not in Inventory
6 AMWG Tabled
13 RMS Approved and AMWG Categorized Awaiting Packaging
7 RMS Approved and Awaiting AMWG Categorization
2 Awaiting JDOA Estimation CR 2015-40 CR 2015-42

## Slide 4: Rough Order Of Magnitude (ROM) Estimate of Effort Classification
These are rough order of magnitudes and do not include project ramp-up and testing effort (SIT & UAT) and only assumes unit testing.
Actual estimates could vary significantly depending on requirements.
Ramp-up and testing would be 20 to 40% of the overall effort
Overall project cost will vary based on efficiency gains from packaging like functionality
Change Type | ROM
MINOR | 0 – 20 K
SMALL | 20 – 40 K
MEDUIM | 40 – 60 K
HIGH | 60 – 120 K
VERY HIGH | Over 120 K

## Slide 5
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2013 001 – Report for AMWG Data Monitoring – Data Completeness Measurements |  | Estimate Complete & RMS Approved 3/3/15 | 2 Important Awaiting Packaging | Small (20-40)
AMWG CR 2013 002 – Reports for AMWG Data Monitoring – Data Timeliness Measurements |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 003 – Reports for AMWG Data Monitoring – Measurement of Percentage of Actual Meter Reads |  | Estimate Complete & RMS Approved 3/3/15 | 2 Important Awaiting Packaging | Small (20-40)
AMWG CR 2013 004 – Reports for AMWG Data Monitoring – Measurement of Estimates |  | Estimate Complete & RMS Approved 3/3/15 | 2 Important Awaiting Packaging | Medium (40-60)
AMWG CR 2013 005 – Reports for AMWG Data Monitoring – Number of SMT Help Desk Tickets Monthly by Ticket Type |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 006 – Reports for AMWG Data Monitoring – Availability of SMT API |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 007 – Reports for AMWG Data Monitoring – Availability of SMT FTPS |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 008 – Reports for AMWG Data Monitoring – Average Time to Deliver HAN Messages |  | Estimate Complete & RMS Approved 3/3/15 | 3 Nice to Have Awaiting Packaging | Small (20-40)
AMWG CR 2013 009 – Reports for AMWG Data Monitoring – Number of Accounts by Type |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 010 – Reports for AMWG Data Monitoring – Number of Reports Requested by GUI (Portal) and Number of FTPS Accesses |  | Estimate Complete & RMS Approved 5/6/15 | Awaiting Categorization | Medium (40-60)
AMWG Change Requests

## Slide 6
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2013 011 – Average Time from HAN Provision Request to Meter Ready Status |  | Estimate Complete & RMS Approved 3/3/15 | 3 Nice to Have Awaiting Packaging | Small (20-40)
AMWG CR 2013 012 – Bypass redundant screen for Users with only one meter when accessing HAN device information |  | Implemented | Q4 2014 Delivered | Included in Third-Party
AMWG CR 2013 013 – Timeout on SMT takes user to “incorrect login” screen |  | Implemented | Q4 2014 Delivered | Included in Third-Party
AMWG CR 2013 014 – Allow SMT user to toggle between 15-Minute Reads and Daily Reads without having to reset the date range |  | Designed | 2015 Next Release | Included in Usability
AMWG CR 2013 015 – Expand Daily Usage Graph to show 35 days of daily usage on the SMT GUI |  | Estimate Complete & RMS Approved 3/3/15 | 2 Important Awaiting Packaging | Medium (40-60)
AMWG CR 2013 016 – Capability for RORs to grant access to vendors on their behalf to the ROR’s customers via API (energy usage, HAN messaging , and HAN provisioning) and FTPS files |  | Implemented | Q3 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Backfill of Historical Usage Data for Existing Customers- “Interim”) | See Below CR 2013 017 Permanent | Implemented Interim | Q4 2013 Delivered | Included in SMT Work In Process
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Subscription for New Customer Historical Usage – “Interim”) | See Below CR 2013 017 Permanent | Implemented Interim | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT – Permanent Solution to Replace Interim Solution |  | JDOA Estimate To Begin After New Infrastructure Refresh Complete | Awaiting Evaluation of New SMT Infrastructure to Determine if any Additional Work is Needed to meet CR Requirements | Will Be Estimated After New Infrastructure Implemented in Q1 2015
AMWG CR 2014 018 – Add Generation Data to the SMT Portal View |  | JDOA Estimate Completed | RMS Tabled 6/2/15 | Medium (40-60) Graph and Table Small (20-40) Table Only
AMWG Change Requests (Cont.)

## Slide 7
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2015 019 – Relocate Various SMT User Guides from the Authenticated Site to the Unauthenticated Site |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | Small (20-40)
AMWG CR 2015 020 – Add Customer Type in the Customer Information Section in the View / Edit Agreement Page |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | Medium (40-60)
AMWG CR 2015 021 – Improve REP of Record Search Criteria During the Customer Registration Process |  | Estimate Complete & RMS Approved 5/6/15 | Awaiting AMWG Categorization | Medium,(40-60)
AMWG CR 2015 022 – Keep Selected ROR Visible During Customer Registration |  | JDOA Estimate Completed | Push Back as Defect | Small (20-40)
AMWG CR 2015 023 – Allow Entry of Multiple ESIIDs During Customer Registration Process |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | High (60-120)
AMWG CR 2015 024 – Third Party Access Renew Energy Data Agreement After One Year |  | JDOA Estimate Completed | 1 Critical Awaiting Delivery in 2015 | 0 Dollar
AMWG CR 2015 025 – Third Party User Experience Add Identifying Data Fields in the Report Request Status Page |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | High (60-120)
AMWG CR 2015 026 – SMT Functionality Display Portal Message when Report Can Not be Displayed in the SMT Portal Page |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | Minor (0-20)
AMWG CR 2015 027 – SMT Functionality Allow Specific Date Entry on the Export Report Screen |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | Small (20-40)
AMWG CR 2015 028 – SMT Functionality Allow ESIIDs to be Copied and Pasted into the ESIID Box on the Usage Page |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | Minor (0-20)
AMWG CR 2015 029 – This Party Allow Third Parties to Utilize an API for On Demand Data Requests |  | Estimate Complete & RMS Approved | Awaiting AMWG Categorization | High (60-120)
AMWG Change Requests (Cont.)

## Slide 8
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2015 030 – Support multiple RORs during CSV file meter upload |  | JDOA Estimate Completed | AMWG Tabled 5/19/15 | High (60-120)
AMWG CR 2015 031 – Allow only current ROR for account registration validation and meter add validation |  | JDOA Estimate Completed | AMWG Tabled 5/19/15 | High (60-120)
AMWG CR 2015 032 – Support SFTP protocol for SMT integration |  | Investigation Complete | AMWG Tabled 5/19/15 Get Further Info | High (60-120)
AMWG CR 2015 033 – Provide user id and password rules up front on UI registration page |  | IBM Re-estimate with Hardcode vs Roll Over | AMWG Tabled 5/19/15 for new Estimate | Medium (40-60)
AMWG CR 2015 034 – Display the day of the week in addition to the date on usage reports |  | JDOA Estimate Completed | AMWG Tabled 5/19/15 | Medium (40-60)
AMWG CR 2015 035 - Provide a customer-selected option to receive a monthly usage report via email |  | Estimate Complete & RMS Approved | Awaiting AMWG Categorization | Medium (40-60)
AMWG CR 2015 036 – Rename Overview tab to Home |  | Estimate Complete & RMS Approved | Awaiting AMWG Categorization | Minor (0-20)
AMWG CR 2015 037 – Remove SMT Demo from Private Site for REPs, TDSPs, and Third Parties |  | Estimate Complete & RMS Approved | Awaiting AMWG Categorization | Minor (0-20)
AMWG CR 2015 038 – Provide a “Hold” capability on Third Party accounts to reactivate usage until the Third Party has integrated with FTPS and API |  | JDOA Estimate Completed | AMWG Tabled 5/19/15 | High (60-120)
AMWG CR 2015 039 – Provide more detail for Third Party Agreement Invitation Error Messages |  | Estimate Complete & RMS Approved | Awaiting AMWG Categorization | Medium (40-60)
AMWG CR 2015 040 – Improve SMT Administration Functionality for TDSPs, RORs, Third Parties, and Businesses |  | JDOA Estimate in Process | Awaiting Estimation | 
AMWG Change Requests (Cont.)

## Slide 9
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2015 041 – |  |  |  | 
AMWG CR 2015 042 – Automate Machine to Machine Consumption of Third Party Agreement Information |  | JDOA Estimate in Process | Awaiting Estimation | 
AMWG Change Requests (Cont.)

## Slide 10: Continuation of Categorization of SMT RMS Approved AMWG CRs

## Slide 11: Q&A Monthly SMT Reports to AMWG Data Through May 2015

## Slide 12: SMT May and June Outages

## Slide 13: SMT May and June Outages
Two File Processing Incidents
May 26th File Processing did not Complete until 3:00 AM CST May 27
May 31st File Processing did not Complete until 12:30 AM CST June 1
Cause – New infrastructure monitoring tools along with tuning of capacity and parameters
Remediation – Tuned monitoring tools and file processing capacity parameters. Also added manual monitoring for initial new infrastructure start up period.
Market Notices – Should have been sent and process has been corrected to support improved Market Notice compliance

## Slide 14: SMT May and June Outages
Two Website Portal Services Incidents
June 5th SMT website portal services were down from 8:00 AM CST until 11:59 AM CST
  No file processing was affected
  Cause – LDAP file system corruption
  Remediation – Reload LDAP file system from backup
  Market Notices were sent during and upon completion of this event
June 9th SMT website portal services intermittently were down from 11:30 AM CST until 2:30 PM CST
  No file processing was affected
  Cause – Hung threads on one portal node
  Remediation – Restart server and provide more capacity for service
  Market Notice was sent for this event

## Slide 15: SMT Market Notices

## Slide 16: SMT Market Notices
To Follow Guidelines as Specified in the SMT SLOs
Requirements for Outage Notification
Listservs for Notification
COPS Communication Market Guide Rules