## Meeting Notes
TDTWG Meeting Notes / Action Items
2015-06-10
Agenda Item: | Decision / Resolution | Action Items :
May Meeting Notes | TDTWG Leadership to follow with ERCOT -Client Service on email request. | MPs will review/approve in the July meeting along with June meeting notes
ERCOT System Instances (Outages and Failure) review November and December | Review Dave Pagliai with ERCOT provided the System Instances (Outages and Failure) for May. Was presented to RMS on June 2 meeting. No SLA missed, only one incidents on 5/15/15 with Find EsIID slow response (72 mins) issue resolved. Last 2 months APS change was due to database upgrade and has been working with the vendor to fix the issue. No Business Processes impacted.The reporting issue from late last year - ERCOT will migrate permanent fix in June.
Review MarkeTrak Monthly Performance | API Query list - 12 due to database upgrade.API update consistently up and on target. GUI response continues to be good. | New method of measuring - will be discussed in upcoming MTTF scheduled meetings June 15th and July 13th. ERCOT will pull numbers from this July and will present in August MTTF meeting.
MarkeTrak Premature Transition Issue Update - Action Item from May | ERCOT will provide answers in the next MTTF and TDTWG meeting on July 13th. Additional questions regarding IE11 support. ERCOT confirm no change to R5 only to begin supporting IE11 and to confirguarion guide. ERCOT confirmed will provided updates at TAC for IE.
1st Quarter Performance Measures | Performance Measures - ERCOT shared that performance measures are filed no later 45 days following the end of the quarter. Added that numbers for Q1 really good. All 100% with Switches,Standard MVI, Same Day MVI, MVOs and esiid create/maintain. Will provide Q2 on August 18th meeting.
ERCOT Test Environment | SCR - Posted with SCR #786 went and has been submitted via PRS list. and will be at next months PRS for language review. Updates on the SCR can be obtain by joining PRS listserv Next steps: • PRS on 7/16 language review • PRS on 8/13 for IA review • TAC on 8/27 • ERCOT Board on 10/13 • **Effective date 11/1/15". Next steps: • PRS on 7/16 language review • PRS on 8/13 for IA review • TAC on 8/27 • ERCOT Board on 10/13 • **Effective date 11/1/15". | TDTWG leadership to Add as topic to the Agenda monthly under the **Ad hoc items
NAESB Upgrade Recommendation | Catherine -provided a presentation with background of the initial focus NAESB upgrade and ERCOT's recommendation to post poning the effort until regulatory,security or technology requirements necessitate the change. At that time a new SCR should be submitted to upgrade the latest version of NAESB (current version is 3.0). Note : if the market feels that the benefits outweight the cost, then ERCOT will be happy to faciliate the creation of the new SCR. | TDTWG leadership to present at next RMS (RMS)
Ad Hoc items | No additional items to discuss.
Next Meeting | July 15th WebEx
Attendees- WebEx
Vikrum Gupta ERCOT | Dave Pagliai (ERCOT)
Isabelle Durham CNP | Lindsay Butterfield
Carolyn Reed CNP
Monica Jones NRG/Reliant
Jim Lee (AEP)
Kaci Jacobs- (TXU Energy)
Diane Rehfeldt (TNMP)
Catherine Meiners (ERCOT)