## Sheet1
TX SET Meeting Notes / Action Items
April 22nd - 23rd, 2015
Agenda Item: | Decision / Resolution | Action Items :
March 2015 Meeting Notes | No Changes were made | The TX SET Chair will have the notes posted to the ERCOT website.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
RMS Updates
668NPRR-01 Updates to Texas SET Implementation Guide Process—Remains tabled at TAC to allow voting alignment with the changes made to the Texas SET Procedures and the Texas SET Implementation Guides Change Control Process documents.—RMS approved both. | The Chair provided the update from RMS.
RMGRR130, Alignment of Section 7, Market Processes, with TDSP Terms and Conditions Tariff Effective 01/15/2015—Tabled at RMS—Review RMS corrections and other comments | Texas SET reviewed and finalized the comments and documents to send to RMS. | The Chair will send the updated documents to ERCOT to post as a voting items for the next RMS meeting.
Flight 0215 Testing Update
• Adhoc Testing and Penny Test Experiences Incurred During Flight 0215 Discussion | Texas SET discussed made modifications for the changes proposed to be made to the Flight Schedule and TMTP. | The Chair will send the updated documents to ERCOT to post as a voting items for the next RMS meeting.
Texas Market Test Plan Review
• Review ERCOT updates • Review prior, during and after responsibility Sections • General Document Review | Texas SET reviewed and made modifications to the responsibility matrix created by NRG. | The Chair will send the updated responsibility spreadsheet to ERCOT and NRG to incorporate the spreadsheet results into the TMTP. ERCOT will continue to modify the ERCOT specific sections.
RMS assignments--Discuss Approach and Requirements
• New Entrant Documentation—Procedures and Documentation Location | No update
• Add Master Customer List (MCL) guide back to the Texas SET Guides | No update
Discussion Items on Hold
Texas SET Release Discussion | No update
RMG Safety Net timelines | No update
REP Certification Matrix—Long-term solution | No update
Next Meeting | May 20th Rm 168 -21st Rm 101 ERCOT Met Center
Attendees
Diana Rehfeldt TNMP | Jim Lee AEP | Lindsay Butterfield ERCOT
Kathryn Thurman ERCOT | Taylor Woodruff ONCOR | Carolyn Reed CNP
Paul Yockey ERCOT | Kyle Patrick Reliant | Chris Rowley ONCOR
Becky Taylor CNP | Pam Shaw SU | Kathy Scott CNP
Kaci Jacobs TXU
WebEx
Amy Rafferty ESG | Debbie McKeever ONCOR | Barbara Goubeaud EC InfoSystems
Jasmine Thom CES | Kim Wall PPL Solutions | Paula Shadle NEC
Suzy Clifton ERCOT | Deborah Croce | Neela Neebar EC InfoSystems