## Slide 1
Review of Aging Projects
July 16, 2015

## Slide 2: Project Prioritization – Agenda
  Discussion Approach
  Revision Request Project Funding History
  2015 Funding Challenges
  Upcoming Project Starts
  Aging Items
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Discussion Approach
Process for Reviewing Aging Items
  Reason for the Revision Request
  Remaining Gray Boxes
  Business Case and/or CBA
  Major Cost Drivers
  ERCOT Input
    Opinion on need based on current state
    Options for more efficient implementation
Reminder
  These items are Board-approved so we would expect to implement all of them unless a compelling case can be made that the business case has changed or the investment no longer makes sense
A supporting doc with this information will be shared prior to the PRS meeting

## Slide 4: Revision Request Project Funding History
Year | Budget | Actual (through 5/31/2015) | Forecast Spend on Specific RRs
2013 | $3.0M | $2.5M | n/a
2014 | $4.0M | $2.4M | n/a
2015 | $4.0M | $1.1M | $1.4M
2016 | $4.0M | n/a | $2.5M
2017 | $4.0M | n/a | $0.0M
2018 | $4.0M | n/a | $0.0M
Comments
  2016 revision request funds are 60+% committed
    This can change as priorities shift
  2017 / 2018 revision request funds are uncommitted
  Ability to fund “game changers” is limited within the current budget

## Slide 5: 2015 Funding Challenges
Every year, ERCOT evaluates project spending to determine how to maximize the value of our project funding
  In some years, that can mean accelerating activities that would take place early in the subsequent year to better manage future year demand
  In 2015, the challenge is to maintain momentum on important efforts that have material budgets
    EMS Upgrade (go-live in 2016)
    MMS/OS Tech Refresh (complete)
    NMMS Upgrade (go-live in 2016)
    CIP Compliance (multiple efforts with go-lives in 2015)
    2015 Market System Enhancements – NPRR626 (complete)
  One option that can be leveraged is to fund vendor project work with unused vendor O&M funds
    Examples being considered in 2015: NPRR219, NPRR515

## Slide 6: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR495 – Changes to Ancillary Services Capacity Monitor | July 2015 | 2016-R1 | $105k-$125k | MIS User Grp
NPRR515 – Day-Ahead Market Self-Commitment of Generation Resources | July 2015 | 2016-R1 | $260k-$285k | ERCOT
NPRR556 – Resource Adequacy During Transmission Equipment Outage | July 2015 | 2015-R6 | $65k-$95k | Tenaska
RMGRR126 – Add’l ERCOT Validations for Customer Billing Contact Information File | July 2015 | 2015-R6 | $35k-$55k | TX SET WG
RRGRR003 – Modifications to Improve Wind Forecasting | Aug 2015 | 2015-R6 | $35k-$50k | ERCOT
NPRR419 – Revise Real-Time Energy Imbalance and RMR Adjustment Charge | Aug 2015 | 2015-R6 | $25k-$30k | ERCOT
NPRR617 – Energy Offer Flexibility | Aug 2015 | 2016-R1 | $60k-$80k | Calpine
NPRR662 – Proxy Energy Offer Curves | Aug 2015 | 2016-R2 | $80k-$120k | TIEC
NPRR620 – Collateral Requirements for Counter-Parties with No Load or Generation | Nov 2015 | 2016-R2 | $80k-$100k | ERCOT
NPRR679 – ONOPTOUT for RUC Given After the Adjustment Period | Nov 2015 | 2016-R2 | $15k-$20k | Tenaska
NPRR683 – Revision to Available Credit Limit Calculation | Nov 2015 | 2016-R2 | $40k-$50k | Luminant
    See Next Slides for More Detailed Questions and Comments
    Aging Revision Requests where importance/relevance input is requested

## Slide 7: Aging Revision Requests – ERCOT Comments and Requests for Market Input
Item | Description | Board Approval Date | Submitter | Target PPL Start Date | Comments / Questions | ERCOT Opinion
NOGRR084 | Daily Grid Operations Summary Report | 5/15/2012 | MISUG | TBD | Pending NOGRR to revise NOGRR084 language. ERCOT is the author so an Impact Analysis is in progress. | Do not start - pending revisions ERCOT finalizing IA of revised NOGRR
NPRR181 | FIP Definition Revision | n/a | Luminant | TBD | TAC tabled the IA in 2011 pending FERC clarification of alignment of gas and electricity days. WMS reviewed the NPRR in 2014 and voted to continue tabling. To our knowledge this has not been addressed by FERC. | Market reviewing need Submitter has indicated support to eliminate
NPRR210 | Wind Forecasting Change to P50, Sync with PRR841 | 6/15/2010 | Morgan Stanley | TBD | Language issue, ERCOT can't implement as written. The P80 forecast required in the NPRR is not available in MMS, which was assumed in the IA. However it is available in EMS. If the market wishes to pursue we will ask for an updated IA. | ERCOT reviewing language to determine changes required to ensure implementation meets the intent of the NPRR ERCOT has identified a missed impact
NPRR256 | Sync with PRR787, Add Non-Compliance Language to QSE Performance Standards | 11/16/2010 | Luminant | TBD | 2 gray boxes still in Protocols: - 8.1.1.4.1 (6) ( c ) - 8.1.1.4.1 (7) | Market reviewing need
NPRR272 | Definition and Participation of Quick Start Generation Resources | 11/16/2010 | ERCOT | TBD | 6 gray boxes still in Protocols: - 3.8.3 (1) - 3.8.3 (2) - 3.8.3 (3) - 3.8.3 (7) - 3.9.1 (5)(b)(i)( C ) - 3.9.1 (5)(b)(i)(N) | ERCOT would like to implement this NPRR – ideally, in conjunction with other changes to reduce cost Currently investigating possibility of including this with NPRR588/NPRR615 project – similar system components are impacted
NPRR285 | Generation Resource Base Point Deviation Charge Corrections | 11/16/2010 | WMS | TBD | Section 6.5.7.4 (e) was inadvertently un-gray-boxed when the first phase of this NPRR was implemented. This caused it to be missed as part of the second (and final) phase. The submitter has agreed it is not urgent but would like to see it implemented in 2016. | Original NPRR was $30k-$40k. ERCOT is investigating to determine the cost of the remaining deliverable. No market action requested at this time.

## Slide 8: Aging Revision Requests – ERCOT Comments and Requests for Market Input
Item | Description | Board Approval Date | Submitter | Target PPL Start Date | Comments / Questions | Status / Updates
NPRR327 | State Estimator Data Redaction Methodology | 4/17/2012 | ERCOT | Oct-2012 | This NPRR has been “On Hold” for an extended period. ERCOT has assessed the effort required to deliver and maintain this reporting and wishes to discuss the value proposition with the market. | ERCOT gating this NPRR back into Planning phase
NPRR455 | CRR Shift Factors Report | 7/17/2012 | MISUG | TBD | High cost item - market has asked that ERCOT not proceed until cost can be reduced considerably | Do not start due to high cost. Recommend CMWG review. ERCOT has re-evaluated this item to determine if more cost-effective options exist – may have results in time for PRS meeting
NPRR484 | Revisions to Congestion Revenue Rights Credit Calculations and Payments - Phase 1b / 2 | 3/19/2013 | Luminant | TBD | Only Phases 1b and 2 remain - ERCOT would like to work with the market to provide clarifications to the NPRR language. | ERCOT working with market to recommend path forward
NPRR493 | Half-Hour RUC Clawback | 3/19/2013 | GDF Suez | TBD | Not sure if still needed given other market changes that have been implemented | ERCOT working with market to recommend path forward
NPRR515 | Day-Ahead Market Self-Commitment of Generation Resources | 7/16/2013 | ERCOT | TBD | ERCOT has a revised position on this item: Recommend start in 2015 | ERCOT reported to WMS that this item can be funded with O&M funds budgeted for vendor maintenance work
NPRR664 | Index Fuel Price | 12/9/2014 | RCWG | TBD | TAC asked that ERCOT not proceed until further notice | Do not start – may be eliminated by NPRR714